

**Institute of Primate Research**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SOP No.** | **Issue Number** | **Issue Date** | **Revision Status** | **Revision Date** |
| **SOP/KIPRE/RPD/DSAS/3.1.76** | **Version 01** | **October 2025** | **-** | **-** |

**STANDARD OPERATING PROCEDURE (SOP) DOCUMENT**

**Project Performance Monitoring (M&E Framework and KPIs)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Approvals** |  |  |  |
|  | **Name** | **Signature** | **Date** |
| **Developed by:** | \_Patrick Waweru Mwaura\_ | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_6th October; 2025\_** |
|  | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** |
|  | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** |
| **Reviewed by:** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** |
| **Approved by:** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** | **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |

**Table of Contents**

[1. PURPOSE 4](#_Toc144316958)

[2. SCOPE 4](#_Toc144316959)

[3. PERSONS RESPONSIBLE: 4](#_Toc144316960)

[4. FREQUENCY 4](#_Toc144316961)

[5. MATERIALS 4](#_Toc144316962)

[6. PROCEDURE 4](#_Toc144316963)

[7. REFERENCES 7](#_Toc144316964)

# 

# PURPOSE

To standardize project performance monitoring across DS&AS-supported projects, ensuring timely evaluation against pre-defined indicators, alignment with institutional goals, and evidence-based decision-making.

# SCOPE

Applies to all research and institutional projects supported by DS&AS, from inception to completion.

# PERSONS RESPONSIBLE:

* **Project Principal Investigator (PI):** Provides project-specific indicators.
* **DS&AS M&E Officer/Analyst:** Designs M&E framework, tracks KPIs.
* **Head of DS&AS:** Approves frameworks and ensures alignment with strategy.
* **Director of Research & Product Development:** Reviews institutional-level reporting.

# FREQUENCY

* **Quarterly monitoring reports** for ongoing projects.
* **Mid-term and final evaluations** for each project.

# MATERIALS

* Project log frames (objectives, outputs, outcomes).
* KPI dashboards (R Shiny, Tableau, PowerBI).
* Institutional M&E templates.
* Data collection tools (surveys, databases, monitoring forms).

# PROCEDURE

1. **Framework Design:** DS&AS collaborates with PI to define indicators, targets, and data sources.
2. **Baseline Assessment:** Collect initial measurements before project implementation.
3. **Data Collection:** Routine monitoring of activities, outputs, and outcomes.
4. **Analysis:** DS&AS compiles KPI dashboards for project leadership.
5. **Reporting:** Quarterly and end-of-project reports submitted to PI and Directorate.
6. **Review:** Feedback incorporated into project decisions and institutional learning.

# REFERENCES