## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Function Linkage | Exptected Output | Performance Indicator | Impact | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility |  | Source of Funds
[10 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
4 | Key Result Area 4: Legal, regulatory and policy framework
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | 1. Develop and Implement Data Governance, Policies and Systems | i. Develop and review data policies and strategies | (i), (iv), (x) | Approved data governance framework and functional data systems. | No. of policies developed/reviewed; data quality and system uptime. | Improved accessibility and reliability. | 3 new policies | Singed policy documents and board meeting minutes | Gap analysis | Stakeholders input | Policy roadmap | First policy drafts | Legal review | Final revisions | Pilot rollout | Staff brieffing | Policy training | Board approval and rollout | Policy audit | Annual review |  | DSAS | RPDD | 570000
|  |  | ii. Establish data governance frameworks |  |  | No. of data governance frameworks developed. | Improved data governance. | 1 Operational framework | Terms of reference/ Charter and Governance committee/council meeting minutes. | Define roles | Form data governance committee/council | Signing of charter | Map data workflows | Assign owners | Define data standards | Workflow testing | Tools selection | Setup registry | Full adoption | Committee./council meeting | Impact report |  | DSAS | RPDD
|  |  | iii. Manage databases and data systems |  |  | No. of Databases and systems developed and managed. | Uptime and 0 data loss | 99.9% Uptime and zero data loss | System uptime reports and databases maintance logs | System audit | Resource planning | Patching cycle to ensure servers stay secure, stable and optimized | Optimization | Backup testing | Server upgrade | Load tesing | Cloud migration | Uptime check | Performance Tuning | Data cleaning | Health report |  | DSAS | RPDD and ICT
|  |  | iv. Ensure data security and integrity; |  |  | No. of data security and integrity protocols installed . | Protection againist data breaches. | 0 critical vulnerabilities | Security audit reports , pentest certificates and incident logs | Risk assessment | Access analysis and review | Security plan development | Encryption devopment | MFA(Multi factor authentication) rollout | Firewall update | Pentesting(Penetration testing). | Incident drill excerceses | Breach protocol devolopment | Final hardening of the system | Security audit | Compliance certification. |  | DSAS | RPDD and ICT
|  |  | v. Automate data collection processes. |  |  | No. of automated data collection processes developed. | Increased efficiency and speed. | 2 Key pipelines automated | System functional specifications, API documentations and UAT(User Acceptance Testing) sign-off | Addressing ID bottlenecks | Tools research | API specifications | Script coding | Integration testing | Beta testing | User trainig | Live pilot | Feedback loop | Full automation | Scalling up | ROI (Return on Investment) analysis. |  | DSAS | RPDD and ICT
|  | 2. Data Collection, Analysis and Research Support Services | i. Collect and manage data | (ii), (iii), (vi) | High-quality data analysis and research support outputs. | % of datasets with<1% error rate ; completion rate | Enhanced quality and credibility of research outputs. Ensures findings are based on clean, trustworthy data | 15 datasets archived with 100% integrity | Validation reports, Audit logs and data management plans | Tools designing | Tools piloting and testing | Ethic sycronizaion | Data collection | Real time quality control | Data indexing | Quality audit | Security check | Backup test | Final archiving | Metadata check | Data release |  | DSAS | RPDD
|  |  | ii. Analyze and interpret biological and health data |  |  | No. of reports produced with 100% accuracy score | Scientific excellence: Translate raw data into actionable insights | 12 analytical reports published/shared | Statistical reports (Bio- modelling outputs) | Logic mapping and development of SAP( Statistical analysis plans) | Development of data dictionaries | Baseline statistics | Phase 1 analysis | Phase 2 review | Interpretation | Advanced modelling | Peer validation | Trend reports | Result summaries | Data sharing | Impact reports. |  | DSAS | RPDD
|  |  | iii. Support study design and reporting |  |  | No. of protocols approved, design quality score | Methodological rigor: Increases grant success and minizes research bias. | 8 study protocols finalized and approved | IRB approval letters; final protocols | PI(s) consults | Design workshop | Protocol drafts | samples sizes determination and power analysis | IRB submission | Methodology QC | Protocol updates | Reporting specifications | Review board | Final sign- off | Result drafting | Design archives |  | DSAS | RPDD
|  |  | iv. Provide statistical and analytical support to researchers. |  |  | % Researcher satisfaction; No. of documented consults | Capacity building: Empowers researchers with advanced data literacy skills | 30 consultations; 4 training workshops | Feedback surveys; service logs; Training certificates issued. | Support portal | Service catalog | Help desk live | Workshop 1 | 1 on 1 support | Progress review | Workshop 2 | Manuscript help | Statistical coaching | Final reviews | Satisfaction poll/Survey | Service report |  | DSAS | RPDD
|  | 3. Disease Modeling, Epidemiological Analysis and Predictive Analytics | i. Conduct epidemiological studies | (vii), (viii), (xvi), (xvii), (xviii) | Disease models and predictive analytics reports. | No. of studies finalized; stakeholders adoption | Early warning: Identifies emerging health threats before they become crisis | 4 comprehensive studies completed | Published study reports ; policy briefs | Scope design | Data sourcing | Ethic sycronizaion | Fieldwork activities and data collection | Data cleaning | Preliminary report | Peer review | Revisions | Finalization | Dissemination | Policy briefs | Impact audit |  | DSAS | RPDD
|  |  | ii. Analyze disease patterns and trends; |  |  | Accuracy of trend pojections; No. of reports. | Resource allocation: Helps health officials put staff/supplies where they are needed most. | 12 monthly trend reports produced | Monthly surveillance reports; dashboards | Baseline set | Trend report 1 | Trend report 2 | Reports | Seasonal analysis | Year-end trend | Reports | Hotspot mapping | Trend review | Reports | Annual trend summaries | Performance check |  | DSAS | RPDD
|  |  | iii. Develop predictive and machine learning models |  |  | Model precision metrics ( recall, specification, sensisitivity, Brier score, ROC) ; uptime | Proactive responses: Moves public health from reactive " damage control" to proactive prevention. | 2 functional models e.g Outbreaks/ Risk/pandemic | Model source codes; technical manuals; validation reports | Use-case ID | Data cleaning | Algorithm choice | Model training | Initial testing | Model tuning | Pilot launch | Accuracy and other metric testing | API intergration | Staff training | Live rollout | Model audit |  | DSAS | RPDD
|  |  | iv. Design and assess disease control programs. |  |  | % improvement in program efficiencies | Accountability: Proves which health programs work and which need to be stopped or fixed. | 2 evaluations of diseses control programs | Evaluation reports; M&E frameworks. | Program audit | Define metrics | Survey design | Data collection | Analysis phase | Progress report | Stakeholder review | Program tuning | Final evaluation | Recommendations | Implementation | Success summary |  | DSAS | RPDD
|  | 4. Monitoring, Evaluation and Impact Assessment of Research Programs | i. Provide M&E services; evaluate research outcomes | (v), (ix) | M&E and impact assessment reports. | No. of M&E reports produced; evaluation studies completed. | Continuous improvements: Identifies program failures early to pivot strategies and save resources. | 4 comprehensive M&E reports (1 per quarter) | M&E reports, evaluation case studies | M&E plan setup | Data collection | Q1 report | Site visits | Data cleaning | Q2 report | Impact audit | Feedback loop | Q3 report | Final reviews | Outcome brief | Q4 annual summary |  | DSAS | RPDD and Planning
|  |  | ii. Assess economic and health impact of disease interventions |  |  | Measurable change in health metrics; Cost benefit ratio | Investiment justification: Provides hard data to donors and government that the research saved lives and money. | 2 impact assessment reports (e.g ROI/DALY) | Impact assessment reports; ROI models. | Define metrics | Baseline sudies | Logic models | Field surveys | Economic analysis | Interim report | Peer validation | Modelling trends | Draft assessment | Final impact documents | Policy seminar | Funding brief |  | DSAS | RPDD and Planning
|  |  | iii. Generate performance reports. |  |  | Timeliness of reports;stakeholders usage rate (%). | Operational transparency: Keeps leadership informed in real-time preventing "blind spots" in management. | 12 monthly performance dashboards. | Performance dashboard; Board minutes. | KPI (Key project indicators) definations | Dashboard setup | Septemeber report | October report | November report | Mid year review | January report | Feburuary report | March report | April report | May report | Annual performance surmmary |  | DSAS | RPDD and Planning
|  | 5. Bioinformatics, Innovation, Capacity Building and Knowledge Dissemination | i. Conduct bioinformatics and genomic analysis | (xi), (xii), (xiii), (xiv), (xv), (xix), (xx) | Advanced analytics outputs, trained staff, and publications. | No. of complex analysis performed | Precision medicine: Unlocks deep biological insights that lead to targeted , more effective health treatments. | 6 Genomic studies completed | Bio- ,Statistical reports; Processed sequence data | Samples preparation | Sequencing | Data cleaning | Primary analysis | Variant calling | Functional notes | Pathway analysis | Interpretaion | Peer review | Final report | Data submission | Results release |  | DSAS | RPDD
|  |  | ii. Develop computational tools |  |  | Tool functionality; User adoption rate (%) | Innovation: Automates complex tasks, allowing researchers to work faster and with fewer errors. | 1 new tool/pipeline launched | Software repositories (GitHub); Technical manuals | Needs audit | Tool design | Script coding | Prototype development. | Beta testing | Debugging | User trainig | Pilot launch | Optimization | Version 1.0 live | Tool support | Impact audit |  | DSAS | RPDD
|  |  | iii. Train staff and researchers |  |  | % Improvement in pre/post test scores | Sustainability: Ensures the institution is not dependent on outside consultants for technical expertise. | 150 personnel trained (4 major sessions) | Training certificates; attendance logs. | Curriulum development. | Trainer preparations (TOT). | Workshop 1 | E-learning setup | Mentorships | Workshop 2 | Advanced modules | Followup tests | Workshop 3 | Final assessment | Impact survey | Workshop 4 |  | DSAS | RPDD, Capacity directorate , ICT
|  |  | iv. Publish findings |  |  | Journal impact factor; No. of citations | Global authority: Validates research through peer review and builds the institution's reputation | 10 peer reviewed papers published | Published articles; DOI (Digital Object IDs ). | MS (Manuscript drafting) | Journal selection | Internal review | Submission | Peer feedback | Revisions | Resubmission | Galley proofing | Online release | Citations track | Media brief | Publications list |  | DSAS | RPDD, CBPGMD
|  |  | v. Support conferences and scientific dissemination. |  |  | No. of delegates quality of feedback | Knowledge exchange: connects local researchers with global experts to foster new collaborations. | 3 scientific conferences hosted/supported | Conference proceedings; Event reports | Theme selection | Call for abstracts | Speaker invites | Program finalization | Logistics | Event 1 | Abstract review | Marketing | Event 2 | Post event report | Outreach | Event 3 |  | DSAS | RPDD, Corporate Communication.

## Sheet1
Target | Activity | Subactivity | Details | Quantity | Unit price | Estimated Cost
3 New Policies | i. Develop and review data policies and strategies | Stakeholder Input & Review | Venue and refreshments for policy workshop | 2 | 85000 | 170000
|  | Policy Drafting | Consultant/Legal fee for data quality policy drafting | 1 | 400000 | 400000 | 570000
1 Operational Framework | ii. Establish data governance frameworks | Charter Development | Strategic retreat for Governance Committee (Chairs & Desks) | 1 | 250000 | 250000
|  | Board/Council Approval | Meeting allowances and printing of Terms of Reference | 4 | 30000 | 120000 | 370000
99.9% Uptime & Zero Data Loss | iii. Manage databases and data systems | Hardware Upgrade | MacBook Air M3 (For System Admins/Researchers) | 5 | 185000 | 925000
|  | Power Protection | Smart UPS 1000VA (Protecting server/workstations) | 10 | 36000 | 360000
|  | Backup Storage | 2TB External Drives (Physical backup of data systems) | 5 | 15000 | 75000
|  | Office Setup | Ergonomic Mesh Chairs & 1.5m Office Desks | 10 | 18,500 (avg) | 185000
Zero Critical Vulnerabilities | iv. Ensure data security and integrity | Vulnerability Assessment | Penetration Testing (Pen-Test) by certified Ethical Hackers | 1 | 650000 | 650000
|  | Protocol Implementation | MFA (Multi-Factor Authentication) license and setup for 60 users | 60 | 7500 | 450000
|  | Hardware Security | Next-Gen Firewall Appliance (e.g., Fortinet/Sophos) with 1yr license | 1 | 250000 | 250000
2 Key Pipelines Automated | v. Automate data collection processes | API Development | Custom API Integration for automated data sync | 1 | 550000 | 550000
|  | Staff Capacity | Data Science & ML Bootcamp (Professional training for lead team) | 5 | 185000 | 925000
Integrity-Assured Datasets | i. Collect and manage data | System Resilience | Smart UPS 1000VA (Mecer/APC) for data entry stations | 10 | 14000 | 140000
|  | Data Archiving | 2TB External Hard Drives (WD My Passport/Seagate) | 5 | 11500 | 57500
12 Analytical Reports | ii. Analyze and interpret data | Research Hardware | MacBook Air M3 13" (16GB RAM/512GB SSD) | 5 | 143000 | 715000
|  | Expert Modeling | i7/i9 High-end Tower PCs for bio-modeling | 3 | 140000 | 420000
8 Study Protocols | iii. Support study design | Collaborative Space | 1.5m Office Desks (3-drawer mahogany finish) | 10 | 10500 | 105000
|  | Ergonomic Seating | High-Back Mesh Chairs with lumbar support | 10 | 12500 | 125000
Qualified Workforce | iv. Statistical/Analytical support | Advanced Training | Data Science & ML 6-Month Bootcamp (per person) | 5 | 180000 | 900000
|  | Continuous Coaching | Monthly expert mentorship/statistical coaching sessions | 12 | 25000 | 300000
4 Comprehensive Studies | i. Conduct epidemiological studies | Data Collection Hardware | MacBook Air M3 (16GB RAM/512GB SSD) | 5 | 185000 | 925000
|  | Resilience | Smart UPS 1000VA (Mecer/APC) for workstations | 10 | 18500 | 185000
12 Monthly Trend Reports | ii. Analyze disease patterns and trends | Statistical Support | 2TB External Hard Drives (Backup of large datasets) | 5 | 14000 | 70000
2 Functional Models | iii. Develop predictive & ML models | Computational Power | i7/i9 High-end Tower PCs (GPU-accelerated for ML) | 3 | 170000 | 510000
|  | Capacity Building | Data Science & ML 6-Month Bootcamp (Specialized) | 5 | 180000 | 900000
2 Program Evaluations | iv. Design/monitor disease control programs | Office Infrastructure | 1.5m Office Desks (3-drawer finish) | 10 | 10500 | 105000
|  | Seating | High-Back Mesh Chairs with lumbar support | 10 | 12500 | 125000
|  | Monitoring Support | Monthly statistical coaching/consultancy sessions | 12 | 25000 | 300000
4 Comprehensive M&E Reports | i. Provide M&E services; evaluate research outcomes | Reporting Hardware | MacBook Air M3 (16GB RAM/512GB SSD) | 5 | 185000 | 925000
|  | Resilience | Smart UPS 1000VA (Mecer/APC) for data stations | 10 | 18500 | 185000
2 Impact Assessment Reports | ii. Assess economic and health impact of interventions | Data Archiving | 2TB External Hard Drives (Backup for ROI/DALY models) | 5 | 14000 | 70000
|  | Economic Modeling | i7/i9 High-end Tower PCs (For heavy impact modeling) | 3 | 170000 | 510000
12 Monthly Dashboards | iii. Generate real-time performance reports | Dashboard Setup | 1.5m Office Desks (3-drawer finish) | 10 | 10500 | 105000
|  | Seating | High-Back Mesh Chairs with lumbar support | 10 | 12500 | 125000
Qualified Workforce | (Combined M&E Support) | Specialized Training | Data Science & ML 6-Month Bootcamp (Impact Analytics) | 5 | 180000 | 900000
|  | Monitoring Support | Monthly statistical coaching/consultancy sessions | 12 | 25000 | 300000
8 Genomic Studies | i. Bioinformatics and genomic analysis | Sequence Analysis Hardware | i7/i9 High-end Tower PCs (GPU-accelerated for sequence data) | 3 | 170000 | 510000
|  | Power Resilience | Smart UPS 1000VA (Mecer/APC) for data stations | 10 | 18500 | 185000
3 New Tool/Pipelines | ii. Develop computational tools | Software Development | MacBook Air M3 (16GB RAM/512GB SSD) | 5 | 185000 | 925000
|  | Code Backup | 2TB External Hard Drives (Git/Local Repository Backup) | 5 | 14000 | 70000
150 Personnel Trained | iii. Train staff and researchers | Professional Development | Data Science & ML 6-Month Bootcamp (Bioinformatics focus) | 5 | 180000 | 900000
10 Peer-Reviewed Papers | iv. Publish findings | Researcher Workspace | 1.5m Office Desks (3-drawer finish) | 10 | 10500 | 105000
3 Scientific Conferences | v. Support conferences and dissemination | Knowledge Dissemination | High-Back Mesh Chairs with lumbar support | 10 | 12500 | 125000
|  | Expert Mentorship | Monthly statistical coaching/consultancy sessions | 12 | 25000 | 300000
Critical Infrastructure Budget Additions
Target | Activity | Subactivity | Item Details | Quantity | Unit Price (KES) | Estimated Cost (KES)
Scientific Excellence | V. Bioinformatics & Innovation | High-End Server Cluster | 2x AMD EPYC (64 cores), 2x RTX 4090 GPUs, 256GB RAM | 1 | 9680000 | 9680000
99.9% Uptime | I. Data Governance & Systems | Central Power Backup | Smart UPS 3KVA (For server rack protection) | 1 | 110000 | 110000
Zero Data Loss | I. Data Governance & Systems | Enterprise Virtualization | Proxmox/Docker Setup & Cloud Sync (Consultancy) | 1 | 250000 | 250000
Zero Vulnerabilities | I. Data Governance & Systems | Network Security | Firewall, VPN Setup & SSL Certificates (Annual) | 1 | 185000 | 185000
Operational Support | All Strategic Issues | Communication & Data | Mobile Data/Airtime & High-Speed MiFi Backups | 12 | 15000 | 180000
Qualified Workforce | V. Capacity Building | Strategy Retreat | Data Governance & Research Compliance Retreat | 1 | 450000 | 450000
TOTAL CRITICAL ADDITIONS | [5 empty] | 10855000