## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Exptected Output | Performance Indicator | Impact | Link to the functions | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[10 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support | Source of funding
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | Develop and implement data governance framework | 1. Conduct data governance needs assessment, 2. Establish governane structure and stakeholder engagement, 3. Develop the data governance framework, 4. Develop data policies and standard operating procedures (SOPs), 5. Implement supporting data management tools and infrastructure, 6. Conduct staff training and capacity building, 7. Pilot the governance framework, 8. Roll out framework across the KIPRE, 9. Monitor and evaluate implementation | Data governance framework developed | Number of data governance framework developed | 1. Improved data quality and standardisation, 2. Better evidence-based policy decisions, 3. Stronger data security and compliance, 4. Improved data sharing and interoperability, 5. Increased operational efficiency, 6. Stronger accountability and data owernership, 7. Enhanced institutional reputation and funding opportunities, 8. Long-term knowledge preservation. | (i) Assist in formulation, implementation, and review of policies, strategies, and guidelines on data analytics (ii) Collect, analyze, and interpret biological and health science data (iii) Support in design, development, and reporting of research studies (iv) Undertake data safeguarding and management of databases, softwares, and workflows (v) Provide monitoring and evaluation services to all research projects (vi) Collect, analyze, and interpret data across multiple research entities (vii–ix) Support disease monitoring, evaluation, and economic assessment (x) Identify valuable data sources and automate collection processes (xii–xiv) Manage genomic/proteomic and scientific data, maintain knowledge, prepare reports (xviii) Analyze large amounts of information to discover trends and patterns (xix) Conduct capacity building and mentorships in biostatistics and modeling | 1 | Approved framework document. Data inventory report. Policy and SOP documents. Data catalog system evidence. Training attendance reports. Pilot compliance audit report. Management approval minutes | Stakeholder mapping and formation of Data Governance Committee. | Institutional data inventory audit | Gap analysis (current practices vs Data Protection Act 2019, GLP, GDPR where applicable) | Draft master data governance policy (security, ownership, quality, ethics, IP) | Develop data classification framework (Public, Internal, Restricted) | Develop and validate SOPs (data capture, storage, access, retention) | Establish institutional data catalog with metadata and assigned data owners | Implement access control and security mechanisms (roles, permissions, encryption) | Conduct data literacy and security training (research and administrative staff) | Pilot project rollout (apply framework in one selected project) | Compliance audit and stress test of pilot. | Annual review, final framework revision and submission for institutional approval; Y2 scaling plan | 15 | Data Science and analystics Section | RPDD