## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Function Linkage | Exptected Output | Performance Indicator | Impact | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility |  | Source of Funds
[10 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
4 | Key Result Area 4: Legal, regulatory and policy framework
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | 1. Develop and Implement Data Governance, Policies and Systems | i. Develop and review data policies and strategies | (i), (iv), (x) | Approved data governance framework and functional data systems. | No. of policies developed/reviewed; data quality and system uptime. | Improved accessibility and reliability. | 3 policies | Singed policy documents and board meeting minutes | [12 empty] | 1000000 | DSAS | RPDD | GOK
|  |  | ii. Establish data governance frameworks |  |  | No. of data governance frameworks developed. | Improved data governance. | 1 Operational framework | Terms of reference/ Charter and Governance committee/council meeting minutes. | [12 empty] | 4000000 | DSAS | RPDD | GOK
|  |  | iii. Manage databases and data systems |  |  | No. of Databases and systems developed and managed. | Uptime and 0 data loss | 99.9% Uptime and zero data loss | System uptime reports and databases maintance logs | [12 empty] | 800000 | DSAS | RPDD and ICT | GOK
|  |  | iv. Ensure data security and integrity; |  |  | No. of data security and integrity protocols installed . | Protection againist data breaches. | 0 critical vulnerabilities; 4 Reports | Security audit reports , pentest certificates and incident logs | [12 empty] | 1100000 | DSAS | RPDD and ICT | GOK | bar: Q1 Sep; Q2 Dec; Q3 Mar; Q4 Jun
|  |  | v. Automate data collection processes. |  |  | No. of automated data collection processes developed. | Increased efficiency and speed. | 2 Key pipelines automated | System functional specifications, API documentations and UAT(User Acceptance Testing) sign-off | [12 empty] | 4000000 | DSAS | RPDD and ICT | GOK | 10900000 | bar: Q2 Oct; Q3 Feb
|  | 2. Data Collection, Analysis and Research Support Services | i. Collect and manage data | (ii), (iii), (vi) | High-quality data analysis and research support outputs. | % of datasets with<1% error rate ; completion rate | Enhanced quality and credibility of research outputs. Ensures findings are based on clean, trustworthy data | 15 datasets archived with 100% integrity | Validation reports, Audit logs and data management plans | Q1 Sep: 4; Q2 Dec: 4; Q3 Mar: 5; Q4 Jun: 4 | 750000 | DSAS | RPDD | GOK
|  |  | ii. Analyze and interpret biological and health data |  |  | No. of reports produced with 100% accuracy score | Scientific excellence: Translate raw data into actionable insights | 12 analytical reports published/shared | Statistical reports (Bio- modelling outputs) | Q2 Oct: 4; Q3 Mar: 4; Q4 Jun: 4 | 250000 | DSAS | RPDD | GOK
|  |  | iii. Support study design and reporting |  |  | No. of protocols approved, design quality score | Methodological rigor: Increases grant success and minizes research bias. | 8 study protocols finalized and approved | ISREC approval letters; final protocols | Q1 Sep: 4; Q2 Dec: 4; Q3 Mar: 4; Q4 Jun: 4 | 400000 | DSAS | RPDD | GOK
|  |  | iv. Provide statistical and analytical support to researchers. |  |  | % Researcher satisfaction; No. of documented consults | Capacity building: Empowers researchers with advanced data literacy skills | 30 consultations; 4 training workshops | Feedback surveys; service logs; Training certificates issued. | Q1 Sep: 7; Q2 Oct: Workshop 1; Q2 Dec: 10; Q3 Jan: Workshop 2; Q3 Mar: 10; Q4 May: Workshop 1; Q4 Jun: 3 | 500000 | DSAS | RPDD | GOK | 1900000
|  | 3. Disease Modeling, Epidemiological Analysis and Predictive Analytics | i. Conduct epidemiological studies | (vii), (viii), (xvi), (xvii), (xviii) | Disease models and predictive analytics reports. | No. of studies finalized; stakeholders adoption | Early warning: Identifies emerging health threats before they become crisis | 4 comprehensive studies completed | Published study reports ; policy briefs | [12 empty] | 1000000 | DSAS | RPDD | GOK | bar: Q1 Aug; Q2 Nov; Q3 Feb; Q4 Jun
|  |  | ii. Analyze disease patterns and trends; |  |  | Accuracy of trend pojections; No. of reports. | Resource allocation: Helps health officials put staff/supplies where they are needed most. | 12 monthly trend reports produced | Monthly surveillance reports; dashboards | Q2 Oct: 4; Q3 Jan: 4; Q4 May: 4 | 800000 | DSAS | RPDD | GOK
|  |  | iii. Develop predictive and machine learning models |  |  | Model precision metrics ( recall, specification, sensisitivity, Brier score, ROC) ; uptime | Proactive responses: Moves public health from reactive " damage control" to proactive prevention. | 2 functional models e.g Outbreaks/ Risk/pandemic | Model source codes; technical manuals; validation reports | [12 empty] | 1000000 | DSAS | RPDD | GOK | bar: Q2 Dec; Q4 May
|  |  | iv. Design and assess disease control programs. |  |  | % improvement in program efficiencies | Accountability: Proves which health programs work and which need to be stopped or fixed. | 2 evaluations of diseses control programs | Evaluation reports; M&E frameworks. | [12 empty] | 800000 | DSAS | RPDD | GOK | 3600000 | bar: Q2 Dec; Q4 Jun
|  | 4. Monitoring, Evaluation and Impact Assessment of Research Programs | i. Provide M&E services; evaluate research outcomes | (v), (ix) | M&E and impact assessment reports. | No. of M&E reports produced; evaluation studies completed. | Continuous improvements: Identifies program failures early to pivot strategies and save resources. | 4 comprehensive M&E reports (1 per quarter) | M&E reports, evaluation case studies | [12 empty] | 300000 | DSAS | RPDD and Planning | GOK | bar: Q1 Sep; Q2 Dec; Q3 Mar; Q4 Jun
|  |  | ii. Assess economic and health impact of disease interventions |  |  | Measurable change in health metrics; Cost benefit ratio | Investiment justification: Provides hard data to donors and government that the research saved lives and money. | 2 impact assessment reports (e.g ROI/DALY) | Impact assessment reports; ROI models. | [12 empty] | 400000 | DSAS | RPDD and Planning | GOK | bar: Q3 Jan; Q4 Jun
|  |  | iii. Generate performance reports. |  |  | Timeliness of reports;stakeholders usage rate (%). | Operational transparency: Keeps leadership informed in real-time preventing "blind spots" in management. | 12 monthly performance dashboards. | Performance dashboard; Board minutes. | Q1 Sep: 1; Q2 Dec: 5; Q3 Feb: 3; Q4 Jun: 3 | 300000 | DSAS | RPDD and Planning | GOK | 1000000
|  | 5. Bioinformatics, Innovation, Capacity Building and Knowledge Dissemination | i. Conduct bioinformatics and genomic analysis | (xi), (xii), (xiii), (xiv), (xv), (xix), (xx) | Advanced analytics outputs, trained staff, and publications. | No. of complex analysis performed | Precision medicine: Unlocks deep biological insights that lead to targeted , more effective health treatments. | 6 Genomic studies completed | Bio- ,Statistical reports; Processed sequence data | Q1 Sep: 1; Q2 Dec: 3; Q3 Mar: 2 | 10100000 | DSAS | RPDD | GOK
|  |  | ii. Develop computational tools |  |  | Tool functionality; User adoption rate (%) | Innovation: Automates complex tasks, allowing researchers to work faster and with fewer errors. | 1 new tool/pipeline launched | Software repositories (GitHub); Technical manuals | [12 empty] | 1000000 | DSAS | RPDD | GOK | bar: Q4 Apr
|  |  | iii. Train staff and researchers |  |  | % Improvement in pre/post test scores | Sustainability: Ensures the institution is not dependent on outside consultants for technical expertise. | 150 personnel trained (4 major sessions) | Training certificates; attendance logs. | Q1 Sep: 30; Q2 Dec: 60; Q4 Apr: 70 | 500000 | DSAS | RPDD, Capacity directorate , ICT | GOK
|  |  | iv. Publish findings |  |  | Journal impact factor; No. of citations | Global authority: Validates research through peer review and builds the institution's reputation | 10 peer reviewed papers published | Published articles; DOI (Digital Object IDs ). | Q1 Sep: 2; Q2 Dec: 4; Q3 Mar: 4 | 500000 | DSAS | RPDD, CBPGMD | GOK
|  |  | v. Support conferences and scientific dissemination. |  |  | No. of delegates quality of feedback | Knowledge exchange: connects local researchers with global experts to foster new collaborations. | 3 scientific conferences hosted/supported | Conference proceedings; Event reports | Q2 Dec: 2; Q4 Jun: 1 | 606500 | DSAS | RPDD, Corporate Communication. | GOK | 12706500
30106500

## Budget
Target | Activity | Subactivity | Details | Quantity | Unit price | Estimated Cost
3 New Policies | i. Develop and review data policies and strategies | Stakeholder Input & Review | Venue and refreshments for policy workshop DSA: 40 X14000, Conference: 4000 X 40 X 7 days, Transport/Fuel: 200000 | 2 | 1000000 | 2000000
|  | Policy Drafting | The total budget for a 40-person, 2-day policy workshop and drafting phase is 3,200,000, covering 1,120,000 for DSA, 480,000 for venue/refreshments, 100,000 for transport, and 1,200,000 for the consultant/legal drafting fee. | 1 | 2900000 | 2900000 | 4900000
1 Operational Framework | ii. Establish data governance frameworks | Charter Development | DSA: 20 X 14,000X5 Conference: 20 X 4,000X5 Transport/Fuel: 250,000 (lump sum) | 1 | 2050000 | 2050000
|  | Board/Council Approval | Sitting allowance: 8 X 20000X4 , Board Lunch : 2000X8X4 , Board Mileage: 50000X4, Refreshments:20000X4 , Meeting allowances and printing of Terms of Reference | 4 | 246000 | 984000 | 3034000
Zero Critical Vulnerabilities | iv. Ensure data security and integrity | Vulnerability Assessment | Penetration Testing (Pen-Test) by certified Ethical Hackers | 1 | 650000 | 650000
|  | Protocol Implementation | MFA (Multi-Factor Authentication) license and setup for 60 users | 60 | 7500 | 450000 | 1100000
2 Key Pipelines Automated | v. Automate data collection processes | API Development | Automated CSPro-REDCap integration for secure, offline-to-cloud research data pipelines. | 1 | 550000 | 550000
|  | Tablets | Mobile tablets configured for offline/online field data collection and synchronization and tools development. | 10 | 20000 | 200000
|  | Staff Capacity | Data Science & ML Bootcamp (Professional training for lead team) Conference: 4000X12X7, DSA: 12X14000X7 , Transport/Fuel: 100000 | 2 | 1512000 | 3024000 | 3774000
12 Analytical Reports | ii. Analyze and interpret data | Research Hardware | MacBook Air M3 13" (16GB RAM/512GB SSD) | 3 | 300000 | 900000
|  | Expert Modeling | i7/i9 High-end Tower PCs for bio-modeling (GPU-accelerated for ML) | 3 | 300000 | 900000 | 1800000
Qualified Workforce | iv. Statistical/Analytical support | Advanced Training | Data Science & ML 6-Month Bootcamp (per person) | 2 | 180000 | 360000
|  | Continuous Coaching | Monthly expert mentorship/statistical coaching sessions (Facilitation fee of the coach) | 12 | 25000 | 300000
|  | Capacity Building | Data Science & ML 6-Month Bootcamp (Specialized) | 2 | 250000 | 500000
|  | Monitoring Support | Monthly statistical coaching/consultancy sessions | 12 | 25000 | 300000 | 1460000
Scientific Excellence | V. Bioinformatics & Innovation | High-End Server Cluster | 2x AMD EPYC (64 cores), 2x RTX 4090 GPUs, 256GB RAM | 1 | 9680000 | 9680000 | 9680000
99.9% Uptime | I. Data Governance & Systems | Central Power Backup | Smart UPS 3KVA (For server rack protection) | 1 | 110000 | 110000 | 110000
Zero Data Loss | I. Data Governance & Systems | Enterprise Virtualization | Proxmox/Docker Setup & Cloud Sync (Consultancy) | 1 | 250000 | 250000 | 250000
Zero Vulnerabilities | I. Data Governance & Systems | Network Security | Firewall, VPN Setup & SSL Certificates (Annual) | 1 | 185000 | 185000
| I. Data Governance & Systems | Backup Storage and archiving | 2TB External Drives (Physical backup of data systems) | 7 | 15000 | 105000 | 290000
| I. Data Governance & Systems | Server intalling and nonfigurations consultations | Consultations | 2 | 750000 | 1500000 | 1500000
Cooling system | I. Data Governance & Systems | Maintenance | Server room | 1 | 400000 | 400000 | 400000
Operational Support | Operations | Communication & Data | Mobile Data/Airtime & High-Speed MiFi Backups | 12 | 15000 | 180000
| Operations | Communication & Data | Linux System Setup & Virtualization (Proxmox / Docker) | 1 | 100000 | 100000
| Operations | Communication & Data | Network & Security Setup (VPN, Firewall, SSL Certificates) | 1 | 150000 | 150000
| Operations | Communication & Data | Backup Configuration (Konza or Off-site Integration)- Archival, backup, and DR hosting | 1 | 100000 | 100000
| Operations | Communication & Data | Cable 2.5mm sq.m (E.A) (Roll) | 1 | 15000 | 15000
| Operations | Communication & Data | Cable 1.5mm sq.m (E.A) (Roll) | 1 | 12000 | 12000
| Operations | Communication & Data | 13A Socket crab Tree single (Pcs) | 1 | 300 | 300
| Operations | Communication & Data | Top Plug 13Amps (Pcs) | 1 | 200 | 200
| Operations | Communication & Data | Shallow patress Box (Pcs) | 1 | 100 | 100
| Operations | Communication & Data | Insulating tape Globe red (Pcs) | 1 | 150 | 150
| Operations | Communication & Data | 30Amps AVS sollateck (Pcs) | 1 | 9500 | 9500
| Operations | Communication & Data | Electric kettle | 1 | 5000 | 5000
| Operations | Communication & Data | CentOS / Rocky Linux Server (Base OS) | 1 | 0 | 0
| Operations | Communication & Data | VPN (Virtual Private Network) | 1 | 0 | 0
| Operations | Communication & Data | SFTP (Secure File Transfer Protocol) | 1 | 0 | 0
| Operations | Communication & Data | RBAC (Role-Based Access Control) | 1 | 0 | 0
| Operations | Communication & Data | Audit Logging & Monitoring | 1 | 0 | 0
| Operations | Communication & Data | Encryption Tools | 1 |  | 0
| Operations | Communication & Data | Industrial gloves | 1 | 1000 | 1000
| Operations | Communication & Data | Bar soap 1kg | 1 | 250 | 250
| Operations | Communication & Data | Dustbins | 1 | 200 | 200
| Operations | Communication & Data | Papertowels | 4 | 400 | 1600
| Operations | Communication & Data | Printing and duplication | 1 | 10000 | 10000
| Operations | Communication & Data | Water dispenser (Hot & Cold) | 1 | 10000 | 10000
| Operations | Communication & Data | Office desk 1.5m | 1 | 10500 | 10500
| Operations | Communication & Data | Office chairs medium, Fabric-black | 5 | 10000 | 50000
| Operations | Communication & Data | locker Steel cabinet | 1 | 10000 | 10000
| Operations | Communication & Data | Coffee table | 2 | 5000 | 10000
| Operations | Communication & Data | Mesh Office Chairs | 3 | 3000 | 9000
| Operations | Communication & Data | Dual Net face plate | 1 | 500 | 500
| Operations | Communication & Data | Single net face plate | 1 | 500 | 500
| Operations | Communication & Data | Cable label printer | 1 | 15000 | 15000
| Operations | Communication & Data | LAN Cable tester | 1 | 2000 | 2000
| Operations | Communication & Data | Access Point | 1 | 50000 | 50000
| Operations | Communication & Data | Ups for switches | 1 | 20000 | 20000
| Operations | Communication & Data | Cable ties set | 1 | 4000 | 4000
| Operations | Communication & Data | RJ45 Box | 1 | 6000 | 6000
| Operations | Communication & Data | Clips Set | 1 | 2500 | 2500
| Operations | Communication & Data | Patrice Boxes | 1 | 500 | 500
| Operations | Communication & Data | Patch Cable 1m | 1 | 700 | 700
| Operations | Communication & Data | Patch Cable 3m | 1 | 1000 | 1000
| Operations | Communication & Data | Cable organizer | 1 | 10000 | 10000
| Operations | Communication & Data | Computer Repair Tool Kit | 1 | 20000 | 20000
| Operations | Communication & Data | 38 in 1 electron screw driver set | 1 | 5000 | 5000
| Operations | Communication & Data | Computer Repair Tool Kit | 1 | 20000 | 20000
| Operations | Communication & Data | Flash Disk 16Gb | 4 | 2500 | 10000
| Operations | Communication & Data | UPS 1.5KvA | 2 | 150000 | 300000
| Operations | Communication & Data | Smart UPS 3KVA | 1 | 130000 | 130000
| Operations | Communication & Data | Office desk 1.5m | 1 | 120000 | 120000
| Operations | Communication & Data | Office chairs medium, Fabric-black | 1 | 18000 | 18000
| Operations | Communication & Data | locker Steel cabinet | 1 | 45000 | 45000
| Operations | Communication & Data | Coffee table | 1 | 60000 | 60000
| Operations | Communication & Data | Mesh Office Chairs | 3 | 25000 | 75000
| Operations | Communication & Data | Visitors Chairs | 1 | 30000 | 30000
| Operations | Communication & Data | 4 way workstation | 1 | 150000 | 150000
| Operations | Communication & Data | Office Point magnetic white board 8*4ft | 1 | 28000 | 28000 | 1808500
[6 empty] | 30106500 | 30106500

## Section functions
Section functions
(i) Assist in formulation, implementation and review of policies, strategies and guidelines on data analytics
(ii) Collect, analyze and interpret biological and health science data across multiple research entities in the institute.
(iii) Support in the design, development, and reporting of research studies
(iv) Undertake data safeguarding and management of databases, softwares and workflows
(v) Provide monitoring and evaluation services to all research projects undertaken within the institution.
(vi) Collect, analyze and interpret biological and health science data across multiple research entities in the institute.
(vii) Establish the ecological, epidemiological and natural history of a disease.
(viii) Design, monitor and assess disease control programmes.
(ix) Evaluate the effects of a disease, and analysis of the costs and economic benefits of alternative control programmes.
(x) Identify valuable data sources and automate collection processes.
(xi) Perform research and analysis on all algorithms and coordinate with various teams and provide support to various research programs
(xii) Assist scientists by providing effective analysis and feedback on all bioinformatics
(xiii) Provide training to community and analyze various genome sequencing projects for various research projects
(xiv) Manage all genomic and proteomic data and maintain knowledge on all scientific literature and prepare appropriate reports
(xv) Design various new computational tools for bioinformatics and assemble and prepare data structures and determine an effective data analysis framework.
(xvi) Build predictive models and machine-learning algorithms.
(xvii) Undertake model combinations through ensemble modeling.
(xviii) Analyze large amounts of information to discover disease trends and patterns
(xix) Conduct capacity building and mentorships in biostatistics and modeling.
(xx) Disseminate scientific findings through publications, conferences, seminars and workshops