## Strategic Issue 1
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[7 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 1: Inadequate Research and innovations for improved Human Health
Strategic Goal 1: To Promote research and innovation to address critical health challenges and improve human well-being.
1 | Key Result Area 1: Pre-clinical and translational Research for improved human health | Outcome: Pre-clinical animal models for human diseases developed
Strategic Objective 1: To conduct pre-clinical research in reproductive health, infectious and non-communicable diseases
|  | Develop non-human primate animal models for infectious diseases | Non-human primate animal models for infectious diseases developed | Percentage of preclinical animal model for infectious diseases developed | 30 | [13 empty] | 13.8 | IDOH | RPDD/ASWED
|  | Develop models for NCDs | Models for NCDs developed | Percentage of disease models developed | 30 | [13 empty] | 12.4 | NCD | RPDD
|  | Develop a baboon pre-clinical model for male contraception | Baboon pre-clinical model for male contraception developed | Percentage of phases of baboon pre-clinical male contraception experiments | 20 | [13 empty] | 28.3 | REPRO | RPDD/ASWED
Outcome: Pre-clinical studies in reproductive health, infectious and non-communicable diseases conducted
|  | Establish pre-clinical studies | Pre-clinical studies established | Percentage of pre-clinical studies established | 15 | [13 empty] | 75 | IDOH, REPRO, NCD | RPDD
|  | Establish in vitro fertilization technology laboratory for assisted reproduction | in vitro fertilization technology laboratory for assisted reproduction established | Percentage establishment of in vitro fertilization technology laboratories for assisted reproduction | 50 | [13 empty] | 1250 | REPRO | RPDD
Outcome: Improved animal health care delivery for laboratory animals
|  | Provide medical and animal welfare services for antivenom research and production | Medical and animal welfare services for antivenom research and production provided | Number of medical and animal welfare services provided for antivenom research and production | 52 | [13 empty] | 7 | K-SRIC | ASWED
|  | Acquire national and international accreditation for KIPRE | National and international accreditation for KIPRE acquired | Number of national and international accreditation for KIPRE acquired | 0 | [13 empty] | 0 | K-SRIC | ASWED
|  | Relocate, quarantine and stabilize laboratory animals to KIPRE | Laboratory animals Relocated, quarantined and stabilized at KIPRE | Number of laboratory animals Relocated, quarantined and stabilized at KIPRE | 50 | [13 empty] | 4.76 | ASWED | CSD
|  | Breed laboratory animals for biomedical research | Nonhuman primates for biomedical research bred | Number of nonhuman primates for biomedical research bred | 15 | [13 empty] | 9.74 | ASWED | CSD
|  |  | Rodents for biomedical research bred | Number of rodents for biomedical research bred | 500 | [13 empty] | 0.21 | ASWED | CSD
|  | Provide daily animal husbandry, clinical care and health monitoring | Daily animal husbandry, clinical care and health monitoring provided | Number of days animal husbandry, clinical care and health monitoring provided | 365 | [13 empty] | 24.5 | ASWED | CSD
|  | Acquire National and International regulatory and accreditation | National and International regulatory and accreditation acquired | Number of National and International regulatory and accreditation acquired | 0 | [13 empty] | 0 | ASWED | CSD
Outcome: Pre-clinical quality control laboratory for pharmaceuticals established
|  | Procure laboratory infrastructure | Laboratory infrastructure procured | Laboratory infrastructure procured | 1 | [13 empty] | 230 | DRPD | DG
|  | Develop quality standard operation procedures | Quality standard operation procedures developed | Number of quality standard operation procedures documents developed | 1 | [13 empty] | 5.65 | DRPD | DG
|  | Train quality control personnel | Quality control personnel trained | Number of quality control personnel trained | 3 | [13 empty] | 4.17 | DRPD | DG
Outcome: Candidate vaccines, drugs, biologics (e.g. antivenoms, phages and phage derivatives) and diagnostic targets for reproductive, infectious and non-infectious diseases of National priority identified and tested
Strategic Objective 2: To Identify and test candidate vaccines, drugs, biologics (e.g. antivenoms, phages) and diagnostic targets for reproductive, infectious and non-infectious diseases of National priority
|  | Identify candidate drugs, vaccines & diagnostic targets for infectious diseases | Candidate drugs, vaccines & diagnostic targets for infectious diseases identified | Number of candidate drugs, vaccines & diagnostic targets for infectious diseases identified | 2 | [13 empty] | 3.29 | IDOH | RPDD/CBPGMD
|  | Perform in vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases | In vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases performed | Number of in vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases performed | 2 | [13 empty] | 10.5 | IDOH | RPDD
|  | Technology transfer in snake venom and antivenom research and development by collaborating partner institutions | Technology transfer in snake venom and antivenom research and development by collaborating partner institutions conducted | Number of technology transfer in snake venom and antivenom research and development by collaborating partner institutions conducted | 1 | [13 empty] | 5 | K-SRIC | DRPD/CBPGMD
|  | Develop technology transfer agreements | Number of technology transfer agreements developed | Technology transfer agreements developed | 1 | [13 empty] | 18.3 | RPDD | Legal Services Directorate
|  | Develop manufacturing agreements | Manufacturing agreements developed | Number of manufacturing agreements developed | 1 | [13 empty] | 9.36 | RPDD | Legal Services Directorate
|  | Acquire equipment to facilitate identification and development of drugs, vaccines and diagnostics | Equipment to facilitate identification and development of drugs, vaccines and diagnostics acquired | Equipment to facilitate identification and development of drugs, vaccines and diagnostics acquired | 2 | [13 empty] | 5.8 | IDOH | RPDD
|  | Service equipment | Equipment serviced | Number of equipment serviced | 23 | [13 empty] | 5.97 | IDOH | RPDD
|  | Identify and test candidate antivenoms, diagnostics and other biologics for preclinical efficacy and safety | Candidate antivenoms, and other biologics identified and tested | Number of candidate antivenoms, and other biologics identified and tested | 2 | [13 empty] | 7.5 | K-SRIC | DRPD
|  | Identify and design models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production | Models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production identified and designed | Percentage of development of models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production identified and designed | 30 | [13 empty] | 3.5 | K-SRIC | DRPD
|  | Identify and test candidate antivenoms, diagnostics and other biologics for clinical efficacy and safety | Candidate antivenoms, diagnostics and other biologics identified and tested for clinical efficacy and safety | Number of candidate antivenoms, diagnostics and other biologics identified and tested for clinical efficacy and safety | 0 | [13 empty] | 0 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  | Policy briefs on scientific outcome developed | Number of policy briefs on scientific outcome developed | 1 | [13 empty] | 6 | K-SRIC | DRPD
|  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 1 | [13 empty] | 4 | K-SRIC | DRPD
|  |  | Attend local and international conferences to present research findings | Number of local and international conferences attended to present research findings | 2 | [13 empty] | 10 | K-SRIC | DRPD
Outcome: Incubation centre linking pre-clinical and clinical research to industry established with support from Intellectual property management office
Strategic Objective 3: To initiate and enhance production and commercialization capacity for quality-assured vaccines, drugs, biologics (e.g. antivenoms, phages) and diagnostics
|  | Develop and package drug, vaccine and diagnostic target for clinical studies and commercialization | Drug, vaccine and diagnostic target for clinical studies and commercialization developed and packaged | Number of drugs, vaccines and diagnostic targets for clinical studies and commercialization developed and packaged | 0 | [13 empty] | 0 | IDOH | RPDD/CBPGMD
|  | Develop candidate antivenoms and other biologics | Candidate antivenoms and other biologics developed | Number of candidate antivenoms and other biologics developed | 1 | [13 empty] | 31 | K-SRIC | DRPD
|  | Produce antivenom vials | Antivenom vials produced | Number of antivenom vials produced | 10000 | [13 empty] | 100 | K-SRIC | DRPD
|  | Distribute antivenom vials | Antivenom vials distributed | Number of antivenom vials distributed | 10000 | [13 empty] | 3 | K-SRIC | DRPD
|  | Develop candidate diagnostics for snakebite envenoming | Candidate diagnostics for snakebite envenoming developed | Percentage development of candidate diagnostics for snakebite envenoming | 20 | [13 empty] | 4.66 | K-SRIC | DRPD
|  | Prepare and Sign PIC and MAT documentations to facilitate snakebite research | PIC and MAT documentations to facilitate snakebite research prepared and signed | Percentage of prepared and signed PIC and MAT documentations to facilitate snakebite research | 20 | [13 empty] | 25 | K-SRIC | DRPD
|  | Acquire snakes of medical importance | Snakes of medical importance acquired | Number of snakes of medical importance acquired | 13 | [13 empty] | 30.5 | K-SRIC | DRPD
|  | Create venom reference standards for antivenom development and production | Venom reference standards for antivenom development and production created | Number of venom reference standards for antivenom development and production created | 4 | [13 empty] | 9.5 | K-SRIC | DRPD
|  |  | Venoms of snakes of medical importance characterized | Number of venoms of snakes of medical importance characterized | 3 | [13 empty] | 9.5 | K-SRIC | DRPD

## Strategic Issue 2
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[7 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 2: Insufficient Pandemic Preparedness, epidemiology, Biodiversity Conservation, Climate change, Environmental Antimicrobial Resistance (AMR), and Ecosystem health.
Strategic Goal 2: To strengthen global health resilience by advancing pandemic preparedness, improving epidemiological studies, climate change mitigation, sustainable biodiversity conservation and AMR stewardship.
2 | Key Result Area 2: Pandemic preparedness, disease surveillance and response through a one health approach | Outcome: Risk factors and mechanisms associated with sports and exercise injuries determined
Strategic Objective 1: To enhance surveillance of reproductive health, infectious and non-communicable diseases of public health importance
|  | Develop an injury surveillance system for sports including professional, amateur, community sports and exercise | Injury surveillance system for sports including professional, amateur, community sports and exercise developed | Number of injury surveillance systems for sports developed | 0 | [13 empty] | 0 | NCD | DRPD
|  | Conduct surveillance for determinants and mechanisms of injuries associated with sports and exercise in selected counties | Counties evaluated for prevalence, predisposing factors and mechanism of injuries in sports | Number of Counties evaluated for prevalence, predisposing factors and mechanism of injuries in sports | 2 | [13 empty] | 33.1 | NCD | DRPD
|  |  | Risk factors/ mechanisms associated with sports and exercise injuries determined | Number of risk factors/mechanisms associated with sports and exercise injuries | 1 | [13 empty] | 33.1 | NCD | DRPD
|  | Collaborate with sports academies for setting up a sports and exercise science | Collaboration for exercise and sports science established | Number of collaborations/partnerships established | 0 | [13 empty] | 0 | NCD | DRPD
Outcome: Mapped hotspot counties for snakebite and other venomous bites
Strategic Objective 2: To identify reproductive health, infectious and non-communicable diseases hotspot counties
|  | Identify and map Snakes of Medical Importance, other venomous snakes and other venomous species, map intra and inter-county snakebite hotspots in endemic counties | Counties surveyed for venomous snake identification and GIS mapping | Number of counties surveyed for venomous snake identification and GIS mapping | 7 | [13 empty] | 45 | K-SRIC | DRPD
|  | Integrate Snakebite Envenoming mapping with other NTD programs | Counties surveyed to integrate snakebite envenoming mapping with other NTD programs | Number of counties surveyed to integrate snakebite envenoming mapping with other NTD programs | 7 | [13 empty] | 20.5 | K-SRIC | DRPD
|  | Integrate Snakebite mapping with the Kenya Livestock Master Plan (KLMP) | Counties surveyed to integrate snakebite mapping with the KLMP | Number of counties surveyed to integrate snakebite mapping with the KLMP | 7 | [13 empty] | 15.5 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  | Attend local and international conferences to present research findings | Number of local and international conferences attended to present research findings | 2 | [13 empty] | 10 | K-SRIC | DRPD
|  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 2 | [13 empty] | 8 | K-SRIC | DRPD
Outcome: Infectious diseases of public health importance mapped
|  | Map counties for infectious diseases of public health importance | Counties mapped for infectious diseases of public health importance | Number of counties mapped for infectious diseases of public health importance | 1 | [13 empty] | 16.5 | IDOH & RPRO | DRPD
Outcome: Environmental, genetic, biological and behavioral risk factors for NCD prevalence identified and mapped
|  | Conduct surveillance and mapping of hotspots for environmental, genetic, biological and behavioral risk factors for NCDs in selected Counties | Surveillance and mapping of hotspots for environmental, genetic, biological and behavioral risk factors for NCDs conducted in selected Counties | Number of Counties evaluated for environmental, genetic, biological and behavioral determinants of NCDs | 2 | [13 empty] | 82.8 | NCD | DRPD
Outcome: Community engagement activities for health promotion and prevention of NCDs conducted
Strategic Objective 3: To enhance management strategies for reproductive, infectious and non-communicable diseases
|  | Develop a dissemination plan in collaboration with stakeholders for data and knowledge on NCDs | Dissemination plan in collaboration with stakeholders for data and knowledge on NCDs developed | Number of dissemination plans developed | 1 | [13 empty] | 6.15 | NCD | DRPD
|  | Conduct mass media campaigns | Mass media campaigns conducted | Number of mass media campaigns conducted | 2 | [13 empty] | 12.6 | NCD | DRPD
|  | Conduct training of Community Healthcare Practitioners (CHP) | CHPs trained | Number of CHPs trained | 200 | [13 empty] | 25.2 | NCD | DRPD
Outcome: Improved snakebite patient outcomes
|  | Conduct Research on the pathophysiology of snakebite envenoming | Research on the pathophysiology of snakebite envenoming conducted | Percentage of research studies on the pathophysiology of snakebite envenoming conducted | 20 | [13 empty] | 5 | K-SRIC | DRPD
|  | Establish snakebite units in selected counties | Snakebite units established in selected counties | Number of snakebite units established in selected counties | 1 | [13 empty] | 25 | K-SRIC | DRPD
|  | Train health care workers on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures | Health care workers trained on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures | Number of health care workers trained on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures | 100 | [13 empty] | 28 | K-SRIC | DRPD
|  | Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures | Community Health Promoters (CHPs) trained on snake species identification, snakebite diagnosis, first aid, prevention and control measures | Number of community Health Promoters (CHPs) trained on snake species identification, snakebite diagnosis, first aid, prevention and control measures | 500 | [13 empty] | 19.5 | K-SRIC | DRPD
|  | Conduct advocacy, communication and social mobilization on snake identification, snakebite first aid, prevention and control measures | Advocacy, communication, and social mobilization on snake identification, snakebite first aid, prevention and control measures conducted | Number of advocacies, communication, and social mobilization on snake identification, snakebite first aid, prevention and control measures conducted | 75 | [13 empty] | 11 | K-SRIC | DRPD
|  | Develop snakebite guidelines and policy briefs | Snakebite guidelines and policy briefs developed | Number of snakebite guidelines and policy briefs developed | 1 | [13 empty] | 6 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 2 | [13 empty] | 6 | K-SRIC | DRPD
Outcome: Community engagement activities for health promotion in reproductive health
|  | Undertake health education in reproductive health | Health education outreach sensitization programs undertaken | Number of health education sensitization meetings | 3 | [13 empty] | 3.11 | REPRO | DRPD
Outcome: Capacity of the laboratory personnel on laboratory and field skills built
Strategic Objective 4: Build capacity of the laboratory personnel on laboratory and field skills to respond to a pandemic.
|  | Develop the field and lab training modules | Developed training modules | % completion | 25 | [13 empty] | 5.5 | DCBPGM | DCS/DG
|  | Develop mentorship | Fully structured mentorship programme | No. of SOPs guidelines developed | 2 | [13 empty] | 6 | DCBPDM | DCS/DG
Outcome: Trained CHPs on detection, prevention and control zoonotic disease outbreaks using One-Health approach.
Strategic Objective 5: Train CHPs on detection, prevention and control zoonotic disease outbreaks using One-Health approach.
|  | Develop CHPs-OH training module on prevention, detection, control and response | CHPs-OH training modules developed | No. of modules developed | 3 | [13 empty] | 2.5 | IDOH | DRPD
|  |  |  | No. of workshops | 3 | [13 empty] | 4.5 | IDOH | DRPD
|  |  |  | No. of community engagements | 6 | [13 empty] | 11.5 | IDOH | DRPD
|  | Develop mentorship programs | CHPs mentorship program developed | No. of CHPs mentorship programs developed | 1 | [13 empty] | 5.5 | IDOH | DRPD
Outcome: Enhanced disease monitoring to identify and map high-risk areas to develop appropriate disease interventions identified.
Strategic Objective 6: Identify and map the high-risk areas with pandemic potentials.
|  | Identify high-risk, conduct risk assessment and map | Disease high-risk with pandemic potential mapped and shared | No. of disease risk maps generated | 1 | [13 empty] | 25.5 | IDOH | DRPD
|  |  |  | No. of disease interventions designed | 1 | [13 empty] | 17.5 | IDOH | DRPD
|  |  |  | No. of publications | 3 | [13 empty] | 1 | IDOH | DRPD
|  | Implement regular surveillance of vector populations in urban, rural and wildlife interface areas | Surveillance of vector populations regularly implemented | No. of vector-borne risk maps generated | 3 | [13 empty] | 27.5 | IDOH | DRPD
|  |  |  | No. of vector-borne interventions strategies implemented | 1 | [13 empty] | 19.2 | IDOH | DRPD
|  |  |  | No. of publications | 3 | [13 empty] | 1 | IDOH | DRPD
Outcome: Trained one-health workforce and CHPs on AMR stewardship
Strategic Objective 7: Train one-health workforce and community health promoters (CHPs) on AMR stewardship
|  | Review the AMR National Action Plan and develop training modules targeting CHPs | Comprehensive CHPs AMR modules developed & CHPs trained | No. of AMR modules developed | 3 | [13 empty] | 7.5 | CBPGMD | DRPD
|  | Train CHPs on AMR & disease risks | CHPs on AMR & disease risks trained | No. of CHPs trained on AMR & Disease risks | 130 | [13 empty] | 15 | DCBPGM | DRPD
|  |  |  | No. of one-health workforce and CHPs trained on AMR. | 20 | [13 empty] | 3.5 | DCBPGM | DRPD
Outcome: Established phage-isolation & formulation research platform
Strategic Objective 8: Establish phage-isolation & formulation research platform
|  | Identify the appropriate lab space for phage research and equip it | Lab space identified and refurbished | Lab space identified and refurbished | 1 | [13 empty] | 5.15 | RPDD | DRPD
3 | Key Result Area 3: Biodiversity conservation, ecosystem health, climate change response and awareness | Outcome: community engagement and support for biodiversity conservation and climate change initiatives, leading to improved participation in conservation strategies and implementation
Strategic Objective 1: To create public awareness, Education, and Advocacy for improved biodiversity and climate change action.
|  | Hold meetings and educational forums with the community to enhance conservation, ecosystem health, and resilience to climate change. | Improved public knowledge, attitudes and participation in conservation efforts. | Number of community members involved in conservation initiatives. | 4 | [13 empty] | 7.5 | EECEHD | DRPD
|  |  |  | Surveys on public knowledge, attitudes and practices. | 5 | [13 empty] | 8 | EECEHD | DRPD
|  | Undertake campaigns to raise awareness on conservation and public health. | Increased dissemination of conservation information. | Number of educational materials distributed | 4 | [13 empty] | 4 | EECEHD | DRPD
|  | Sensitize and educate school children to promote long-term conservation of primates and biodiversity, sustained ecosystem health, and response to climate change. | Greater youth engagement in conservation efforts. | Number of youth-oriented conservation programs implemented. | 4 | [13 empty] | 5 | EECEHD | DRPD
|  | Support initiatives that contribute towards mitigation of climate change through attaining zero-carbon pathways. | Reduced carbon emissions and increased carbon sinks. | No. of initiatives supported | 2 | [13 empty] | 4 | EECEHD | DRPD
|  | Collect and archive indigenous knowledge and practices related to conservation. | Preserved and utilized indigenous knowledge for conservation. | Documentation and use of indigenous practices in conservation. | 1 | [13 empty] | 2 | EECEHD | DRPD
|  | Conduct training programs and workshops to educate indigenous communities on sustainable resource management practices. | Sustainable resource management practices adopted. | Adoption rate of sustainable practices in communities. | 4 | [13 empty] | 3 | EECEHD | DRPD
|  | Collaborate with indigenous communities on conservation projects. | Improved livelihoods through alternative income sources. | Increase in income from alternative livelihoods. | 1 | [13 empty] | 2.5 | EECEHD | DRPD
|  | Integrate indigenous knowledge into conservation research and education. | Enhanced resilience to climate change. | Improved food security and water access metrics. | 1 | [13 empty] | 1 | EECEHD | DRPD
|  | Establish initiatives such as beekeeping, ecotourism, and tree nurseries to promote conservation while supporting alternative livelihoods. | Increased community participation in conservation efforts. | Number of community members involved in conservation initiatives. | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Implement projects to improve food security, increase water access, and restore degraded lands to build resilience and enhance adaptation to climate change. | Improved livelihoods through alternative income sources. | No. of adaptive projects implemented | 1 | [13 empty] | 5 | EECEHD | DRPD
|  | Develop policy briefs and advocate for evidence-based policies that promote primate conservation | Adoption of evidence-based conservation policies. | Policy briefs developed and policies adopted | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Facilitate knowledge exchange and collaborative projects between conservationists, policymakers, and community leaders. | Increased stakeholder engagement and knowledge exchange. | Attendance list and feedback from interdisciplinary workshops and conferences. | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Bring together experts from diverse fields to create a multidisciplinary research team and develop frameworks to tackle issues. | Enhanced interdisciplinary collaboration and integrated conservation strategies. | Number of frameworks and interdisciplinary research teams formed. | 0 | [13 empty] | 0 | EECEHD | DRPD
|  | Organize interdisciplinary workshops and conferences to foster dialogue and partnership among stakeholders. | Increased stakeholder engagement and knowledge exchange. | Attendance and feedback from interdisciplinary workshops and conferences. | 0 | [13 empty] | 0 | DDEECEHD | DRPD
|  | Establish a digital platform to enhance dissemination and application of knowledge. | Digital platform established | Knowledge base content | 0 | [13 empty] | 0 | DDEECEHD | DRPD
Outcome: Enhanced resilience, understanding, and protection of ecosystems and primate populations through effective conservation management practices, improved stakeholder collaboration, and reduced threats to primate habitats.
Strategic Objective 2: To promote primate Conservation Research and Monitoring for improved ecosystem health
|  | Conduct Primate and biodiversity surveys in unsurveyed areas to support primate & biodiversity conservation and protection. | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 1 | [13 empty] | 10 | DDEECEHD | DRPD
|  | Conduct Routine census of threatened primate species and other endangered species | Up-to-date database on primate species diversity and distribution. | Updated entries in the species database. | 1 | [13 empty] | 14.5 | DDEECEHD | DRPD
|  | Develop, maintain, and update a database on diversity, population status, and distribution of Kenyan primates. | Identification and mitigation of threats to primate habitats. | Threat assessment reports and mitigation plans. | 1 | [13 empty] | 3 | DDEECEHD | DRPD
|  | Map out the distribution of key primates and biodiversity hotspots in the country. | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 1 | [13 empty] | 5 | DDEECEHD | DRPD
|  | Assess threats to species & their habitats, develop mitigation plans, and monitor intervention impacts. | Identification and mitigation of threats to primate habitats. | Threat assessment reports and mitigation plans. | 1 | [13 empty] | 3.5 | DDEECEHD | DRPD
|  | Undertake population ecology and behavioral studies to understand species demographics and population dynamics of the endangered species. | Improved understanding of primate population dynamics and genetics. | Research publications on primate population dynamics and genetics. | 2 | [13 empty] | 6.5 | DDEECEHD | DRPD
|  | Monitor human-wildlife interactions and map out human-primate conflict hotspots. | Effective management of human-primate conflicts. | Number of human-primate conflicts resolved. | 3 | [13 empty] | 5 | DDEECEHD | DRPD
|  | Undertake primate translocations as the last option to resolve human-non-human primate conflicts and rescue threatened populations. | Effective management of human-primate conflicts. | Number of human-primate conflicts resolved. | 0 | [13 empty] | 0 | DDEECEHD | DRPD
|  | Conduct wildlife habitat research including habitat characterization, suitability assessments, food resource dynamics, and habitat changes. | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 2 | [13 empty] | 10 | DDEECEHD | DRPD
|  | Conduct primate and wildlife genomics and microbiome characterization to inform taxonomy, population differences, bottlenecks, species genetic rescue disturbances effects on primate survival, and drivers of adaptation and species survival. | Improved understanding of primate population dynamics and genetics. | Research publications on primate population dynamics and genet | 2 | [13 empty] | 10 | DDEECEHD | DRPD
Outcome: Enhanced ecosystem health and increased biodiversity, resulting in stable or growing primate populations and improved ecosystem services for local communities
Strategic Objective 3: To improve ecosystem health and restoration effort
|  | Conduct surveys and mapping to identify priority areas for restoration, focusing on habitats critical for primates, biodiversity hotspots, and regions vulnerable to climate change impacts. | Identification of priority areas for ecosystem restoration. | Number of priority areas identified and mapped. | 2 | [13 empty] | 8 | DDEECEHD | DG's office
|  | Analyze the drivers of land degradation (e.g., deforestation, overgrazing, unsustainable agriculture) and assess their impact on primate populations, biodiversity, and ecosystem services. | Reduction in land degradation and its impact. | Reports on drivers of degradation and their impacts. | 1 | [13 empty] | 10 | DDEECEHD | DG's office
|  | Evaluate the impact of different resource management practices on ecosystem services and human well-being. | Improved resource management practices and ecosystem services. | Metrics on the impact of resource management practices. | 1 | [13 empty] | 4 | DDEECEHD | DG's office
|  | Conduct workshops with local communities and other stakeholders to gather their knowledge, concerns, and priorities for incorporation in restoration and conservation strategies. | Increased local community participation in restoration efforts. | Number of community members participating in restoration. | 4 | [13 empty] | 6 | DDEECEHD | DG's office
|  | Establish community-run seed collection programs and nurseries to ensure a sustainable supply of native plants seeds for restoration efforts. | Sustainable supply of native plants for restoration. | Quantity of native plants supplied and planted. | 4 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Develop restoration plans to address the needs of threatened primates' food sources, nesting sites, and movement corridors. | Identification of priority areas for ecosystem restoration. | Number of priority areas identified and mapped | 2 | [13 empty] | 8 | DDEECEHD | DG's office
|  | Conduct nutritional and endocrinological studies in relation to animal behavior and health. | Better understanding of the nutritional and health status of primates. | Reports on zoonotic disease risks and prevention measures. | 3 | [13 empty] | 7 | DDEECEHD | DG's office
|  | Develop integrated conservation plans that incorporate ecological, social, economic and environmental perspectives. | Enhanced interdisciplinary collaboration and integrated conservation strategies. | Number of interdisciplinary research teams formed. | 3 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Conduct primate behavioral studies to understand social behavior, natural selection, individual learning, and cultural transmission. | Insights into primate social behavior and its implications for health and conservation. | Research publications on primate nutrition and endocrinology. | 1 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Conduct studies that generate actionable data and insights to conservation, public health, and climate change adaptation strategies. | Actionable data and insights for informed decision-making. | Research publications and reports generated. | 1 | [13 empty] | 5 | DDEECEHD | DG's office

## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[7 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
4 | Key Result Area 4: Legal, regulatory and policy framework | Outcome: Regulatory compliance obtained
Strategic Objective 1: To ensure regulatory compliance and develop legal provisions
|  | Regulatory compliance obtained | Obtain new regulatory compliance documents (e.g. SOPs, ISO, Policies, NEMA, DOSH, GFGP, Labs, professional) | Number of newly obtained regulatory compliance documents (e.g. SOPs, ISO, Policies, NEMA, DOSH, GFGP, Labs, professional) obtained | 2 | [13 empty] | 5 | DCS | DG's office
Outcome: Review of the KIPRE legal notice to an Act of Parliament
|  | Review of the KIPRE legal notice to an Act of Parliament | KIPRE legal notice to an Act of Parliament reviewed | KIPRE Act of Parliament | 0 | [13 empty] | 0 | DCS | DG's office
Outcome: Internal business processes reviewed and streamlined
Strategic Objective 2: To review and streamline internal business processes
|  | Develop tools of management, policies and SOPs | Management tools, policies and SOPs developed | No. management tools develop | 0 | [13 empty] | 0 | Planning & Strategy Division | All Directorates
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | Develop and implement data governance framework | Data governance framework developed | Number of data governance framework developed | 1 | Approved framework document. Data inventory report. Policy and SOP documents. Data catalog system evidence. Training attendance reports. Pilot compliance audit report. Management approval minutes | Stakeholder mapping and formation of Data Governance Committee. | Institutional data inventory audit | Gap analysis (current practices vs Data Protection Act 2019, GLP, GDPR where applicable) | Draft master data governance policy (security, ownership, quality, ethics, IP) | Develop data classification framework (Public, Internal, Restricted) | Develop and validate SOPs (data capture, storage, access, retention) | Establish institutional data catalog with metadata and assigned data owners | Implement access control and security mechanisms (roles, permissions, encryption) | Conduct data literacy and security training (research and administrative staff) | Pilot project rollout (apply framework in one selected project) | Compliance audit and stress test of pilot. | Annual review, final framework revision and submission for institutional approval; Y2 scaling plan | 0 | Data Science and analystics Section | RPDD
Outcome: Procurement management plan developed
Strategic Objective 4: To improve supply chain management
|  | Develop procurement plan | Procurement plan | No. of procurement plan developed | 1 | [13 empty] | 0.5 | SCMD | All directorates/divisions
|  | Maintain and update inventory of assets | Asset inventory updates | No of inventory of assets updated | 1 | [13 empty] | 0.01 | SCMD | SCM Head\DCS
|  | Develop and implement asset and disposal policy | Asset disposal policy operationalized | No. of assets disposed | 0 | [13 empty] | 0 | SCMD | SCM Head\DCS
|  | Tag assets using radio frequency identification (RFID) | Assets tagged reports | No of assets tagged reports | 1 | [13 empty] | 0.1 | SCMD | SCM Head\DCS
Outcome: Increased public engagement and communication
Strategic Objective 6: To engage in Corporate Social and Environmental Responsibility (CSER).
|  | Conduct scientific workshops on health research | Workshops conducted | Number of workshops conducted | 4 | [13 empty] | 1.3 | Director Research | DG's office
|  | Conduct scientific conference on health research | Conference conducted | Number of conferences conducted | 1 | [13 empty] | 20 | Director Research | DG's office
|  | Enhance Media & Digital Communication | Media and Digital communication campaigns conducted | Number of media campaigns conducted | 5 | [13 empty] | 15 | Corporate Communications | DG's office
|  |  |  | Number of blogs and articles published | 5 | [13 empty] | 1.3 | Corporate Communications | DG's office
|  | Develop Educational programs for health research | Public courses developed | Number of public courses developed | 1 | [13 empty] | 1.9 | Director Capacity Building | DG's office
|  |  | Outreach programs designed | Number of outreach programs designed | 1 | [13 empty] | 4 | Director Capacity Building | DG's office
|  |  | Education tours for high school and university students conducted | Number of education tours conducted | 4 | [13 empty] | 0.04 | Director Capacity Building | DG's office
|  | Develop interactive websites and online platform | Interactive websites developed | Number of interactive websites developed | 0 | [13 empty] | 0 | ICT | DG's office
|  |  | Online webinars and livestreams undertaken | Number of webinars and livestreams undertaken | 4 | [13 empty] | 0.26 | ICT | DG's office
Outcome: Increased engagement in Corporate Social and Environmental Responsibility (CSER)
|  | Undertake charitable activities such as tree planting, drilling boreholes for Nkare-Narok community County, donation of boat for OZI Community in Tana River County, donation of Snakebite Emergency Response System (Hot-line and Ambulance service), addressing monkey menace through relocation donation of bee-hives and nature trail fee waiver for the destitute | Charitable activities undertaken | No. of charitable activities undertaken | 1 | [13 empty] | 2 | Corporate Communication Div. | DCS
5 | Key Result Area 5: Human Resource Development | Outcome: Increased skilled and competent workforce
Strategic Objective 1: To promote public engagement and communication
|  | Establishment of reward and recognition systems | Reward and recognition system established | Reward and recognition system established | 0 | [13 empty] | 0 | DCS | All Directorates
|  | Develop sensitization programs | No. of sensitization programs | No. of sensitization activities conducted | 3 | [13 empty] | 0.01 | DCS | All Directorates
|  | Develop and implement human resource instruments | Human resource instruments developed and implemented | No. of human resource instruments developed and implemented | 0 | [13 empty] | 0 | DG | DCS
|  | Develop and implement job description manual | Job description manual developed and implemented | No. job description manuals developed and implemented | 0 | [13 empty] | 0 | DG | DCS
|  | Advertise job vacancies | Job vacancies advertised | No. of job vacancies adverts | 45 | [13 empty] | 2 | DG | DCS
|  | Shortlisting of applicant and reach out for interview | Applicants shortlisted and communicated to | No. candidates shortlisted | 45 | [13 empty] | 0.1 | DG | DCS
|  | Conduct interview and analyse candidate’s performance | Interview conducted and performance analysed | No. of candidates interviewed | 45 | [13 empty] | 0.1 | DG | DCS
|  | Carry out staff induction | Staff induction carried out | No. of staff induction programs and reports | 4 | [13 empty] | 0.01 | DCS | All Directorates
|  | Conduct correct placement and upgrading | Correct placement and staff upgrading conducted | No. of correct placements and upgrading conducted | 0 | [13 empty] | 0 | DCS | DG's office
|  | Conduct performance appraisals | No. of staff appraisal reports generated | No. of reports generated | 1 | [13 empty] | 2 | DCS | DG's office
|  | Conduct staff welfare programmes | Staff welfare programmes conducted | No. of staff welfare programmes conducted | 1 | [13 empty] | 5 | DCS | DG's office
|  | Conduct institutional management committees’ meetings, trainings and retreats | Institutional management committees’ meetings, trainings and retreats conducted | No. of meetings, trainings and retreats conducted | 96 | [13 empty] | 50 | DCS | DG's office
|  | Appraise student for top performance | Top performing students appraised | No. of students appraised as top performers | 5 | [13 empty] | 0 | DCS | DG's office
|  | Facilitate specialized training and licensing for staff | Specialized training and licensing for staff facilitate | No. of training and licensing for staff facilitated | 25 | [13 empty] | 5 | DCS | DG's office
|  | Conduct and implement training needs assessment | Training needs assessment conducted and implemented | Training needs assessment | 1 | [13 empty] | 2 | DCS | ALL Directorates
|  | Strengthen employees’ relations | Employees relations strengthened | % of employees relations | 100 | [13 empty] | 2 | DCS | All Directorates
|  | Regularly Review organization establishment, grading and pay structure | Organization establishment, grading and pay structure reviewed | No. of review reports | 1 | [13 empty] | 2 | DG | DCS
|  | Training professionals | Training of professionals conducted | % of professionals trained | 100 | [13 empty] | 1 | DCS | ALL Directorates
6 | Key Result Area 6: Infrastructure and equipment | Outcome: Infrastructure upgraded
Strategic Objective 1: To construct and upgrade infrastructure for health Research Excellence
|  | Upgrade the research laboratory facilities to meet the set standards | Research Laboratory facilities Expanded | Number of Research Laboratory facilities Expanded | 2 | [13 empty] | 0.8 | DG | SCM Head/DCS
|  | Procure laboratory and office equipment | Research Laboratory and office equipment procured | Number of Research Laboratory Equipment procured | 2 | [13 empty] | 5 | DG | SCM Head/ All Directorates
|  | Upgrade staff offices and facilities | Staff offices and facilities expanded | No. of staff offices and facilities expanded | 2 | [13 empty] | 2 | DG | SCM Head/ DCS
|  | Facilitate audit of the research laboratory facilities | Audit of the research laboratory facilities | Number of audit report | 2 | [13 empty] | 0.5 | DG | DCS/ Audit Head
|  | Acquire Service contracts of the research laboratory equipment | Service contracts of the research laboratory equipment acquired | Number Service contracts of the research laboratory equipment acquired | 2 | [13 empty] | 5 | DG | SCM Head \DCS/ Corporation Secretary
|  | Increase number of the fleet for research | Vehicles and motorbikes acquired | Number of vehicles and motor vehicles acquired | 2 | [13 empty] | 16 | DCS | SCM Head
|  | Removal of asbestos from building | Asbestos removed from buildings | No. buildings refurbished (asbestos removed) | 4 | [13 empty] | 250 | DCS | SCM Head
|  | Establish a training center for biomedical research, pre-clinical and clinical research | Training center established | No. of training center | 0 | [13 empty] | 0 | DCS & DCB | SCM Head
|  | Installation of CO2 and liquid Nitrogen generation plants | CO2 and Liquid Nitrogen plants installed | No. of plants installed | 1 | [13 empty] | 100 | DR&PD | DCS
Outcome: Technologies Installed
|  | Upgrade ICT infrastructure | ICT infrastructure upgraded | Number of upgraded ICT infrastructure | 6 | [13 empty] | 14 | DCS | SCM Head
Outcome: Field research station infrastructural facility constructed
|  |  |  | No. of field research activities | 1 | [13 empty] | 20 | KESRIC, | DG
Outcome: Green energy technology installed
Strategic Objective 5: To invest in green energy technology
|  | Installation of green energy technology (Solar) | Green energy technology installed | No of green energy technology installed | 1 | [13 empty] | 5 | DG | DCS/SCM Head
7 | Key Result Area 7: Research collaborations and partnerships | Outcome: Increased number of collaborators and partners
Strategic Objective1: To increase the number of collaborations and partnerships
|  | Establish local and international partnerships and collaborations | Partnerships and collaborations established | Number of partnerships and collaborations established | 14 | [13 empty] | 19.416 | DCBPGM | DRPD

## Strategic Issue 4
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[7 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 4: Inadequate Financial support for health research & Innovation
Strategic Goal 4: To secure funding to sustain health research and innovation whilst ensuring efficient use of KIPRE finances.
8 | Key Result Area 8: Advocacy and engagement of the government for increased research funding | Outcome: Increased research funding from government
Strategic Objective 1: Formulate and implement favorable, well aligned health research & management policies
|  | Developing strategic plan as per the guidelines | Approved strategic plan | Approved strategic plan | 0 | [13 empty] | 0 | Planning and Strategy Division | Heads of Directorates/divisions
|  | Developing Institutional workplan | Approved institutional workplan | Number of institutional work plans | 1 | [13 empty] | 15.9 | Planning and Strategy Division | Heads of Directorates/divisions, MOH, TNT
|  | Develop Institutional Performance contract as per the guidelines | Approved Institutional Performance contract | Approved Institutional Performance contract | 1 | [13 empty] | 13.2 | Planning and Strategy Division | Heads of Directorates/divisions, MOH, TNT
|  | Develop advocacy strategy | Advocacy strategy developed | Number of advocacy strategies developed | 0 | [13 empty] | 0 | DRPD | Deputy Directors
|  | Conduct advocacy for funding of research and development | Advocacy for funding of research and development conducted | Number of advocacy activities for funding of research and development conducted | 11 | [13 empty] | 53.1 | DRPD | Director Research & Product Development (DRPD), DDFA
|  | Hold consultative meetings to advocate for more resources towards health research | Consultative meetings held | Number of consultative meetings held | 1 | [13 empty] | 4 | Planning & Strategy | Head of Divisions, MOH, TNT
9 | Key Result Area 9: Diversified funding streams | Outcome: Increased revenue generation
Strategic Objective 3: Mobilize and manage financial resources
|  | Develop a Resource Mobilization strategy | Resource mobilization strategy | Approved Resource Mobilization strategy | 1 | [13 empty] | 25 | FAD | Heads of Directorates & Divisions
Outcome: Cost saving measures implemented
Strategic Objective 3: Implement cost saving measures
|  | Regular financial reviews | Quarterly Financial reports developed | financial reports | 4 | [13 empty] | 0 | Finance
|  | Conduct internal finance audits | Quarterly risk assessment reports developed | Risk assessment reports | 4 | [13 empty] | 1.33 | Audit | All Directors
|  |  | Annual internal audit reports developed | Audit reports | 1 | [13 empty] | 0 | Audit | Finance
|  | Automation of Revenue collection | Finance and accounts ERP module procured | Finance and Accounts ERP module | 0 | [13 empty] | 0 | ICT | Finance
|  | Maintenance and upgrading of ERP- finance module | ERP-finance module maintained and upgraded | Maintenance and upgrade reports | 4 | [13 empty] | 2 | ICT | Finance
10 | Key Result Area 10: Efficient resource Utilization | Outcome: Effective management of projects & initiatives and accurate assessment of their impacts
Strategic Objective 1: Integrate planning, Monitoring & Evaluation (PM&E) programs and process
|  | Developing and disseminating PM&E SOPs | Performance, Monitoring & Evaluation SOPs developed and disseminated | Number of Performance, monitoring & Evaluation SOPs developed and disseminated | 0 | [13 empty] | 0 | Planning & strategy | Heads of Directorates/Divisions
|  | Develop a comprehensive PM&E framework | Performance, Monitoring & Evaluation framework developed | Number of performance, monitoring & evaluation framework developed | 0 | [13 empty] | 0 | Planning & strategy | Heads of Directorates/Divisions
|  | Mid & End term review of the strategic plan | Reviewed Mid & End term strategic plan | Number of review reports submitted | 1 | [13 empty] | 12 | Planning & strategy | Heads of Directorates/Divisions
|  | Conduct annual performance review | Annual performance review conducted | Annual performance review report submitted | 1 | [13 empty] | 3.5 | Planning & strategy | Heads of Directorates/Divisions