## Strategic Issue 1
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[8 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 1: Inadequate Research and innovations for improved Human Health
Strategic Goal 1: To Promote research and innovation to address critical health challenges and improve human well-being.
1 | Key Result Area 1: Pre-clinical and translational Research for improved human health | Outcome: Pre-clinical animal models for human diseases developed
Strategic Objective 1: To conduct pre-clinical research in reproductive health, infectious and non-communicable diseases
|  | Develop non-human primate animal models for infectious diseases |  | Non-human primate animal models for infectious diseases developed | Percentage of preclinical animal model for infectious diseases developed | 30 | [13 empty] | 13.8 | IDOH | RPDD/ASWED
|  | Develop models for NCDs |  | Models for NCDs developed | Percentage of disease models developed | 30 | [13 empty] | 12.4 | NCD | RPDD
|  | Develop a baboon pre-clinical model for male contraception |  | Baboon pre-clinical model for male contraception developed | Percentage of phases of baboon pre-clinical male contraception experiments | 20 | [13 empty] | 28.3 | REPRO | RPDD/ASWED
Outcome: Pre-clinical studies in reproductive health, infectious and non-communicable diseases conducted
|  | Establish pre-clinical studies |  | Pre-clinical studies established | Percentage of pre-clinical studies established | 15 | [13 empty] | 75 | IDOH, REPRO, NCD | RPDD
|  | Establish in vitro fertilization technology laboratory for assisted reproduction |  | in vitro fertilization technology laboratory for assisted reproduction established | Percentage establishment of in vitro fertilization technology laboratories for assisted reproduction | 50 | [13 empty] | 1250 | REPRO | RPDD
Outcome: Improved animal health care delivery for laboratory animals
|  | Provide medical and animal welfare services for antivenom research and production |  | Medical and animal welfare services for antivenom research and production provided | Number of medical and animal welfare services provided for antivenom research and production | 52 | [13 empty] | 7 | K-SRIC | ASWED
|  | Acquire national and international accreditation for KIPRE |  | National and international accreditation for KIPRE acquired | Number of national and international accreditation for KIPRE acquired | 0 | [13 empty] | 0 | K-SRIC | ASWED
|  | Relocate, quarantine and stabilize laboratory animals to KIPRE |  | Laboratory animals Relocated, quarantined and stabilized at KIPRE | Number of laboratory animals Relocated, quarantined and stabilized at KIPRE | 50 | [13 empty] | 4.76 | ASWED | CSD
|  | Breed laboratory animals for biomedical research |  | Nonhuman primates for biomedical research bred | Number of nonhuman primates for biomedical research bred | 15 | [13 empty] | 9.74 | ASWED | CSD
|  |  |  | Rodents for biomedical research bred | Number of rodents for biomedical research bred | 500 | [13 empty] | 0.21 | ASWED | CSD
|  | Provide daily animal husbandry, clinical care and health monitoring |  | Daily animal husbandry, clinical care and health monitoring provided | Number of days animal husbandry, clinical care and health monitoring provided | 365 | [13 empty] | 24.5 | ASWED | CSD
|  | Acquire National and International regulatory and accreditation |  | National and International regulatory and accreditation acquired | Number of National and International regulatory and accreditation acquired | 0 | [13 empty] | 0 | ASWED | CSD
Outcome: Pre-clinical quality control laboratory for pharmaceuticals established
|  | Procure laboratory infrastructure |  | Laboratory infrastructure procured | Laboratory infrastructure procured | 1 | [13 empty] | 230 | DRPD | DG
|  | Develop quality standard operation procedures |  | Quality standard operation procedures developed | Number of quality standard operation procedures documents developed | 1 | [13 empty] | 5.65 | DRPD | DG
|  | Train quality control personnel |  | Quality control personnel trained | Number of quality control personnel trained | 3 | [13 empty] | 4.17 | DRPD | DG
Outcome: Candidate vaccines, drugs, biologics (e.g. antivenoms, phages and phage derivatives) and diagnostic targets for reproductive, infectious and non-infectious diseases of National priority identified and tested
Strategic Objective 2: To Identify and test candidate vaccines, drugs, biologics (e.g. antivenoms, phages) and diagnostic targets for reproductive, infectious and non-infectious diseases of National priority
|  | Identify candidate drugs, vaccines & diagnostic targets for infectious diseases |  | Candidate drugs, vaccines & diagnostic targets for infectious diseases identified | Number of candidate drugs, vaccines & diagnostic targets for infectious diseases identified | 2 | [13 empty] | 3.29 | IDOH | RPDD/CBPGMD
|  | Perform in vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases |  | In vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases performed | Number of in vivo pre-clinical testing of candidate drugs, vaccines and diagnostic targets for infectious diseases performed | 2 | [13 empty] | 10.5 | IDOH | RPDD
|  | Technology transfer in snake venom and antivenom research and development by collaborating partner institutions |  | Technology transfer in snake venom and antivenom research and development by collaborating partner institutions conducted | Number of technology transfer in snake venom and antivenom research and development by collaborating partner institutions conducted | 1 | [13 empty] | 5 | K-SRIC | DRPD/CBPGMD
|  | Develop technology transfer agreements |  | Number of technology transfer agreements developed | Technology transfer agreements developed | 1 | [13 empty] | 18.3 | RPDD | Legal Services Directorate
|  | Develop manufacturing agreements |  | Manufacturing agreements developed | Number of manufacturing agreements developed | 1 | [13 empty] | 9.36 | RPDD | Legal Services Directorate
|  | Acquire equipment to facilitate identification and development of drugs, vaccines and diagnostics |  | Equipment to facilitate identification and development of drugs, vaccines and diagnostics acquired | Equipment to facilitate identification and development of drugs, vaccines and diagnostics acquired | 2 | [13 empty] | 5.8 | IDOH | RPDD
|  | Service equipment |  | Equipment serviced | Number of equipment serviced | 23 | [13 empty] | 5.97 | IDOH | RPDD
|  | Identify and test candidate antivenoms, diagnostics and other biologics for preclinical efficacy and safety |  | Candidate antivenoms, and other biologics identified and tested | Number of candidate antivenoms, and other biologics identified and tested | 2 | [13 empty] | 7.5 | K-SRIC | DRPD
|  | Identify and design models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production |  | Models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production identified and designed | Percentage of development of models to refine, reduce, and replace animals for preclinical research in venom and antivenoms production identified and designed | 30 | [13 empty] | 3.5 | K-SRIC | DRPD
|  | Identify and test candidate antivenoms, diagnostics and other biologics for clinical efficacy and safety |  | Candidate antivenoms, diagnostics and other biologics identified and tested for clinical efficacy and safety | Number of candidate antivenoms, diagnostics and other biologics identified and tested for clinical efficacy and safety | 0 | [13 empty] | 0 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders |  | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  |  | Policy briefs on scientific outcome developed | Number of policy briefs on scientific outcome developed | 1 | [13 empty] | 6 | K-SRIC | DRPD
|  |  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 1 | [13 empty] | 4 | K-SRIC | DRPD
|  |  |  | Attend local and international conferences to present research findings | Number of local and international conferences attended to present research findings | 2 | [13 empty] | 10 | K-SRIC | DRPD
Outcome: Incubation centre linking pre-clinical and clinical research to industry established with support from Intellectual property management office
Strategic Objective 3: To initiate and enhance production and commercialization capacity for quality-assured vaccines, drugs, biologics (e.g. antivenoms, phages) and diagnostics
|  | Develop and package drug, vaccine and diagnostic target for clinical studies and commercialization |  | Drug, vaccine and diagnostic target for clinical studies and commercialization developed and packaged | Number of drugs, vaccines and diagnostic targets for clinical studies and commercialization developed and packaged | 0 | [13 empty] | 0 | IDOH | RPDD/CBPGMD
|  | Develop candidate antivenoms and other biologics |  | Candidate antivenoms and other biologics developed | Number of candidate antivenoms and other biologics developed | 1 | [13 empty] | 31 | K-SRIC | DRPD
|  | Produce antivenom vials |  | Antivenom vials produced | Number of antivenom vials produced | 10000 | [13 empty] | 100 | K-SRIC | DRPD
|  | Distribute antivenom vials |  | Antivenom vials distributed | Number of antivenom vials distributed | 10000 | [13 empty] | 3 | K-SRIC | DRPD
|  | Develop candidate diagnostics for snakebite envenoming |  | Candidate diagnostics for snakebite envenoming developed | Percentage development of candidate diagnostics for snakebite envenoming | 20 | [13 empty] | 4.66 | K-SRIC | DRPD
|  | Prepare and Sign PIC and MAT documentations to facilitate snakebite research |  | PIC and MAT documentations to facilitate snakebite research prepared and signed | Percentage of prepared and signed PIC and MAT documentations to facilitate snakebite research | 20 | [13 empty] | 25 | K-SRIC | DRPD
|  | Acquire snakes of medical importance |  | Snakes of medical importance acquired | Number of snakes of medical importance acquired | 13 | [13 empty] | 30.5 | K-SRIC | DRPD
|  | Create venom reference standards for antivenom development and production |  | Venom reference standards for antivenom development and production created | Number of venom reference standards for antivenom development and production created | 4 | [13 empty] | 9.5 | K-SRIC | DRPD
|  |  |  | Venoms of snakes of medical importance characterized | Number of venoms of snakes of medical importance characterized | 3 | [13 empty] | 9.5 | K-SRIC | DRPD

## Strategic Issue 2
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[8 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 2: Insufficient Pandemic Preparedness, epidemiology, Biodiversity Conservation, Climate change, Environmental Antimicrobial Resistance (AMR), and Ecosystem health.
Strategic Goal 2: To strengthen global health resilience by advancing pandemic preparedness, improving epidemiological studies, climate change mitigation, sustainable biodiversity conservation and AMR stewardship.
2 | Key Result Area 2: Pandemic preparedness, disease surveillance and response through a one health approach | Outcome: Risk factors and mechanisms associated with sports and exercise injuries determined
Strategic Objective 1: To enhance surveillance of reproductive health, infectious and non-communicable diseases of public health importance
|  | Develop an injury surveillance system for sports including professional, amateur, community sports and exercise |  | Injury surveillance system for sports including professional, amateur, community sports and exercise developed | Number of injury surveillance systems for sports developed | 0 | [13 empty] | 0 | NCD | DRPD
|  | Conduct surveillance for determinants and mechanisms of injuries associated with sports and exercise in selected counties |  | Counties evaluated for prevalence, predisposing factors and mechanism of injuries in sports | Number of Counties evaluated for prevalence, predisposing factors and mechanism of injuries in sports | 2 | [13 empty] | 33.1 | NCD | DRPD
|  |  |  | Risk factors/ mechanisms associated with sports and exercise injuries determined | Number of risk factors/mechanisms associated with sports and exercise injuries | 1 | [13 empty] | 33.1 | NCD | DRPD
|  | Collaborate with sports academies for setting up a sports and exercise science |  | Collaboration for exercise and sports science established | Number of collaborations/partnerships established | 0 | [13 empty] | 0 | NCD | DRPD
Outcome: Mapped hotspot counties for snakebite and other venomous bites
Strategic Objective 2: To identify reproductive health, infectious and non-communicable diseases hotspot counties
|  | Identify and map Snakes of Medical Importance, other venomous snakes and other venomous species, map intra and inter-county snakebite hotspots in endemic counties |  | Counties surveyed for venomous snake identification and GIS mapping | Number of counties surveyed for venomous snake identification and GIS mapping | 7 | [13 empty] | 45 | K-SRIC | DRPD
|  | Integrate Snakebite Envenoming mapping with other NTD programs |  | Counties surveyed to integrate snakebite envenoming mapping with other NTD programs | Number of counties surveyed to integrate snakebite envenoming mapping with other NTD programs | 7 | [13 empty] | 20.5 | K-SRIC | DRPD
|  | Integrate Snakebite mapping with the Kenya Livestock Master Plan (KLMP) |  | Counties surveyed to integrate snakebite mapping with the KLMP | Number of counties surveyed to integrate snakebite mapping with the KLMP | 7 | [13 empty] | 15.5 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders |  | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  |  | Attend local and international conferences to present research findings | Number of local and international conferences attended to present research findings | 2 | [13 empty] | 10 | K-SRIC | DRPD
|  |  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 2 | [13 empty] | 8 | K-SRIC | DRPD
Outcome: Infectious diseases of public health importance mapped
|  | Map counties for infectious diseases of public health importance |  | Counties mapped for infectious diseases of public health importance | Number of counties mapped for infectious diseases of public health importance | 1 | [13 empty] | 16.5 | IDOH & RPRO | DRPD
Outcome: Environmental, genetic, biological and behavioral risk factors for NCD prevalence identified and mapped
|  | Conduct surveillance and mapping of hotspots for environmental, genetic, biological and behavioral risk factors for NCDs in selected Counties |  | Surveillance and mapping of hotspots for environmental, genetic, biological and behavioral risk factors for NCDs conducted in selected Counties | Number of Counties evaluated for environmental, genetic, biological and behavioral determinants of NCDs | 2 | [13 empty] | 82.8 | NCD | DRPD
Outcome: Community engagement activities for health promotion and prevention of NCDs conducted
Strategic Objective 3: To enhance management strategies for reproductive, infectious and non-communicable diseases
|  | Develop a dissemination plan in collaboration with stakeholders for data and knowledge on NCDs |  | Dissemination plan in collaboration with stakeholders for data and knowledge on NCDs developed | Number of dissemination plans developed | 1 | [13 empty] | 6.15 | NCD | DRPD
|  | Conduct mass media campaigns |  | Mass media campaigns conducted | Number of mass media campaigns conducted | 2 | [13 empty] | 12.6 | NCD | DRPD
|  | Conduct training of Community Healthcare Practitioners (CHP) |  | CHPs trained | Number of CHPs trained | 200 | [13 empty] | 25.2 | NCD | DRPD
Outcome: Improved snakebite patient outcomes
|  | Conduct Research on the pathophysiology of snakebite envenoming |  | Research on the pathophysiology of snakebite envenoming conducted | Percentage of research studies on the pathophysiology of snakebite envenoming conducted | 20 | [13 empty] | 5 | K-SRIC | DRPD
|  | Establish snakebite units in selected counties |  | Snakebite units established in selected counties | Number of snakebite units established in selected counties | 1 | [13 empty] | 25 | K-SRIC | DRPD
|  | Train health care workers on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures |  | Health care workers trained on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures | Number of health care workers trained on snakebite diagnosis, management, antivenoms administration and snakebite prevention and control measures | 100 | [13 empty] | 28 | K-SRIC | DRPD
|  | Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures |  | Community Health Promoters (CHPs) trained on snake species identification, snakebite diagnosis, first aid, prevention and control measures | Number of community Health Promoters (CHPs) trained on snake species identification, snakebite diagnosis, first aid, prevention and control measures | 500 | [13 empty] | 19.5 | K-SRIC | DRPD
|  | Conduct advocacy, communication and social mobilization on snake identification, snakebite first aid, prevention and control measures |  | Advocacy, communication, and social mobilization on snake identification, snakebite first aid, prevention and control measures conducted | Number of advocacies, communication, and social mobilization on snake identification, snakebite first aid, prevention and control measures conducted | 75 | [13 empty] | 11 | K-SRIC | DRPD
|  | Develop snakebite guidelines and policy briefs |  | Snakebite guidelines and policy briefs developed | Number of snakebite guidelines and policy briefs developed | 1 | [13 empty] | 6 | K-SRIC | DRPD
|  | Disseminate research outputs to various stakeholders |  | Scientific manuscripts in peer-reviewed journals published | Number of scientific manuscripts in peer-reviewed journals published | 1 | [13 empty] | 0.5 | K-SRIC | DRPD
|  |  |  | Technical working group meetings attended and coordinated | Number of technical working group meetings attended and coordinated | 2 | [13 empty] | 6 | K-SRIC | DRPD
Outcome: Community engagement activities for health promotion in reproductive health
|  | Undertake health education in reproductive health |  | Health education outreach sensitization programs undertaken | Number of health education sensitization meetings | 3 | [13 empty] | 3.11 | REPRO | DRPD
Outcome: Capacity of the laboratory personnel on laboratory and field skills built
Strategic Objective 4: Build capacity of the laboratory personnel on laboratory and field skills to respond to a pandemic.
|  | Develop the field and lab training modules |  | Developed training modules | % completion | 25 | [13 empty] | 5.5 | DCBPGM | DCS/DG
|  | Develop mentorship |  | Fully structured mentorship programme | No. of SOPs guidelines developed | 2 | [13 empty] | 6 | DCBPDM | DCS/DG
Outcome: Trained CHPs on detection, prevention and control zoonotic disease outbreaks using One-Health approach.
Strategic Objective 5: Train CHPs on detection, prevention and control zoonotic disease outbreaks using One-Health approach.
|  | Develop CHPs-OH training module on prevention, detection, control and response |  | CHPs-OH training modules developed | No. of modules developed | 3 | [13 empty] | 2.5 | IDOH | DRPD
[5 empty] | No. of workshops | 3 | [13 empty] | 4.5 | IDOH | DRPD
[5 empty] | No. of community engagements | 6 | [13 empty] | 11.5 | IDOH | DRPD
|  | Develop mentorship programs |  | CHPs mentorship program developed | No. of CHPs mentorship programs developed | 1 | [13 empty] | 5.5 | IDOH | DRPD
Outcome: Enhanced disease monitoring to identify and map high-risk areas to develop appropriate disease interventions identified.
Strategic Objective 6: Identify and map the high-risk areas with pandemic potentials.
|  | Identify high-risk, conduct risk assessment and map |  | Disease high-risk with pandemic potential mapped and shared | No. of disease risk maps generated | 1 | [13 empty] | 25.5 | IDOH | DRPD
[5 empty] | No. of disease interventions designed | 1 | [13 empty] | 17.5 | IDOH | DRPD
[5 empty] | No. of publications | 3 | [13 empty] | 1 | IDOH | DRPD
|  | Implement regular surveillance of vector populations in urban, rural and wildlife interface areas |  | Surveillance of vector populations regularly implemented | No. of vector-borne risk maps generated | 3 | [13 empty] | 27.5 | IDOH | DRPD
[5 empty] | No. of vector-borne interventions strategies implemented | 1 | [13 empty] | 19.2 | IDOH | DRPD
[5 empty] | No. of publications | 3 | [13 empty] | 1 | IDOH | DRPD
Outcome: Trained one-health workforce and CHPs on AMR stewardship
Strategic Objective 7: Train one-health workforce and community health promoters (CHPs) on AMR stewardship
|  | Review the AMR National Action Plan and develop training modules targeting CHPs |  | Comprehensive CHPs AMR modules developed & CHPs trained | No. of AMR modules developed | 3 | [13 empty] | 7.5 | CBPGMD | DRPD
|  | Train CHPs on AMR & disease risks |  | CHPs on AMR & disease risks trained | No. of CHPs trained on AMR & Disease risks | 130 | [13 empty] | 15 | DCBPGM | DRPD
[5 empty] | No. of one-health workforce and CHPs trained on AMR. | 20 | [13 empty] | 3.5 | DCBPGM | DRPD
Outcome: Established phage-isolation & formulation research platform
Strategic Objective 8: Establish phage-isolation & formulation research platform
|  | Identify the appropriate lab space for phage research and equip it |  | Lab space identified and refurbished | Lab space identified and refurbished | 1 | [13 empty] | 5.15 | RPDD | DRPD
3 | Key Result Area 3: Biodiversity conservation, ecosystem health, climate change response and awareness | Outcome: community engagement and support for biodiversity conservation and climate change initiatives, leading to improved participation in conservation strategies and implementation
Strategic Objective 1: To create public awareness, Education, and Advocacy for improved biodiversity and climate change action.
|  | Hold meetings and educational forums with the community to enhance conservation, ecosystem health, and resilience to climate change. |  | Improved public knowledge, attitudes and participation in conservation efforts. | Number of community members involved in conservation initiatives. | 4 | [13 empty] | 7.5 | EECEHD | DRPD
[5 empty] | Surveys on public knowledge, attitudes and practices. | 5 | [13 empty] | 8 | EECEHD | DRPD
|  | Undertake campaigns to raise awareness on conservation and public health. |  | Increased dissemination of conservation information. | Number of educational materials distributed | 4 | [13 empty] | 4 | EECEHD | DRPD
|  | Sensitize and educate school children to promote long-term conservation of primates and biodiversity, sustained ecosystem health, and response to climate change. |  | Greater youth engagement in conservation efforts. | Number of youth-oriented conservation programs implemented. | 4 | [13 empty] | 5 | EECEHD | DRPD
|  | Support initiatives that contribute towards mitigation of climate change through attaining zero-carbon pathways. |  | Reduced carbon emissions and increased carbon sinks. | No. of initiatives supported | 2 | [13 empty] | 4 | EECEHD | DRPD
|  | Collect and archive indigenous knowledge and practices related to conservation. |  | Preserved and utilized indigenous knowledge for conservation. | Documentation and use of indigenous practices in conservation. | 1 | [13 empty] | 2 | EECEHD | DRPD
|  | Conduct training programs and workshops to educate indigenous communities on sustainable resource management practices. |  | Sustainable resource management practices adopted. | Adoption rate of sustainable practices in communities. | 4 | [13 empty] | 3 | EECEHD | DRPD
|  | Collaborate with indigenous communities on conservation projects. |  | Improved livelihoods through alternative income sources. | Increase in income from alternative livelihoods. | 1 | [13 empty] | 2.5 | EECEHD | DRPD
|  | Integrate indigenous knowledge into conservation research and education. |  | Enhanced resilience to climate change. | Improved food security and water access metrics. | 1 | [13 empty] | 1 | EECEHD | DRPD
|  | Establish initiatives such as beekeeping, ecotourism, and tree nurseries to promote conservation while supporting alternative livelihoods. |  | Increased community participation in conservation efforts. | Number of community members involved in conservation initiatives. | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Implement projects to improve food security, increase water access, and restore degraded lands to build resilience and enhance adaptation to climate change. |  | Improved livelihoods through alternative income sources. | No. of adaptive projects implemented | 1 | [13 empty] | 5 | EECEHD | DRPD
|  | Develop policy briefs and advocate for evidence-based policies that promote primate conservation |  | Adoption of evidence-based conservation policies. | Policy briefs developed and policies adopted | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Facilitate knowledge exchange and collaborative projects between conservationists, policymakers, and community leaders. |  | Increased stakeholder engagement and knowledge exchange. | Attendance list and feedback from interdisciplinary workshops and conferences. | 1 | [13 empty] | 4 | EECEHD | DRPD
|  | Bring together experts from diverse fields to create a multidisciplinary research team and develop frameworks to tackle issues. |  | Enhanced interdisciplinary collaboration and integrated conservation strategies. | Number of frameworks and interdisciplinary research teams formed. | 0 | [13 empty] | 0 | EECEHD | DRPD
|  | Organize interdisciplinary workshops and conferences to foster dialogue and partnership among stakeholders. |  | Increased stakeholder engagement and knowledge exchange. | Attendance and feedback from interdisciplinary workshops and conferences. | 0 | [13 empty] | 0 | DDEECEHD | DRPD
|  | Establish a digital platform to enhance dissemination and application of knowledge. |  | Digital platform established | Knowledge base content | 0 | [13 empty] | 0 | DDEECEHD | DRPD
Outcome: Enhanced resilience, understanding, and protection of ecosystems and primate populations through effective conservation management practices, improved stakeholder collaboration, and reduced threats to primate habitats.
Strategic Objective 2: To promote primate Conservation Research and Monitoring for improved ecosystem health
|  | Conduct Primate and biodiversity surveys in unsurveyed areas to support primate & biodiversity conservation and protection. |  | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 1 | [13 empty] | 10 | DDEECEHD | DRPD
|  | Conduct Routine census of threatened primate species and other endangered species |  | Up-to-date database on primate species diversity and distribution. | Updated entries in the species database. | 1 | [13 empty] | 14.5 | DDEECEHD | DRPD
|  | Develop, maintain, and update a database on diversity, population status, and distribution of Kenyan primates. |  | Identification and mitigation of threats to primate habitats. | Threat assessment reports and mitigation plans. | 1 | [13 empty] | 3 | DDEECEHD | DRPD
|  | Map out the distribution of key primates and biodiversity hotspots in the country. |  | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 1 | [13 empty] | 5 | DDEECEHD | DRPD
|  | Assess threats to species & their habitats, develop mitigation plans, and monitor intervention impacts. |  | Identification and mitigation of threats to primate habitats. | Threat assessment reports and mitigation plans. | 1 | [13 empty] | 3.5 | DDEECEHD | DRPD
|  | Undertake population ecology and behavioral studies to understand species demographics and population dynamics of the endangered species. |  | Improved understanding of primate population dynamics and genetics. | Research publications on primate population dynamics and genetics. | 2 | [13 empty] | 6.5 | DDEECEHD | DRPD
|  | Monitor human-wildlife interactions and map out human-primate conflict hotspots. |  | Effective management of human-primate conflicts. | Number of human-primate conflicts resolved. | 3 | [13 empty] | 5 | DDEECEHD | DRPD
|  | Undertake primate translocations as the last option to resolve human-non-human primate conflicts and rescue threatened populations. |  | Effective management of human-primate conflicts. | Number of human-primate conflicts resolved. | 0 | [13 empty] | 0 | DDEECEHD | DRPD
|  | Conduct wildlife habitat research including habitat characterization, suitability assessments, food resource dynamics, and habitat changes. |  | Comprehensive data on primate populations and biodiversity. | Number of surveys conducted. | 2 | [13 empty] | 10 | DDEECEHD | DRPD
|  | Conduct primate and wildlife genomics and microbiome characterization to inform taxonomy, population differences, bottlenecks, species genetic rescue disturbances effects on primate survival, and drivers of adaptation and species survival. |  | Improved understanding of primate population dynamics and genetics. | Research publications on primate population dynamics and genet | 2 | [13 empty] | 10 | DDEECEHD | DRPD
Outcome: Enhanced ecosystem health and increased biodiversity, resulting in stable or growing primate populations and improved ecosystem services for local communities
Strategic Objective 3: To improve ecosystem health and restoration effort
|  | Conduct surveys and mapping to identify priority areas for restoration, focusing on habitats critical for primates, biodiversity hotspots, and regions vulnerable to climate change impacts. |  | Identification of priority areas for ecosystem restoration. | Number of priority areas identified and mapped. | 2 | [13 empty] | 8 | DDEECEHD | DG's office
|  | Analyze the drivers of land degradation (e.g., deforestation, overgrazing, unsustainable agriculture) and assess their impact on primate populations, biodiversity, and ecosystem services. |  | Reduction in land degradation and its impact. | Reports on drivers of degradation and their impacts. | 1 | [13 empty] | 10 | DDEECEHD | DG's office
|  | Evaluate the impact of different resource management practices on ecosystem services and human well-being. |  | Improved resource management practices and ecosystem services. | Metrics on the impact of resource management practices. | 1 | [13 empty] | 4 | DDEECEHD | DG's office
|  | Conduct workshops with local communities and other stakeholders to gather their knowledge, concerns, and priorities for incorporation in restoration and conservation strategies. |  | Increased local community participation in restoration efforts. | Number of community members participating in restoration. | 4 | [13 empty] | 6 | DDEECEHD | DG's office
|  | Establish community-run seed collection programs and nurseries to ensure a sustainable supply of native plants seeds for restoration efforts. |  | Sustainable supply of native plants for restoration. | Quantity of native plants supplied and planted. | 4 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Develop restoration plans to address the needs of threatened primates' food sources, nesting sites, and movement corridors. |  | Identification of priority areas for ecosystem restoration. | Number of priority areas identified and mapped | 2 | [13 empty] | 8 | DDEECEHD | DG's office
|  | Conduct nutritional and endocrinological studies in relation to animal behavior and health. |  | Better understanding of the nutritional and health status of primates. | Reports on zoonotic disease risks and prevention measures. | 3 | [13 empty] | 7 | DDEECEHD | DG's office
|  | Develop integrated conservation plans that incorporate ecological, social, economic and environmental perspectives. |  | Enhanced interdisciplinary collaboration and integrated conservation strategies. | Number of interdisciplinary research teams formed. | 3 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Conduct primate behavioral studies to understand social behavior, natural selection, individual learning, and cultural transmission. |  | Insights into primate social behavior and its implications for health and conservation. | Research publications on primate nutrition and endocrinology. | 1 | [13 empty] | 5 | DDEECEHD | DG's office
|  | Conduct studies that generate actionable data and insights to conservation, public health, and climate change adaptation strategies. |  | Actionable data and insights for informed decision-making. | Research publications and reports generated. | 1 | [13 empty] | 5 | DDEECEHD | DG's office

## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Exptected Output | Performance Indicator | Impact | Link to the functions | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[10 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support | Source of funding
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
4 | Key Result Area 4: Legal, regulatory and policy framework | Outcome: Regulatory compliance obtained
Strategic Objective 1: To ensure regulatory compliance and develop legal provisions
|  | Regulatory compliance obtained |  | Obtain new regulatory compliance documents (e.g. SOPs, ISO, Policies, NEMA, DOSH, GFGP, Labs, professional) | Number of newly obtained regulatory compliance documents (e.g. SOPs, ISO, Policies, NEMA, DOSH, GFGP, Labs, professional) obtained |  |  | 2 | [13 empty] | 5 | DCS | DG's office
Outcome: Review of the KIPRE legal notice to an Act of Parliament
|  | Review of the KIPRE legal notice to an Act of Parliament |  | KIPRE legal notice to an Act of Parliament reviewed | KIPRE Act of Parliament |  |  | 0 | [13 empty] | 0 | DCS | DG's office
Outcome: Internal business processes reviewed and streamlined
Strategic Objective 2: To review and streamline internal business processes
|  | Develop tools of management, policies and SOPs |  | Management tools, policies and SOPs developed | No. management tools develop |  |  | 0 | [13 empty] | 0 | Planning & Strategy Division | All Directorates
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | Develop and implement data governance framework | 1. Conduct data governance needs assessment, 2. Establish governane structure and stakeholder engagement, 3. Develop the data governance framework, 4. Develop data policies and standard operating procedures (SOPs), 5. Implement supporting data management tools and infrastructure, 6. Conduct staff training and capacity building, 7. Pilot the governance framework, 8. Roll out framework across the KIPRE, 9. Monitor and evaluate implementation | Data governance framework developed | Number of data governance framework developed | 1. Improved data quality and standardisation, 2. Better evidence-based policy decisions, 3. Stronger data security and compliance, 4. Improved data sharing and interoperability, 5. Increased operational efficiency, 6. Stronger accountability and data owernership, 7. Enhanced institutional reputation and funding opportunities, 8. Long-term knowledge preservation. | (i) Assist in formulation, implementation, and review of policies, strategies, and guidelines on data analytics (ii) Collect, analyze, and interpret biological and health science data (iii) Support in design, development, and reporting of research studies (iv) Undertake data safeguarding and management of databases, softwares, and workflows (v) Provide monitoring and evaluation services to all research projects (vi) Collect, analyze, and interpret data across multiple research entities (vii–ix) Support disease monitoring, evaluation, and economic assessment (x) Identify valuable data sources and automate collection processes (xii–xiv) Manage genomic/proteomic and scientific data, maintain knowledge, prepare reports (xviii) Analyze large amounts of information to discover trends and patterns (xix) Conduct capacity building and mentorships in biostatistics and modeling | 1 | Approved framework document. Data inventory report. Policy and SOP documents. Data catalog system evidence. Training attendance reports. Pilot compliance audit report. Management approval minutes | Stakeholder mapping and formation of Data Governance Committee. | Institutional data inventory audit | Gap analysis (current practices vs Data Protection Act 2019, GLP, GDPR where applicable) | Draft master data governance policy (security, ownership, quality, ethics, IP) | Develop data classification framework (Public, Internal, Restricted) | Develop and validate SOPs (data capture, storage, access, retention) | Establish institutional data catalog with metadata and assigned data owners | Implement access control and security mechanisms (roles, permissions, encryption) | Conduct data literacy and security training (research and administrative staff) | Pilot project rollout (apply framework in one selected project) | Compliance audit and stress test of pilot. | Annual review, final framework revision and submission for institutional approval; Y2 scaling plan | 15 | Data Science and analystics Section | RPDD
Outcome: Procurement management plan developed
Strategic Objective 4: To improve supply chain management
|  | Develop procurement plan |  | Procurement plan | No. of procurement plan developed |  |  | 1 | [13 empty] | 0.5 | SCMD | All directorates/divisions
|  | Maintain and update inventory of assets |  | Asset inventory updates | No of inventory of assets updated |  |  | 1 | [13 empty] | 0.01 | SCMD | SCM Head\DCS
|  | Develop and implement asset and disposal policy |  | Asset disposal policy operationalized | No. of assets disposed |  |  | 0 | [13 empty] | 0 | SCMD | SCM Head\DCS
|  | Tag assets using radio frequency identification (RFID) |  | Assets tagged reports | No of assets tagged reports |  |  | 1 | [13 empty] | 0.1 | SCMD | SCM Head\DCS
Outcome: Increased public engagement and communication
Strategic Objective 6: To engage in Corporate Social and Environmental Responsibility (CSER).
|  | Conduct scientific workshops on health research |  | Workshops conducted | Number of workshops conducted |  |  | 4 | [13 empty] | 1.3 | Director Research | DG's office
|  | Conduct scientific conference on health research |  | Conference conducted | Number of conferences conducted |  |  | 1 | [13 empty] | 20 | Director Research | DG's office
|  | Enhance Media & Digital Communication |  | Media and Digital communication campaigns conducted | Number of media campaigns conducted |  |  | 5 | [13 empty] | 15 | Corporate Communications | DG's office
[5 empty] | Number of blogs and articles published |  |  | 5 | [13 empty] | 1.3 | Corporate Communications | DG's office
|  | Develop Educational programs for health research |  | Public courses developed | Number of public courses developed |  |  | 1 | [13 empty] | 1.9 | Director Capacity Building | DG's office
|  |  |  | Outreach programs designed | Number of outreach programs designed |  |  | 1 | [13 empty] | 4 | Director Capacity Building | DG's office
|  |  |  | Education tours for high school and university students conducted | Number of education tours conducted |  |  | 4 | [13 empty] | 0.04 | Director Capacity Building | DG's office
|  | Develop interactive websites and online platform |  | Interactive websites developed | Number of interactive websites developed |  |  | 0 | [13 empty] | 0 | ICT | DG's office
|  |  |  | Online webinars and livestreams undertaken | Number of webinars and livestreams undertaken |  |  | 4 | [13 empty] | 0.26 | ICT | DG's office
Outcome: Increased engagement in Corporate Social and Environmental Responsibility (CSER)
|  | Undertake charitable activities such as tree planting, drilling boreholes for Nkare-Narok community County, donation of boat for OZI Community in Tana River County, donation of Snakebite Emergency Response System (Hot-line and Ambulance service), addressing monkey menace through relocation donation of bee-hives and nature trail fee waiver for the destitute |  | Charitable activities undertaken | No. of charitable activities undertaken |  |  | 1 | [13 empty] | 2 | Corporate Communication Div. | DCS
5 | Key Result Area 5: Human Resource Development | Outcome: Increased skilled and competent workforce
Strategic Objective 1: To promote public engagement and communication
|  | Establishment of reward and recognition systems |  | Reward and recognition system established | Reward and recognition system established |  |  | 0 | [13 empty] | 0 | DCS | All Directorates
|  | Develop sensitization programs |  | No. of sensitization programs | No. of sensitization activities conducted |  |  | 3 | [13 empty] | 0.01 | DCS | All Directorates
|  | Develop and implement human resource instruments |  | Human resource instruments developed and implemented | No. of human resource instruments developed and implemented |  |  | 0 | [13 empty] | 0 | DG | DCS
|  | Develop and implement job description manual |  | Job description manual developed and implemented | No. job description manuals developed and implemented |  |  | 0 | [13 empty] | 0 | DG | DCS
|  | Advertise job vacancies |  | Job vacancies advertised | No. of job vacancies adverts |  |  | 45 | [13 empty] | 2 | DG | DCS
|  | Shortlisting of applicant and reach out for interview |  | Applicants shortlisted and communicated to | No. candidates shortlisted |  |  | 45 | [13 empty] | 0.1 | DG | DCS
|  | Conduct interview and analyse candidate’s performance |  | Interview conducted and performance analysed | No. of candidates interviewed |  |  | 45 | [13 empty] | 0.1 | DG | DCS
|  | Carry out staff induction |  | Staff induction carried out | No. of staff induction programs and reports |  |  | 4 | [13 empty] | 0.01 | DCS | All Directorates
|  | Conduct correct placement and upgrading |  | Correct placement and staff upgrading conducted | No. of correct placements and upgrading conducted |  |  | 0 | [13 empty] | 0 | DCS | DG's office
|  | Conduct performance appraisals |  | No. of staff appraisal reports generated | No. of reports generated |  |  | 1 | [13 empty] | 2 | DCS | DG's office
|  | Conduct staff welfare programmes |  | Staff welfare programmes conducted | No. of staff welfare programmes conducted |  |  | 1 | [13 empty] | 5 | DCS | DG's office
|  | Conduct institutional management committees’ meetings, trainings and retreats |  | Institutional management committees’ meetings, trainings and retreats conducted | No. of meetings, trainings and retreats conducted |  |  | 96 | [13 empty] | 50 | DCS | DG's office
|  | Appraise student for top performance |  | Top performing students appraised | No. of students appraised as top performers |  |  | 5 | [13 empty] | 0 | DCS | DG's office
|  | Facilitate specialized training and licensing for staff |  | Specialized training and licensing for staff facilitate | No. of training and licensing for staff facilitated |  |  | 25 | [13 empty] | 5 | DCS | DG's office
|  | Conduct and implement training needs assessment |  | Training needs assessment conducted and implemented | Training needs assessment |  |  | 1 | [13 empty] | 2 | DCS | ALL Directorates
|  | Strengthen employees’ relations |  | Employees relations strengthened | % of employees relations |  |  | 100 | [13 empty] | 2 | DCS | All Directorates
|  | Regularly Review organization establishment, grading and pay structure |  | Organization establishment, grading and pay structure reviewed | No. of review reports |  |  | 1 | [13 empty] | 2 | DG | DCS
|  | Training professionals |  | Training of professionals conducted | % of professionals trained |  |  | 100 | [13 empty] | 1 | DCS | ALL Directorates
6 | Key Result Area 6: Infrastructure and equipment | Outcome: Infrastructure upgraded
Strategic Objective 1: To construct and upgrade infrastructure for health Research Excellence
|  | Upgrade the research laboratory facilities to meet the set standards |  | Research Laboratory facilities Expanded | Number of Research Laboratory facilities Expanded |  |  | 2 | [13 empty] | 0.8 | DG | SCM Head/DCS
|  | Procure laboratory and office equipment |  | Research Laboratory and office equipment procured | Number of Research Laboratory Equipment procured |  |  | 2 | [13 empty] | 5 | DG | SCM Head/ All Directorates
|  | Upgrade staff offices and facilities |  | Staff offices and facilities expanded | No. of staff offices and facilities expanded |  |  | 2 | [13 empty] | 2 | DG | SCM Head/ DCS
|  | Facilitate audit of the research laboratory facilities |  | Audit of the research laboratory facilities | Number of audit report |  |  | 2 | [13 empty] | 0.5 | DG | DCS/ Audit Head
|  | Acquire Service contracts of the research laboratory equipment |  | Service contracts of the research laboratory equipment acquired | Number Service contracts of the research laboratory equipment acquired |  |  | 2 | [13 empty] | 5 | DG | SCM Head \DCS/ Corporation Secretary
|  | Increase number of the fleet for research |  | Vehicles and motorbikes acquired | Number of vehicles and motor vehicles acquired |  |  | 2 | [13 empty] | 16 | DCS | SCM Head
|  | Removal of asbestos from building |  | Asbestos removed from buildings | No. buildings refurbished (asbestos removed) |  |  | 4 | [13 empty] | 250 | DCS | SCM Head
|  | Establish a training center for biomedical research, pre-clinical and clinical research |  | Training center established | No. of training center |  |  | 0 | [13 empty] | 0 | DCS & DCB | SCM Head
|  | Installation of CO2 and liquid Nitrogen generation plants |  | CO2 and Liquid Nitrogen plants installed | No. of plants installed |  |  | 1 | [13 empty] | 100 | DR&PD | DCS
Outcome: Technologies Installed
|  | Upgrade ICT infrastructure |  | ICT infrastructure upgraded | Number of upgraded ICT infrastructure |  |  | 6 | [13 empty] | 14 | DCS | SCM Head
Outcome: Field research station infrastructural facility constructed
[5 empty] | No. of field research activities |  |  | 1 | [13 empty] | 20 | KESRIC, | DG
Outcome: Green energy technology installed
Strategic Objective 5: To invest in green energy technology
|  | Installation of green energy technology (Solar) |  | Green energy technology installed | No of green energy technology installed |  |  | 1 | [13 empty] | 5 | DG | DCS/SCM Head
7 | Key Result Area 7: Research collaborations and partnerships | Outcome: Increased number of collaborators and partners
Strategic Objective1: To increase the number of collaborations and partnerships
|  | Establish local and international partnerships and collaborations |  | Partnerships and collaborations established | Number of partnerships and collaborations established |  |  | 14 | [13 empty] | 19.416 | DCBPGM | DRPD

## Strategic Issue 4
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub activities | Exptected Output | Performance Indicator | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[8 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support
Strategic Issue 4: Inadequate Financial support for health research & Innovation
Strategic Goal 4: To secure funding to sustain health research and innovation whilst ensuring efficient use of KIPRE finances.
8 | Key Result Area 8: Advocacy and engagement of the government for increased research funding | Outcome: Increased research funding from government
Strategic Objective 1: Formulate and implement favorable, well aligned health research & management policies
|  | Developing strategic plan as per the guidelines |  | Approved strategic plan | Approved strategic plan | 0 | [13 empty] | 0 | Planning and Strategy Division | Heads of Directorates/divisions
|  | Developing Institutional workplan |  | Approved institutional workplan | Number of institutional work plans | 1 | [13 empty] | 15.9 | Planning and Strategy Division | Heads of Directorates/divisions, MOH, TNT
|  | Develop Institutional Performance contract as per the guidelines |  | Approved Institutional Performance contract | Approved Institutional Performance contract | 1 | [13 empty] | 13.2 | Planning and Strategy Division | Heads of Directorates/divisions, MOH, TNT
|  | Develop advocacy strategy |  | Advocacy strategy developed | Number of advocacy strategies developed | 0 | [13 empty] | 0 | DRPD | Deputy Directors
|  | Conduct advocacy for funding of research and development |  | Advocacy for funding of research and development conducted | Number of advocacy activities for funding of research and development conducted | 11 | [13 empty] | 53.1 | DRPD | Director Research & Product Development (DRPD), DDFA
|  | Hold consultative meetings to advocate for more resources towards health research |  | Consultative meetings held | Number of consultative meetings held | 1 | [13 empty] | 4 | Planning & Strategy | Head of Divisions, MOH, TNT
9 | Key Result Area 9: Diversified funding streams | Outcome: Increased revenue generation
Strategic Objective 3: Mobilize and manage financial resources
|  | Develop a Resource Mobilization strategy |  | Resource mobilization strategy | Approved Resource Mobilization strategy | 1 | [13 empty] | 25 | FAD | Heads of Directorates & Divisions
Outcome: Cost saving measures implemented
Strategic Objective 3: Implement cost saving measures
|  | Regular financial reviews |  | Quarterly Financial reports developed | financial reports | 4 | [13 empty] | 0 | Finance
|  | Conduct internal finance audits |  | Quarterly risk assessment reports developed | Risk assessment reports | 4 | [13 empty] | 1.33 | Audit | All Directors
|  |  |  | Annual internal audit reports developed | Audit reports | 1 | [13 empty] | 0 | Audit | Finance
|  | Automation of Revenue collection |  | Finance and accounts ERP module procured | Finance and Accounts ERP module | 0 | [13 empty] | 0 | ICT | Finance
|  | Maintenance and upgrading of ERP- finance module |  | ERP-finance module maintained and upgraded | Maintenance and upgrade reports | 4 | [13 empty] | 2 | ICT | Finance
10 | Key Result Area 10: Efficient resource Utilization | Outcome: Effective management of projects & initiatives and accurate assessment of their impacts
Strategic Objective 1: Integrate planning, Monitoring & Evaluation (PM&E) programs and process
|  | Developing and disseminating PM&E SOPs |  | Performance, Monitoring & Evaluation SOPs developed and disseminated | Number of Performance, monitoring & Evaluation SOPs developed and disseminated | 0 | [13 empty] | 0 | Planning & strategy | Heads of Directorates/Divisions
|  | Develop a comprehensive PM&E framework |  | Performance, Monitoring & Evaluation framework developed | Number of performance, monitoring & evaluation framework developed | 0 | [13 empty] | 0 | Planning & strategy | Heads of Directorates/Divisions
|  | Mid & End term review of the strategic plan |  | Reviewed Mid & End term strategic plan | Number of review reports submitted | 1 | [13 empty] | 12 | Planning & strategy | Heads of Directorates/Divisions
|  | Conduct annual performance review |  | Annual performance review conducted | Annual performance review report submitted | 1 | [13 empty] | 3.5 | Planning & strategy | Heads of Directorates/Divisions