## Strategic Issue 3
DRAFT 0 ANNUAL WORKPLAN 2026-2027
| Result Areas | Activity | Sub Activities | Exptected Output | Performance Indicator | Impact | Link to the functions | Target | Means of Verification (MoV) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Estimated Cost | Responsibility
[10 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Y4 | Lead | Support | Source of funding
Strategic Issue 3: Weak institutional capability for health research excellence
Strategic Goal 3: To build institutional capacity to achieve excellence in health research through training, infrastructure development, enhancement of corporate governance and collaborations.
Outcome: Data management analytics and strategies developed and implemented
Strategic Objective 3: To develop data management analytics and protection strategies
|  | Develop and implement data management and sharing guidelines | 1. Conduct data governance needs assessment, 2. Establish governane structure and stakeholder engagement, 3. Develop the data governance framework, 4. Develop data policies and standard operating procedures (SOPs), 5. Implement supporting data management tools and infrastructure, 6. Conduct staff training and capacity building, 7. Pilot the governance framework, 8. Roll out framework across the KIPRE, 9. Monitor and evaluate implementation | Data managenent and sharing guidelines developed | Number of data governance framework developed | 1. Improved data quality and standardisation, 2. Better evidence-based policy decisions, 3. Stronger data security and compliance, 4. Improved data sharing and interoperability, 5. Increased operational efficiency, 6. Stronger accountability and data owernership, 7. Enhanced institutional reputation and funding opportunities, 8. Long-term knowledge preservation. | (i) .(ii) ,(iii) ,(iv) ,(v) ,(vi) ,(vii–ix) ,(x) ,(xii–xiv) , (xviii) ,(xix) | 1 | Approved framework document. Data inventory report. Policy and SOP documents. Data catalog system evidence. Training attendance reports. Pilot compliance audit report. Management approval minutes | Stakeholder mapping and formation of Data Governance Committee. | Institutional data inventory audit | Gap analysis (current practices vs Data Protection Act 2019, GLP, GDPR where applicable) | Draft master data governance policy (security, ownership, quality, ethics, IP) | Develop data classification framework (Public, Internal, Restricted) | Develop and validate SOPs (data capture, storage, access, retention) | Establish institutional data catalog with metadata and assigned data owners | Implement access control and security mechanisms (roles, permissions, encryption) | Conduct data literacy and security training (research and administrative staff) | Pilot project rollout (apply framework in one selected project) | Compliance audit and stress test of pilot. | Annual review, final framework revision and submission for institutional approval; Y2 scaling plan | 15 | Data Science and analystics Section | RPDD
|  | Provide statistical support to research projects | Study design and protocol development Sample size determination and power analysis Data analysis and modelling (regression, survival, longitudinal) Results interpretation and report writing Support manuscript development | Statistical support provided to institutional research projects | Support coverage | Improved research quality and validity Increased publication output Better evidence-based decision-making | (ii), (iii), (v), (xviii), (xx) | ≥ 80% of projects supported | Analysis reports Study protocols Publications | Q1 Jul: Q1: Identify projects and provide initial design support; Q2 Oct: Q2: Ongoing analysis and interim reporting; Q3 Jan: Q3: Advanced modelling and interpretation; Q4 Apr: Q4: Final reports and publications |  | Data Science and analystics Section | Research divisions
|  | Develop and deploy data management and analysis pipelines | Develop data cleaning and preprocessing protocols Build reproducible R/Python scripts Implement version control systems Standardise data formats and workflows | Standardised data pipelines established | Pipeline adoption rate | Improved reproducibility Reduced data errors Increased efficiency | (iv), (x), (xi), (xv) | At least 5 standard pipelines | Code repositories Pipeline documentation | Q1 Jul: Q1: Develop templates and standards; Q2 Oct: Q2: Pilot pipelines; Q3 Jan: Q3: Scale implementation; Q4 Apr: Q4: Optimisation and review |  | Data Science and analystics Section | Research divisions
|  | Strengthen monitoring and evaluation systems | Develop M&E indicators and frameworks Build dashboards and reporting tools Conduct periodic evaluations Generate M&E reports | Functional M&E system for research projects | Reporting compliance(%) | Improved project accountability Better tracking of outcomes | (v) | 100% project reporting | M&E reports Dashboards | Q1 Jul: Q1: Framework development; Q2 Oct: Q2: Dashboard deployment; Q3 Jan: Q3: Mid-year evaluation; Q4 Apr: Q4: Annual evaluation |  | Data Science and analystics Section | Research divisions
|  | Conduct epidemiological and disease modelling studies | Disease trend analysis Risk factor modelling Survival and longitudinal modelling Spatial analysis | Epidemiological models and reports | Number of models developed | Improved disease understanding Better intervention planning | (vii), (viii), (ix), (xviii) | ≥ 3 studies completed | Technical reports Publications | Q1 Jul: Q1: Data collection; Q2 Oct: Q2: Model development; Q3 Jan: Q3: Validation; Q4 Apr: Q4: Reporting |  | Data Science and analystics Section | Research divisions
|  | Support to ISERC | Support research coordination through data tracking systems and dashboards Provide statistical input in protocol review and study design Develop data management and governance support tools for ISERC Support monitoring and evaluation of ISERC-coordinated projects Conduct data analysis and reporting for ISERC programmes Support dissemination (reports, publications, presentations) Provide training in data analysis, biostatistics, and research methods | Data science and analytics support provided to ISERC operations and research coordination | ISERC support coverage (%) Project tracking efficiency(% | Improved coordination and oversight of research activities Strengthened research quality and compliance Enhanced monitoring and evaluation of institutional projects Increased research outputs and dissemination | (ii), (iii), (iv), (v), (x), (xvi), (xviii), (xx) | ≥ 90% of ISERC projects supported ≥ 1 functional project tracking/dashboard system ≥ 4 analytical reports produced | ISERC reports and meeting minutes Dashboards and tracking systems Analytical reports and publications Training reports and attendance registers | Needs assessment with ISERC | Design of tracking systems and dashboards | Initial protocol and statistical support | Implementation of dashboards | Ongoing data analysis and reporting | Support M&E framework | Advanced analysis and evaluation | Mid-term reporting | Training sessions | Final analysis and reporting | Dissemination (publications, presentations) | System review and optimisation |  | Data Science and analystics Section | ISREC and Research Divisions
|  | Develop machine learning models and advanced analytics tools | Train predictive models Validate and optimise models Implement ensemble methods Deploy models | Predictive models developed and deployed | Number of models developed | Enhanced predictive capacity Improved decision support | (xvi), (xvii), (xviii) | ≥ 3 models | Model documentation Code and outputs | Q1 Jul: Q1: Model design; Q2 Oct: Q2: Training; Q3 Jan: Q3: Validation; Q4 Apr: Q4: Deployment |  | Data Science and analystics Section | Research Divisions
|  | Provide bioinformatics and genomic data analysis | Analyse sequencing data Develop bioinformatics pipelines Manage genomic datasets Generate reports | Bioinformatics analyses conducted | Number of genomic analyses completed | Improved molecular research capacity Enhanced scientific output | (xii), (xiii), (xiv) | ≥ 2 projects supported | Analysis reports Data outputs | Q1 Jul: Q1–Q4: Continuous support |  | Data Science and analystics Section | Research Divisions
|  | Automate data collection and develop decision-support tools | Develop automated data pipelines Integrate multiple data sources Build dashboards (e.g., Shiny apps) | Automated data systems and dashboards | Number of systems developed | Real-time decision-making Improved efficiency | (x), (xv), (xviii) | ≥ 2 systems | Functional dashboards System documentation | Q1 Jul: Q1: Design; Q2 Oct: Q2: Development; Q3 Jan: Q3: Testing; Q4 Apr: Q4: Deployment |  | Data Science and analystics Section
|  | Capacity building and training | Conduct training workshops Provide mentorship Develop training materials | Staff trained in data science and analytics | Training coverage (%) | Increased institutional capacity Improved research quality | (xix) | ≥ 70% staff trained | Training reports Attendance records | Q1 Jul: Q1: Training needs assessment; Q2 Oct: Q2: Workshops; Q3 Jan: Q3: Advanced training; Q4 Apr: Q4: Evaluation |  | Data Science and analystics Section | Research Division and Capacity Building Directorate
|  | Dissemination of research findings | Prepare manuscripts Present at conferences Organise seminars | Scientific outputs disseminated | Number of publications and presentations | Increased visibility Knowledge sharing | (xx) | ≥ 5 outputs | Publications Conference reports | Q1 Jul: Q1–Q4: Continuous |  | Data Science and analystics Section | Research Division and Capacity Building Directorate