# Format for TEAM project proposals

Version of 21 October 2025

Table of content

Format for TEAM project proposals	1

Project proposal TEAM projects	2

GENERAL INFORMATION	2

Module 1: Context / problem analysis	3

1.1.	Sustainable development context	3

1.2	Institutional context of the partner institution(s)	4

Module 2: Project strategy (Theory of Change)	6

Module 3: Organisation	13

Module 4: Stakeholders and coherence	16

Module 5: Planning and budgeting	18

Module 7: Monitoring 	20

Module 8: Learning and steering	21

Annexes	22

# Project proposal TEAM projects

# GENERAL INFORMATION

(note: this is a working document, all info needs to be inserted via the project submission tool)

Project information

Project title

National Data Science Network for Health, Agriculture, Environment and Education: A Flemish–Kenyan Partnership for Evidence-Driven Public Policy.

Project Summary

The National Data Science Network (NDSN) aims to strengthen Kenya’s ability to use data for better and more inclusive decision-making. The project aims to establish a central Data Science and Analytics Centre (DSAC) and connect data scientists and institutions working across health, agriculture, environment, and education. At present, valuable data are scattered across these institutions, which slows down decision-making and weakens preparedness for health outbreaks, climate-related risks, and agricultural challenges. Moreover, much of the evidence produced ends up in technical reports or academic publications that are difficult for non-specialists, especially communities, to understand or use. This project will bring these datasets together, improve how they are managed, and strengthen skills within these Kenyan institutions. Through targeted training, mentoring, and staff exchanges with UHasselt, Kenyan data scientists will build strong capacities in biostatistics, epidemiology, bioinformatics, and data science. Clear data governance arrangements will ensure that data are used responsibly, securely, and in line with ethical standards. A key innovation of the project is its focus on the “last mile” of data use. Instead of stopping at policy reports, the project will ensure that analytical results are translated into clear, practical, and locally relevant information that communities can understand and act upon. Communities will not only receive information but will also be involved in interpreting findings and shaping responses, creating a two-way flow between evidence and action. The project will be coordinated by KIPRE, with technical support from UHasselt. Partner institutions, including the NPHI (National Public Health Institute), the DVS (Directorate of Veterinary Services), the NEMA (National Environment Management Authority), and the CEMA (Centre for Epidemiological Modelling and Analysis), will contribute data, expertise, and support the link between evidence and policy. With a strong monitoring and evaluation framework, the project will help build a sustainable and inclusive data science ecosystem in Kenya, supporting better policies and contributing to SDGs 2, 3, 4, 9, 13, and 17.

Please indicate whether your project is in one country, or in multiple countries. You will need to specify which country (or countries), indicating main (at least one) and other countries.

Kenya

Project duration and start

5 years / 1 September 2026

| Institutions / promoters (in case of multiple institutes, indicate the main administrative institution/promoter in the partner country and at the Flemish HE level) (this data can be uploaded via the data file Annex 1, or directly in the submission tool) |  |
| --- | --- |
| Flemish institution (s) | University of Hasselt , DSI (Data Science Institute) |
| Flemish promoter (s) | Dr. Leyla Kodalci, PhD. |
| Partner institution (s) | KIPRE, NPHI, DVS, NEMA, CEMA |
| Partner promoter (s) | Patrick Waweru Mwaura |
| Co-promoter Flemish/ partner | - Christopher K. Kariuki (KIPRE) - Joseph M.Kamau (KIPRE) - Stella Irungu (KIPRE) - Joyce O. Imende (NEMA) - Mathew Muturi (DVS) - Leonard Kingwara (NPHI) - Khadija Chepkorir (NPHI) - Mwangi Thumbi (CEMA) |

| Sector code OECD | As part of the preparation of the proposal, VLIRUOS requests some coding of the proposals for data purposes, you can prepare this in Annex 1 or complete directly in the submission tool |
| --- | --- |

| Sustainable Development Goals (SDG) |  |
| --- | --- |
| Main SDG | SDG 3 |
| Additional SDG | SDG 2, 4, 9, 13 and 17 |

# Module 1: Context / problem analysis

## Sustainable development context

Provide the evidence-based relevance of this proposal and describe the key sustainable developmental challenge(s) that the project wants to tackle (cf. Agenda 2030, taking into account as well the SDG principles of LNOB, MIP and MSP) and its global, regional, or local context (including local and national policies, and the key actors involved).

Since the One Health framework was first conceptualised in 2004, many countries, including Kenya and others in sub-Saharan Africa, continue to face challenges in implementing it effectively. A recent systematic review by Yopa et al. (2023) identifies persistent barriers, including weak governance and leadership, fragmented planning, limited cross-sector collaboration, inadequate community engagement, poorly coordinated surveillance, lack of operational experience, chronic resource constraints, workforce shortages, and gaps in communication. As Bukachi et al. note, these challenges repeatedly emerge during zoonotic outbreaks, environmental stresses, agricultural shocks, and public health emergencies. Fragmented information systems and limited analytical capacity further slow evidence-based decision-making and reduce the country’s ability to respond effectively. Similar gaps exist in the education sector, where universities and training institutions often lack interoperable infrastructure for data sharing and applied analytics, limiting the development of a skilled workforce that could support a national One Health agenda. Kenya’s national context clearly reflects these challenges. While capable institutions exist, including our partner organisations, each typically collects, generates, and manages its own datasets, standards, and governance frameworks. Without harmonised protocols and interoperable platforms, information flow across health, agriculture, environment, and education remains fragmented. This siloed approach carries significant financial, operational, and public health costs, including delayed threat detection, duplicated efforts, inefficient resource allocation, and gaps in multisector risk communication. Evidence from Griffin et al. and Milazzo et al. shows that weak inter-agency coordination directly contributes to delayed decisions and higher outbreak control costs. Without real-time integration of surveillance, laboratory, environmental, agricultural, and community-level data, agencies cannot build a complete risk picture, prioritise interventions, or evaluate the impact of public health measures. These systemic weaknesses slow progress toward SDGs 2 (Zero Hunger), 3 (Good Health and Well-being), 4 (Quality Education), 9 (Industry, Innovation and Infrastructure), 13 (Climate Action), and 17 (Partnerships for the Goals), and challenge the principles of Leaving No One Behind (LNOB), Meaningful Involvement of People (MIP), and Multi-Stakeholder Partnerships (MSP) that underpin Agenda 2030.

## Institutional context of the partner institution(s)

Analysis of the capacity constraints and needs/priorities of the local partner institution and in particular the involved research & educational units/departments. Describe the added value of the project in addressing these challenges and how through shared ownership the local institution can be enabled to become a driver of change linked with the proposed project outcomes (Clarify the link with the sustainable development context described under 1.1.).

In Kenya, many institutions continue to operate in silos, managing fragmented datasets and facing significant capacity constraints. Research and educational units often lack sufficient skilled personnel in data science, epidemiological modelling, statistics, and data engineering (Coker et al., 2023). Limited computing infrastructure, outdated servers, and inconsistent data governance further restrict their ability to conduct advanced analytics, predictive modelling, or integrated research. Opportunities for hands-on training, joint learning, and methodological alignment remain scarce, limiting these units’ ability to generate actionable evidence that can guide policy or inform community-level interventions. The National Data Science Network (NDSN), through the Data Science and Analytics Centre (DSAC), directly addresses these gaps. By introducing standardized data systems, practical workflows, and collaborative governance frameworks, DSAC enables local institutions to take ownership of projects and lead data-driven initiatives. Structured training programs, mentorship, and joint research clusters strengthen staff skills and encourage cross-sector collaboration, turning previously isolated units into active drivers of evidence-based decision-making. Critically, the project incorporates a “last-mile” focus, translating analytical outputs into accessible, actionable formats that reach communities and other end-users. By engaging stakeholders at the community level in interpreting findings, co-designing interventions, and providing feedback, local institutions become not only knowledge producers but also facilitators of evidence-informed action, bridging the gap between data generation, policy, and practical impact. These efforts align directly with Kenya’s sustainable development priorities, linking institutional capacity-building to real-world challenges: improving public health (SDG 3) through integrated health data and outbreak preparedness; supporting food security (SDG 2) via predictive agricultural analytics; enhancing education and training (SDG 4) through applied learning; building innovation and infrastructure (SDG 9) through modern data systems; addressing climate risks (SDG 13) via environmental and ecological modelling; and fostering strong partnerships (SDG 17) through co-designed governance and North–South knowledge exchange. By connecting institutional strengthening to both national priorities and community impact, the project ensures that partner institutions become central actors in driving sustainable, evidence-based solutions.

# Module 2: Project strategy (Theory of Change)

Describe your project strategy (Theory of Change) in 3 key questions. While these questions echo the key questions in Theory of Change (ToC) thinking process, a fully-fledged ToC is not requested. This ToC should reflect the alignment of your project with the general VLIRUOS ToC, and the 3 SDG principles. Explain your project following the key questions below.

What is the long-term change to which you want to contribute (this answers the WHY question)? - Summarise this in a short impact statement clarifying the long-term change to which the project wishes to make a meaningful contribution. - Elaborate this further in a narrative text explaining the importance of this long-term change within Agenda 2030 and the SDG’s and for who it is crucial.

Impact statement The project strengthens Kenya’s capacity for evidence-driven decision-making by connecting data scientists across sectors through a national network and a centralized Data Science and Analytics Centre (DSAC). By integrating health, agriculture, environment, and education data and translating insights into actionable knowledge that reaches communities and institutions, local partners become drivers of change, improving preparedness, resource use, and interventions. The initiative advances SDGs 2, 3, 4, 9, and 17, promoting inclusivity, community engagement, and sustainable multi-stakeholder collaboration.

Elaborate on the impact envisaged, why it is important and for whom? The envisaged impact of this project is to strengthen Kenya’s ability to make timely, evidence-based decisions that protect the health, livelihoods, and well-being of its people. By creating a national network of data scientists and reinforcing local institutions, the project ensures that data from the health, agriculture, environment, and education sectors can be effectively translated into actionable insights and interventions. This is particularly crucial for responding rapidly to disease outbreaks, environmental shocks, and agricultural challenges, ensuring that resources and actions reach those who need them most. Primary beneficiaries are the institutions that generate and use data, ministries, research institutes, and universities, which gain skills, tools, and governance structures to convert complex datasets into clear, actionable knowledge. Indirect beneficiaries include policymakers, vulnerable communities, and the general public, who benefit from faster responses, better-targeted interventions, and policies grounded in real-world evidence. By bridging gaps in capacity, infrastructure, and collaboration, the project enables local institutions to become drivers of sustainable change, supporting national development priorities while advancing equity, inclusion, and long-term sustainability.

What do you want to achieve by the end of the project? This needs to refer to the changes you want to achieve/observe by the end of the project. Convincingly explain how these align with VLIRUOS outcomes (cf. call document) by ticking the applicable ‘boxes’ and make this very explicit. Point of attention: Reflect on the challenges for the sustainability of the project results after VLIRUOS funding in terms of capacity retention, continuation of improved research/education/extension activities, dissemination of results, etc.

By the end of the project, a fully operational Data Science and Analytics Centre (DSAC) will be established in Kenya, serving as a national coordination hub for integrating, managing, and facilitating the use of data across health, agriculture, environment, and education sectors. The DSAC will connect institutions, harmonize fragmented datasets, and implement interoperable workflows, enabling timely, consistent, and reproducible analyses to support evidence-based decision-making at national and sub-national levels. Crucially, the DSAC will ensure that analytical outputs reach the communities generating or affected by the data, bridging the “last mile” between evidence and action. Institutional capacity will be significantly strengthened: research and educational units will gain trained data scientists, analysts, and technical staff with advanced competencies in biostatistics, epidemiology, bioinformatics, data management, and responsible data governance. Structured processes for collaboration, methodological harmonization, and applied training will enable institutions to continue high-quality research and analytical activities independently after the project ends. Human capacity and knowledge retention are central to sustainability. Through mentorship, training, and co-development of analytical workflows, local personnel will acquire practical skills and leadership experience. Knowledge transfer will be embedded in institutional routines, fostering a culture of continuous learning, collaboration, and evidence-driven research. The national network will also support ongoing partnerships among ministries, research institutes, universities, and international collaborators, sustaining North–South and South–South knowledge exchange beyond VLIR-UOS funding. Research and policy impact will be tangible: institutions will generate and interpret multisectoral evidence to inform public policy, resource allocation, and preparedness for disease outbreaks, environmental stresses, and agricultural challenges. Evidence will be disseminated through dashboards, policy briefs, workshops, stakeholder forums, and community engagement platforms, ensuring that insights reach policymakers, practitioners, and local communities, completing the “last-mile” of impact. Sustainability and long-term vision are embedded in the design. Governance frameworks co-created with local partners will secure shared ownership and responsibility for DSAC operations within national institutions. Standardized, interoperable data systems, trained personnel, and formalized partnerships will support continuous coordination, research, teaching, and outreach, ensuring that both institutional improvements and last-mile knowledge transfer persist after VLIR-UOS funding ends. Alignment with VLIR-UOS outcomes is explicit: the project strengthens institutional capacity, improves research quality, enhances teaching and training programs, and promotes multi-stakeholder engagement for evidence-based policy. Gender-sensitive approaches, local ownership, and capacity retention ensure inclusivity, equity, and sustainability, enabling Kenyan institutions to become drivers of change in health, agriculture, environment, and education, with lasting national and community-level impact.

How do you want to do this? Explain how you will do it, describing your operational and methodological approaches, identifying key deliverables and activities (in line with the project’s operational plan). In the operational plan, activities are to be organised in accordance with the six standard VLIRUOS project domains, giving particular attention for the standard domain dissemination/uptake strategy. Clarify your approach for various underlying aspects, for example: - Innovative research methods and approaches Strategies to create conditions for uptake (stakeholder involvement, communication, .) - …

The project will achieve its objectives through a coordinated set of operational and methodological approaches across the six VLIR-UOS project domains, focusing on institutional capacity, human development, data integration, evidence generation, and stakeholder engagement. 1. Education and Capacity Building Structured training programs, mentorship, and international academic exchanges will develop a skilled cadre of Kenyan data scientists capable of advanced analytics, predictive modelling, bioinformatics, epidemiology, and One Health approaches. Training will combine theory with hands-on work using multisectoral datasets; ensuring knowledge is immediately relevant to real-world challenges. Key deliverables include trained personnel, curriculum modules, and a mentorship network linking students, researchers, and practitioners. 2. Research The DSAC will act as a national coordination hub for collaborative research, enabling coherent analysis of health, agricultural, environmental, and education data. Methodological innovation will include interoperable data pipelines, predictive modelling, geospatial analyses, and scenario-based simulations to inform policy. Deliverables include research outputs, policy briefs, and cross-sector methodological guidelines. 3. Outreach, Dissemination, and Uptake To ensure evidence reaches decision-makers and communities, the project will implement a comprehensive dissemination strategy, including policy briefs, dashboards, workshops, stakeholder forums, and targeted communication to ministries, local authorities, and communities. Stakeholders will be engaged continuously to co-design research questions, validate analyses, and shape recommendations, ensuring practical uptake of evidence—the “last mile” of impact. 4. Service to Society DSAC will translate analytical outputs into actionable interventions, informing public health policies, agricultural strategies, and environmental management. By integrating multisector data, interventions will be timely, context-specific, and equitable. Deliverables include decision-support tools, early-warning models, and sector-specific recommendations aligned with national priorities. 5. Infrastructure and Institutional Strengthening The project will establish interoperable, secure digital infrastructure, standardized data repositories, and robust governance frameworks for ethical data sharing. DSAC will provide institutional platforms for continuous learning, cross-sector collaboration, and evidence generation. Deliverables include functional infrastructure, standardized workflows, and documented governance protocols. 6. Partnerships and Networking Sustainability and scale will be ensured through multi-stakeholder partnerships at national, regional, and international levels, including UHasselt. Networks will facilitate North–South and South–South knowledge exchange, mentorship, and collaborative research. Deliverables include formal partnership agreements, research clusters, and knowledge-sharing platforms. Integration of Gender and Environmental Considerations All activities will adopt a gender-sensitive lens to ensure equitable participation of women and underrepresented groups. Environmental indicators will be integrated into analyses, supporting evidence-based policy that balances human health, agricultural productivity, and ecological sustainability. Innovative Research Methods The project emphasizes innovative approaches such as predictive outbreak modelling, real-time multisectoral data integration, scenario-based policy simulations, and One Health analytics to address complex socio-ecological challenges. Creating Conditions for Uptake Stakeholders, including ministries, research institutions, and local communities, will be actively involved in co-design, validation, and dissemination. Policy-focused workshops, dashboards, and decision-support tools will ensure evidence is not only produced but also actively used for decision-making. Summary Through these integrated approaches, the project will establish a sustainable national network of data scientists, strengthen institutional and human capacity, standardize data systems, and ensure that evidence reaches institutions and communities, bridging the last mile. By embedding local ownership, inclusive governance, and stakeholder engagement, the initiative aligns with VLIR-UOS outcomes, supports long-term sustainability, and advances Kenya’s national development goals.

Please describe how the project will integrate the 3 SDG principles as presented by VLIRUOS: - Interconnectedness with due attention for the integration of gender, diversity & inclusion, and environment - Coherence, Multi-Institutional partnerships and Multi-Stakeholder partnerships - Leave No One Behind (LNOB)

The project integrates interconnectedness by addressing health, agriculture, environment, and education as a single, interlinked system. Gender, diversity, and inclusion are embedded across training, mentorship, and leadership activities to ensure equitable participation, particularly for women and underrepresented groups. Environmental indicators are systematically incorporated into data integration and analytical workflows, enabling evidence-based decisions that balance human well-being, food security, and ecological sustainability. Coherence and partnership are achieved through strong multi-institutional and multi-stakeholder collaboration. National ministries, research institutes, universities, and specialised agencies work within a shared governance framework, with the Data Science and Analytics Centre (DSAC) acting as a coordination and facilitation hub. International partners, including UHasselt, provide technical support and joint learning, while policymakers, practitioners, and community representatives are involved throughout the project cycle to ensure relevance, ownership, and effective uptake. The project applies the Leave No One Behind (LNOB) principle by prioritising underserved and vulnerable populations in both capacity-building and evidence use. Analytical outputs are translated into accessible, user-oriented formats to ensure that insights reach practitioners, local authorities, and communities, bridging the last mile between data and action. By embedding inclusivity and equity in both processes and outcomes, the project ensures that the benefits of data-driven decision-making are broadly shared.

Describe the challenges for the sustainability of the project results after VLIR-UOS funding and the possible strategies to tackle those challenges.

A key sustainability challenge after VLIR-UOS funding is capacity retention, as trained data scientists and technical staff may transition to other institutions or sectors. To mitigate this risk, the project embeds capacity development within local universities and research institutions by institutionalising training programmes, supervision structures, and applied learning pathways. The Data Science and Analytics Centre (DSAC), functioning as a coordination centre rather than a standalone unit, will provide clear career development, mentorship, and leadership opportunities. Formal agreements with partner institutions will further anchor trained personnel in long-term roles linked to national data initiatives. Ensuring the continuity of research, education, and extension activities beyond external funding is another challenge. The project addresses this by integrating research outputs, analytical tools, and training materials into existing institutional curricula and research agendas. Open-access data repositories and standardised analytical workflows will be developed to support continued use by local teams. Thematic clusters coordinated through the DSAC will be led by national institutions, enabling independent planning, expansion, and resource mobilisation after project completion. Sustaining dissemination and uptake of results requires deliberate structures to prevent evidence from remaining unused. The project therefore formalises stakeholder engagement through advisory mechanisms, policy dialogues, and regular dissemination forums. Policy briefs, dashboards, and decision-support tools will be co-produced with end users to ensure relevance, usability, and continued application. Ongoing multi-stakeholder partnerships, including North–South and South–South collaboration, will reinforce technical support and knowledge exchange beyond the funding period. Finally, infrastructure and governance pose long-term sustainability challenges if systems remain externally dependent. The project mitigates this by embedding interoperable data standards, ethical governance frameworks, and clear institutional responsibilities within partner organisations. Cost-effective, locally maintained infrastructure will be prioritised to allow scaling without excessive external reliance. Formal governance agreements will ensure that responsibility for system maintenance, coordination, and oversight remains anchored within national institutions. By addressing these challenges proactively, the project ensures that the DSAC-enabled network evolves into a self-sustaining national ecosystem, capable of supporting continuous evidence generation, last-mile policy uptake, and resilient, data-informed decision-making in Kenya beyond VLIR-UOS support.

Next to the narrative description, you will be asked to select the relevant VLIRUOS outcomes and domains to which your project aligns when submitting the proposal in the VLIRUOS tool

# Module 3: Organisation

📝 Update the personal data of the project (co-)promoters in the submission tool (uploading Annex 1). Online links to CVs of the Flemish and partner promoter(s) are to be included. Check Annex 1 for more details: please use ORCID identifier for the Flemish promoter (and if applicable co-promoter)). For partner promoters (max. 1 per partner institution) any readable online CV is requested, but if not available, then add a CV as attachment in the online submission form. CVs of co-promoters are optional.

Please take note that in the case of an MSP, a representative of a non-HE actor could be indicated as a team member or partner co-promoter, but not as a (main) partner promoter.

How is the project structured / organised? Describe the project’s organisational structure/governance, internal communication, and distribution of roles and responsibilities, with attention for balanced partnership structures and interinstitutional cooperation. In case multiple partners are involved at Flemish or partner level, the roles of each partner in the implementation and management of the project need to be explained.

The National Data Science Network will be organised to bring together institutions, experts, and communities around one shared goal: using data to strengthen Kenya’s health, agriculture, environment, and education systems. The project is built on a partnership model that values collaboration, transparency, and shared responsibility. KIPRE will lead the initiative as the national coordination hub, hosting the Data Science and Analytics Centre (DSAC). The project director at KIPRE will provide strategic oversight, while a deputy director manages day-to-day operations and ensures smooth communication between partners. Together, they will guide the network’s activities and maintain strong links with government ministries. UHasselt will serve as the Flemish partner, offering technical mentorship, support in advanced analytics, and guidance in curriculum development. Their technical lead will work closely with Kenyan teams to co-design training programmes, strengthen research capacity, and establish interoperable data systems that follow best practices. National institutions—including the National Public Health Institute (NPHI), the Directorate of Veterinary Services (DVS), the National Environment Management Authority (NEMA), and the Centre for Epidemiological Modelling and Analysis (CEMA)—will play central roles. Each institution will nominate a focal point responsible for coordinating local activities, sharing expertise, and ensuring adherence to data governance and ethical standards. The project will use a hub-and-spoke structure: KIPRE as the central hub for coordination and data integration, and partner institutions as spokes contributing specialised knowledge, datasets, and pathways for policy uptake. Regular steering committee meetings will bring together all focal points and the Flemish promoter to review progress, address emerging challenges, and jointly make decisions. To ensure inclusivity and accountability, an advisory board with representatives from government, civil society, and gender and equity experts will provide strategic guidance and ensure that the needs of underserved groups inform the project’s direction. Clear roles and responsibilities will support efficient implementation: • KIPRE will coordinate the network and manage infrastructure. • UHasselt will provide technical leadership and capacity-building. • Ministries, research bodies, and universities will contribute domain expertise and facilitate policy linkages. • DSAC focal points will oversee local workflows, mentor junior staff, and support compliance. Training and mentorship opportunities will be openly advertised, with selection criteria that emphasise gender balance, diversity, and inclusion. The structure promotes equal participation, shared ownership, and strong inter-institutional cooperation, ensuring that the network remains effective and sustainable beyond the project’s lifetime. Max. 2500 characters.

Describe, if relevant, the role and selection procedure of scholarship holders (master, PhD) in the project set-up. It is deemed crucial to already think about how this will be organised, in order to ensure a smooth start of the project.

Scholarship holders—whether at Master’s or PhD level—will play an important role in strengthening the technical backbone of the National Data Science Network. Their work will directly support DSAC activities in data integration, advanced analytics, and policy translation. They will contribute to applied research projects in areas such as disease surveillance, environmental modelling, agricultural risk prediction, and education data analysis, while also helping build demonstrator dashboards, methodological tools, and reproducible workflows for use by partner institutions. Their involvement will also reinforce the long-term sustainability of the network, as each scholarship holder will be attached to one of the participating institutions—KIPRE, NPHI, DVS, NEMA, or CEMA—ensuring that the skills gained remain within the national system. Joint supervision between UHasselt and Kenyan institutions will strengthen academic mentorship, encourage co-publication, and support the development of high-quality thesis work aligned with national priorities. The selection of scholarship holders will follow a transparent and competitive process. Calls will be publicly advertised across relevant ministries, universities, and research institutes. Eligibility criteria will emphasise academic merit, motivation, and alignment with project themes, while also ensuring strong representation of women and underserved groups in line with LNOB and gender equity principles. A selection panel composed of KIPRE, UHasselt, and partner institution representatives will review applications, conduct interviews, and match successful candidates to specific research projects and supervisors. This structured approach ensures that scholarship holders meaningfully contribute to the project’s operational work while building a new generation of skilled data scientists committed to Kenya’s long-term development. Max. 2000 characters

MIP / MSP set-up: Please indicate if you consider your project is a Multi-Institutional Partnership, meaning it structurally involves additional institutions of higher education in Belgium/locally, and/or whether it is a Multi-Stakeholder Partnership with non-academic actors.

MIP: No

MSP: Yes

In case Yes, then explain the added value of this MIP collaboration setting for the project, at the level of partner HE&SIs and/or Flemish HEIs; or at the level of the different actors in an MSP.

This project is designed as a Multi-Stakeholder Partnership (MSP), bringing together a diverse group of institutions that each play a critical role in Kenya’s data ecosystem. While it is not a Multi-Institutional Partnership (MIP) on the Flemish side, the MSP model provides considerable added value for both impact and sustainability. The partnership links KIPRE, the NPHI, the DVS, the NEMA, and the CEMA, working closely with UHasselt as the technical and academic lead. By involving these actors from the health, agriculture, environment, and education sectors, the project reflects the complexity of real-world challenges and ensures that solutions are practical, relevant, and nationally owned. The MSP structure adds value in several ways. First, it ensures that the project draws from the strengths of each institution—whether scientific expertise, access to data, policy influence, or operational capacity—allowing the DSAC to function as a truly national resource. Second, it promotes shared ownership and accountability, reducing the fragmentation that has historically limited Kenya’s ability to use data effectively for early warning, preparedness, and policy development. Third, working with multiple stakeholders speeds up uptake of project outputs, as institutions involved in generating evidence are the same ones responsible for using it in decision-making. For UHasselt, the MSP provides a strong platform for co-created research, co-supervision, and long-term collaboration across sectors. For Kenyan institutions, it strengthens capacity through embedded mentorship, harmonised data practices, and sustained interaction with international expertise. Ultimately, the MSP structure creates a realistic pathway for the DSAC to be scalable, inclusive, and sustainable well beyond the project lifecycle. Max. 2000 characters

# Module 4: Stakeholders and coherence

4.1. Stakeholder management

Stakeholder management strategy Stakeholder management refers to the management of the interactions with the most important stakeholders of a project (external to the project team e.g., knowledge users (farmers, policy makers, etc.), intermediaries (NGO’s), etc.), contributing to the realisation of the project outcomes and impact (e.g., the end-users of the project results, knowledge users). Explain how the project will manage stakeholders or engage with them (see examples above).

The success of the National Data Science Network (NDSN) relies on sustained and meaningful engagement with stakeholders who generate, manage, and use data across Kenya’s health, agriculture, environment, and education sectors. The project therefore adopts a structured, inclusive, and adaptive stakeholder management strategy to ensure that project outputs are relevant, credible, and effectively used in policy and practice. Internal stakeholders include researchers, analysts, and technical staff from partner institutions, who will serve as institutional focal points for data integration, analysis, and coordination through the Data Science and Analytics Centre (DSAC). These stakeholders will actively contribute to the co-development of analytical tools, workflows, and governance frameworks, while participating in targeted training and mentoring activities. Early-career researchers and trainees form a critical internal group, as they represent the future human capacity sustaining the network beyond the project period. External stakeholders include national policymakers from key ministries, who depend on timely and reliable evidence for preparedness, planning, and response. Civil society organisations, intermediaries, and community-based knowledge users will be engaged to ensure that project outputs reflect real needs and local contexts. International partners, particularly Belgian academic partner, will contribute through technical mentoring, joint supervision, and methodological guidance, strengthening both quality and credibility. Stakeholder engagement will follow a tiered approach based on influence and interest. High-influence stakeholders, such as ministerial decision-makers and institutional leadership, will be closely involved through advisory structures, joint planning meetings, and structured consultations aligned with national priorities. Stakeholders with high interest but lower influence, including junior researchers, civil society actors, and community representatives, will be engaged through participatory research activities, workshops, and open dialogue. Broader stakeholder groups will be kept informed through dashboards, briefs, and regular updates to maintain transparency and identify emerging collaboration opportunities. Uptake of results will be supported through continuous interaction rather than one-off dissemination. The project will use policy briefs, interactive dashboards, training sessions, webinars, and practical demonstrations to support integration of evidence into routine decision-making. Engagement processes will be guided by gender-sensitive and Leave No One Behind principles to ensure inclusive participation and representation. Finally, coherence with national and international initiatives will be ensured through systematic mapping of related programmes and coordination with other VLIR-UOS initiatives and development actors. This approach strengthens synergies, avoids duplication, and builds trust, enabling long-term collaboration and sustained impact of the NDSN beyond the project lifetime.

Next to the narrative, please identify the project’s 5 most important stakeholders.

List of 5 key stakeholders

National Government Ministries (Knowledge users & Decision-makers)

Local Research and Academic Institutions (Core implementing partners)

Data Science and Analytics Centre (DSAC) – Coordination hub

Civil Society Organizations and Community Knowledge Users (Intermediaries & End-users)

International Academic Partners (Technical & Strategic partners)

4.2. Coherence

Coherence is about the complementarity of the project with the actions and networks of other actors and/or other HES4SD initiatives. Elaborate on how the project is coherent with: other VLIRUOS funded activities (e.g. with TEAM, SI, ITP, IUC, Global Minds projects, ICP Connect, PSP, etc.) (internal coherence); - other actors/projects (e.g., local, partner country level, regional, Belgian non-governmental actors, etc.) (external coherence) Please note that lessons learned from previous experiences from earlier projects and/or between the project partners fit in Module 8.

The National Data Science Network is fully aligned with the broader VLIR-UOS HES4SD portfolio. Building on existing ICP Connect and Global Minds initiatives at UHasselt, the project leverages established analytical expertise, teaching materials, and ethical data practices to strengthen Kenya’s evidence-based decision-making. The DSAC functions as a national coordination centre, harmonising methodologies, integrating fragmented datasets, and providing an operational layer that reinforces prior TEAM and SI projects. This ensures continuity, avoids duplication, and maximises the impact of VLIR-UOS investments. Nationally, the project complements the mandates of key institutions, including the National Public Health Institute, Directorate of Veterinary Services, National Environment Management Authority, and the Climate and Environmental Monitoring bodies. By standardising data systems, creating interoperable platforms, and enabling cross-sectoral analytics, the DSAC enhances institutional capacity, supports early-warning systems, and facilitates coordinated, evidence-informed interventions. This strengthens complementarity by allowing these institutions to maintain their mandates while benefiting from shared infrastructure and methodological support. Regionally, the network connects with East African initiatives on infectious disease modelling, climate risk assessment, and food systems resilience, promoting knowledge exchange, data interoperability, and regional comparability. International coherence is maintained through partnerships with UHasselt and Belgian development actors, providing technical mentorship, capacity reinforcement, and opportunities for scaling. By embedding DSAC within national and regional ecosystems and aligning with prior VLIR-UOS initiatives, the project ensures complementarity, maximises institutional synergies, and establishes a sustainable, multi-stakeholder network. It positions local institutions as drivers of long-term change, fostering evidence-based policy, cross-sectoral collaboration, and capacity retention beyond VLIR-UOS funding.

# Module 5: Planning and budgeting

📝 Plan your activities over the different activity years per project domain

For the budget, please use the budget annex, a separate excel sheet to be uploaded to the online tool

Budget – value for money Motivate your requested budget. Elaborate on how much will be spent on the different activities and why you choose this repartition. Particular attention should be given to (a) any personnel costs, (b) investment costs. Explain the main financial focus/needs of your project (explain link with core activities; share of investment, personnel/operational/scholarship costs) and any in-kind co-funding at the level of the partner institution. Identify what parts of the budget will be managed by which partner (Flemish/partner HEI(s)), and in particular in the case of interinstitutional collaborations with multiple promoters reflect on how the budget will be managed (incl. any redistribution of local coordination costs).

The planning and budgeting for the National Data Science Network (NDSN) are structured around practical project needs and the long-term goal of strengthening Kenya’s capacity for evidence-informed decision-making. Activities are organised across five domains, capacity building, infrastructure and institutional strengthening, research and methodological development, multi-stakeholder engagement, and knowledge dissemination, each with defined timelines and responsibilities shared between Kenyan and Flemish partners. Capacity building runs throughout the project and combines short courses, professional certificates, mentorship, and exchange programmes with UHasselt. Training targets data scientists, analysts, and technical staff from ministries, universities, and research institutes. The budget covers facilitators, materials, travel support, and digital learning platforms, with deliberate attention to gender balance, regional diversity, and inclusion of underrepresented groups. Infrastructure and institutional strengthening focuses on establishing the Data Science and Analytics Centre (DSAC), including servers, secure cloud solutions, and essential software tools. These investments are central to integrating national datasets and sustaining analytics workflows. Technical staff from KIPRE, NPHI, NEMA, DVS, and CEMA will oversee installation and maintenance, with UHasselt providing technical guidance. Research and methodological development comprises joint projects applying advanced analytics, predictive modelling, outbreak forecasting, environmental monitoring, on integrated datasets. Budget allocations support operational costs, local data collection, collaborative research meetings, and skill transfer activities that strengthen scientific output. Multi-stakeholder engagement will be maintained annually through policy dialogues, consultation workshops, and joint planning sessions with government departments, civil society, and private-sector partners. Budget covers convening and coordination costs to ensure ownership, relevance, and uptake of results. Knowledge dissemination and uptake includes public workshops, dashboards, policy briefs, and stakeholder forums, translating technical outputs into actionable insights. Funds are allocated to communication materials, digital platforms, and outreach travel, with a focus on reaching marginalised communities. Project management supports coordination, financial oversight, reporting, and monitoring. Personnel costs are lean, with dedicated coordination roles where necessary. Budget management is shared: UHasselt oversees Flemish expenditures, while KIPRE manages local costs. In-kind contributions—office space, partial staff time, and administrative support—enhance efficiency. In summary, the budget balances infrastructure, human capacity, and operational needs to ensure value for money. Investments in DSAC and training create durable institutional capacity, while operational funds sustain innovation, collaboration, and the translation of evidence into practice across sectors.

# Module 7: Monitoring

Approach of monitoring & quality assurance Selected projects will be asked to report on a limited set of generic, standard indicators (e.g., number of peer reviewed publications, extension/outreach/capacity-building activities realised, uptake/influence of new skills/, # of PhD and Master scholars directly supported by the project, etc.). Complementary, in this section of the proposal, briefly describe how you will assess/monitor the results of your specific project (can be both qualitative and quantitative) during and at the end of the project.

Monitoring and quality assurance will be embedded throughout the project to ensure activities remain on track and generate meaningful, real-world results. In addition to standard VLIR-UOS indicators, a set of project-specific measures will focus on capacity building, institutional strengthening, and the actual uptake of DSAC outputs by partner institutions and end-users, the “last mile” of impact. At the individual level, Master’s and PhD scholars, as well as trainees from partner organisations, will be monitored through learning assessments, milestone reviews, supervision reports, and evaluations of the practical application of acquired skills. This ensures that training translates into measurable improvements in analytical and technical capacity that can inform decision-making. At the institutional level, monitoring will assess progress toward adopting shared data standards, implementing secure and ethical data workflows, and strengthening collaboration among technical teams. Indicators will include documentation of datasets and metadata, pilot testing of controlled access mechanisms, and evidence that analytical outputs are integrated into routine operations that affect service delivery. At the system and policy level, the focus will be on the use of DSAC outputs, such as dashboards, policy briefs, and prototype analytical tools, in decision-making that reaches communities and vulnerable populations. Qualitative feedback from ministries, agencies, and technical working groups will capture the relevance, usability, and influence of these outputs on real-world interventions, ensuring that project benefits extend to the last mile. A combination of quantitative and qualitative methods, disaggregated by institution, gender, and stakeholder type, will be used. Routine documentation, quarterly review meetings, and a DSAC monitoring dashboard will provide real-time updates to partners and VLIR-UOS, supporting adaptive management and early identification of risks. Monitoring level; Key indicators; Methods. Individuals (MSc/PhD); Training completion, research milestones, practical skill uptake; Pre- and post-tests, supervision reports, assignments. Institutions; Adoption of shared data standards, workflows applied in operational contexts; Technical logs, documentation checks, meeting minutes. System & Policy; Uptake of DSAC outputs in decision-making impacting communities; Stakeholder feedback, observation of interventions. Cross-cutting; Gender/LNOB inclusion, quality of collaboration; Surveys, interviews, attendance records. Max. 2.000 characters

# Module 8: Learning and steering

Project track record: Indicate whether this project proposal is a continuation of an existing VLIRUOS funded intervention, or a re-submission (note: a checkbox will be included in the online submission tool) - List, if relevant, previous experiences, projects between the project partners and describe the achievements / actions already undertaken. How will the lessons learned from previous experiences be taken on board? - In case of follow-up projects, or in case of an earlier IUC partnership, what is the added value of this project? In case the project is a re-submission of a proposal submitted previously in VLIRUOS calls for proposals, please also indicate how you dealt with shortcomings as compared to a previous proposal. Note: If this is a first-time project, the question below can be left open.

The Kenya Institute of Primate Research (KIPRE) has a strong history of collaborations with national institutions and Flemish partners through VLIR-UOS funding. Previous initiatives, such as the IPMB workshops and the RECON project, have strengthened capacity in molecular biology, zoonotic disease surveillance, and cross-border animal disease management. IPMB provided intensive training for Kenyan researchers and laboratory upskilling, while RECON established cross-border Foot-and-Mouth Disease surveillance protocols and promoted multi-sectoral communication. Lessons from these projects highlight the importance of sustained capacity building, integrated One Health approaches, and translating research outputs into actionable policy. KIPRE’s ongoing collaborations with key national partners form the foundation for this project. With NPHI, KIPRE advances zoonotic disease research, snakebite envenoming interventions, and local vaccine and drug development. Work with DVS focuses on transboundary animal disease research, ethical animal management, and data-driven disease control strategies. Collaboration with CEMA involves epidemiological modeling, spatial analysis, and predictive tools to translate field and laboratory data into actionable insights. NEMA engages with KIPRE on ecosystem health, environmental determinants of disease, and GIS-based monitoring of land use and biodiversity to inform conservation and public health policy. These partnerships have built institutional capacity, developed skilled research teams, and fostered multi-stakeholder networks. Key lessons learned, such as the need for interoperable data systems, structured stakeholder engagement, and continuous skills development, directly inform the design of the National Data Science Network. The added value of this project lies in its focus on creating a national coordination hub, the DSAC, that integrates health, agricultural, environmental, and educational data in real time. Unlike previous projects, which were sector-specific or focused on individual capacity building, this initiative strengthens institutional and systemic capacity across multiple sectors, promotes multisectoral collaboration, and embeds mechanisms for sustainable data use, governance, and knowledge sharing. By leveraging past experiences while scaling impact nationally, the project ensures enduring contributions to evidence-based policy and development in Kenya.

Confirm this proposal was developed together (partner in Flanders and partner country) and was not AI-generated (e.g. for the context analysis). If generative AI was used: explain how and to what extent

This proposal was developed collaboratively by the partners in Kenya and Flanders, including KIPRE, NPHI, DVS, NEMA, CEMA, and Hasselt University (UHasselt). All sections, including the context analysis, project design, and operational planning, were jointly drafted and reviewed by the human project team to ensure accuracy, feasibility, and alignment with national priorities. Generative AI tools were not used to create any substantive content of this proposal. Any minor use of AI was limited to formatting or language suggestions, without affecting the project rationale, design, or data. The ideas, objectives, methodologies, and partnerships presented here reflect the knowledge, experience, and planning of the project partners. Maximum 1000 characters

# Annexes

Annex 1: Excel with tabs per module for formulation

| General information | General information on the project |
| --- | --- |
| Module 3 | Information on who is involved in the project and its organisational structure. Please be aware that the institutions linked to the Flemish promoters (max. 1 in Belgium) and partner promoters (1 or multiple in the partner country, max. 1 per partner institution). Institutions of Flemish or local co-promoters are not contracted. |
| Module 5 | Activities (= activity plan, organised per intermediate change domain, with indication of who is responsible for the activity) |

Annex 2: TEAM budget format

Mandatory Annexes without format

Annex 3: CVs of the (main) promoters (in case not submitted as an online link)

Annex 4: Endorsement letter of the partner institution(s)

Optional Annexes : Letter of support of formalised Synergy in case of a Multi-Stakeholder Partnership (MSP)/Multi-Institutional Partnership (MIP) set-up ; Complementary Endorsement letters of other partner institutions in the project proposal (apart from the Endorsement letter(s) of the partner promoter(s) (if any)

Note: This Word format is a working document, only meant as a preparatory format to help you in preparing your proposal. t as this information needs to be included in an online environment, the project submission tool.

For visualization purposes limited here to main promoters/institutions, but full details to be included in the submission tool.

Module 1 is strongly linked with the selection criterion 1. relevance and coherence.

Please do no tick all the boxes for all of the outcomes, but simply those that are important to your project (max. 3), and explain how your project aligns with the standard VLIR-UOS outcomes that have been marked.

Fit with selection criterion 2 on the Quality of the design of the proposal (descriptor 2.1.)

Multi-Institutional Partnership (MIP): This concerns a structural collaboration between several higher education institutions at Flemish/Belgian (including the Institute of Tropical Medicine (ITM)) and/or partner level within the framework of a project, with the aim of obtaining better results by pooling available expertise.

Multi-Stakeholder Partnership (MSP): this concerns a structural collaboration with at least 1 non-academic actor (= multi-stakeholder; civil society, private sector, governmental actors, etc.) within the framework of a project, in which this actor plays an active role in the project implementation.

HES4SD: Higher Education for Sustainable Development, referring hereby more especifically to the thematic Joint Strategic Framework of Belgian Scientific actors ARES, ITM and VLIRUOS.

Please check out our financial framework document, section TEAM projects, and take into account the good practices related to the share (%)of these categories in relation to the overall budget’. A good practice is to keep the share of personnel costs as limited as possible, and to limit investment costs to an indicative max. of 25% of the total budget.

Please note Module 6 is not applicable for TEAM projects.

In the exceptional case that the project proposal is submitted by a Flemish postdoc, the CV of the Flemish co-promoter with min. 10% ZAP status should also be added.

Endorsement letter: institutional support letter, referring to the employment link of the main partner promoter with a (recognized higher education) partner institution, and the support of this same institution to the project. The letter should be signed at least by an authority at Faculty level, but preferable by the vice-chancellor.

No other annexes will be considered