## WP 24-25
Results Areas | Main Activities | Sub Activities | Expected Outputs | Performance Indicators | Target | Means of verification |  | 2024/25 | [16 empty] | GOK |  | Funding Gap
[7 empty] | GOK | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2-Q4 | Q2 | Q3 | Q4 |  | Source of funding
Mapping of snakes of medical importance and snakebite Hotspots | Identify and map Snakes of Medical Importance and other venomous snakes, map intra and intercounty snakebite hotspots in endemic counties | Train 5 program officers on mapping of snakes of Medical Importance and other venomous snakes using the Geographic Information System.(GIS) | program officers trained on mapping of snakes of Medical Importance and other venomous snakes using the GIS system | Number of program officers trained | 5 | Training programes/ schedules, training certificates | [13 empty] | 250000 | 0 | 0 | 0 | 0 | 250000
|  | Procure voice recorders, digital camera, data collection tablets, laptops, GIS communication devices, power banks, high definition binoculars, printer, N ViVo analysis software, tents (10 units) | Items procured | Number of items procured | 73 | Invoices, DOF, Receipts | [13 empty] | 4843716 | 0 | 0 | 0 | 0 | 4843716
|  | Conduct a 5 day workshop for the training of data collectors on snakebite community-based survey methodologies in 5 counties (Kilifi, Marsabit, Wajir, Makueni, Samburu) | Data collectors trained on community-based survey methodologies | number of data collectors trained per county | 5 | Training certificates | [13 empty] | 5160000 | 7740000 | 2580000 | 2580000 | 2580000 | 12900000
|  | Survey 5 counties to map snakebite incidences (Procure subsistence allowance for 10 county data collectors, transport and DSA for 10 public officers for 3 weeks per county) | counties surveyed for venomous snake identification and GIS mapping | Number of counties surveyed, Species of snakes of medical importance and other venomous snakes identified, Number of county geographical maps developed | 5 | Vehicle work tickets, county approval letters, complete Snake species data sheets, County geographical maps | [13 empty] | 8169000 | 12628000 | 3934000 | 4347999 | 4347999 | 20797000
| Integrate Snakebite Envenoming mapping with other NTD programs | Train healthcare workers and community healthcare promoters on protocols in integrating Snakebite Envenoming mapping with other NTD programs in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with other NTD programs | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 734000 | 1101000 | 367000 | 367000 | 367000 | 1835000
|  | Conduct surveys to integrate Snakebite Envenoming mapping with other NTD programs in 5 counties. (procure transport and DSA for 10 public officers for 5 days per county ) | 10 counties surveyed for integration of snakebite envenoming mapping with other NTD programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 1970000 | 2955000 | 985000 | 985000 | 985000 | 4925000
|  | Develop a user friendly community based reporting tool to report snakebite incidences and deaths across 5 counties | Tool for reporting community-based snakebite incidences and deaths developed | Number of reporting tools developed | 1 | reporting tool populated across 8 counties | [13 empty] | 0 | 300000 | 300000 | 0 | 0 | 300000
|  | Conduct a validation survey to assess and validate the reach and impact of surveys to integrate Snakebite Envenoming mapping with other NTD in 5 counties (procure transport and DSA for 10 public officers for 5 days per county) | validation surveys conducted | Number of counties where validation surveys were conducted | 5 | Validation report, Vehicle work tickets | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Disseminattion of survey findings to 5 counties (procure transport and DSA for 10 public officers for 12 days, 2 days per county- total 10 counties ) | Dissemination conducted in counties where integration of snakebite envenoming mapping with other NTD programs was conducted | Number of sub counties where dissemination was conducted | 5 | Report | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Integrate Snakebite mapping with the Kenya Livestock MasterPlan (KLMP) | Train livestock ward officers and community healthcare promoters on protocols in integrating Snakebite integrating snakebite mapping with the KLMP in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with the Livestock program | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 578000 | 867000 | 289000 | 289000 | 289000 | 1445000
|  | Survey 5 counties to integrate snakebite mapping with the KLMP in 5 counties (procure transport and DSA for 5 public officers for 10 days per county ) | 5 counties surveyed for integration of snakebite envenoming mapping with other NTDs, Malaria and Livestock programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 3600000 | 5400000 | 1800000 | 1800000 | 1800000 | 9000000
|  | Conduct public awareness campaigns on snake identification, snakebite first aid and prevention and control measures in 5 counties | awareness campaigns to educate communities on snakebite first aidnd prevention and control measures held | Number of awareness campaigns held | 5 | Meeting notices, Photos | [13 empty] | 1792400 | 2688600 | 896200 | 896200 | 896200 | 4481000
|  | Engage Social media, website & other digital platforms to create awareness on snake identification, snakebite first aid and prevention and control measures | Social media, website & other digital platforms engaged | Number of Social media, website & other digital platforms Engaged | 10 | Active Social Media Handles, Website | [13 empty] | 500000 | 0 | 0 | 0 | 0 | 500000
|  | Conduct five school-based campaigns in each of the 10 counties to raise awareness among children on snake identification, first aid measures, and snakebite prevention and control. | school based campaigns to raise awareness on snake identification, first aid measures and prevention and control of snakebite conducted (educational games, puppetries) | Number of school based campaigns conducted | 50 | mpaign reports, attendance records, photographs, feedback forms | [13 empty] | 2170000 | 3255000 | 1085000 | 1085000 | 1085000 | 5425000
|  | Disseminate survey findings to 10 Counties (Kitui, Turkana, Lamu, Kwale, Baringo, Samburu) (procure transport and DSA for 15 public officers for 5 days) | Dissemination conducted in counties where integration of snakebite envenoming mapping with KLMP programs was conducted | Number of sub counties where dissemination was conducted |  | Report | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | [18 empty] | 29767116 | 36934600 | 12311533.3333 | 12311533.3333 | 12311533.3333 | 66701716
Strengthen the Human Resource for snakebite management and antivenom production | Human Resource and personnel | [18 empty] | 2655000 | 7965000 | 2655000 | 2655000 | 2655000 | 10620000
| Train health care workers on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures | Conduct a county level Trainer of Trainer (ToT) trainings on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures to capacity build across different health care carders in 5 counties. Procure training venue, provide daily subsistence allowance (DSA) for 5 officers, and lunch allowance for 20 healthcare workers per county, for a duration of 5 days per county | County ToTs trained on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measure | Number of counties trained | 5 | County approvals, Training Reports, training certificates, attendance sheets | [13 empty] | 4860000 | 7290000 | 2430000 | 2430000 | 2430000 | 12150000
|  | Conduct a Kenya Health Reporting System (KHIS) training workshop to county and subcounty Health Records Information Officers (HRIOs) to ensure complete accurate and timely reporting of snakebite and antivenom utilization data in 5 counties. Procure conference venue, transport, DSA for 5 officers, allowance for 20 (HRIOs) | county and subcounty HRIOs trained on snakebite reporting in the KHIS | Number of counties trained | 5 | Training reports | [13 empty] | 2762000 | 4143000 | 1381000 | 1381000 | 1381000 | 6905000
| Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures | organise a 5 day workshop to develop, update and improve CHP training modules Information, Education and Communication (IEC) materials on snakebite awareness, first aid measures and prevention and control of snakebite (secure workshop venue, transport and DSA for 15 officers) | CHP training modules, IEC materials developed (posters, pullup banners, leaflets, T-shirts, lesos, Caps, brochures, pamplets) | Number of IEC materials developed, Number of training modules imptroved | 1 | workshop report, attendance list, IEC materials and training mannuals | [13 empty] | 1214000 | 1821000 | 1821000 | 0 | 0 | 3035000
|  | Launch CHP training programs in 5 counties. procure workshop venue, transportation and DSA for 5 officers for 5 days per county. | County CHP training programes launched | Number of CHP Training programs launched | 5 | Attendance sheets, county approval letters, invitation letters, photos | [13 empty] | 3174800 | 4762200 | 1587400 | 1587400 | 1587400 | 7937000
|  | Train CHPs on snake species identification, snakebite diagnosis, first aid, prevention and control measures. (Procure IEC tools to populate amongst CHPs, procure workshop venue, transportation and DSA for 5 officers for 5 days per county) | CHPs trained on snakebite diagnosis, treatment, management and rehabilitation | Number of counties where CHPs were trained | 5 | Training reports, training certificates | [13 empty] | 2504000 | 3756000 | 1252000 | 1252000 | 1252000 | 6260000
|  | Implement Motorcycle Snakebite Emergency Response System (SERS) for Community Health Promoters (CHPs) to efficiently respond to snakebite incidents within the community. Procure fuel and maintenance for 6 motorcycle ambulances in 6 counties. | motorcycle ambulances fuel and maintenance service procured | Number of maintenance services per county | 4 | fuel invoices, receipts | [13 empty] | 0 | 2130000 | 710000 | 710000 | 710000 | 2130000
Subtotal | [19 empty] | 17169800 | 31867200 | 10622400 | 10622400 | 10622400 | 49037000
Grand total | [24 empty] | 115738716

## Sheet1
Sub activity 1
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Training fee | 50000 | 5 | 1 | 1 | 250000 | 250000 | 0 | 0 | 0
Total |  |  |  |  | 250000 | 250000 | 0 | 0 | 0
Sub activity 2
Survey materials (U5)
Item | No. | QTY | Unit cost | Total |  | Q1 | Q2 | Q3 | Q4
Voice Recorder | No. | 10 | 20000 | 200000 |  | 200000 | 0 | 0 | 0
External Hards Disk 3TB | No. | 5 | 26000 | 130000 |  | 130000 | 0 | 0 | 0
Digital Cameras | No. | 1 | 490000 | 490000 |  | 490000 | 0 | 0 | 0
laptops | nos | 2 | 280000 | 560000 |  | 560000 | 0 | 0 | 0
Tablets | nos | 20 | 90000 | 1800000 |  | 1800000 | 0 | 0 | 0
Power Bank | nos | 20 | 10000 | 200000 |  | 200000 | 0 | 0 | 0
GPS Communicaton Devices | nos | 10 | 50000 | 500000 |  | 500000 | 0 | 0 | 0
Tents |  | 10 | 40000 | 400000 |  | 400000 | 0 | 0 | 0
Printer | nos | 1 | 50000 | 50000 |  | 50000 | 0 | 0 | 0
computer software | nos | 2 | 131858 | 263716 |  | 263716 | 0 | 0 | 0
High Defination Binoculars | No. | 10 | 25000 | 250000 |  | 250000 | 0 | 0 | 0
Total |  |  |  | 4843716 |  | 4843716 | 0 | 0 | 0
Sub activity 3 | [10 empty] | Training materials
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4 |  | Flip chart | no | 20 | 2000 | 40000
Per diem | 14000 | 10 | 10 | 5 | 7000000 | 2800000 | 1400000 | 1400000 | 1400000 |  | Flip chart stand | no | 5 | 10000 | 50000
conference | 5000 | 10 | 10 | 5 | 2500000 | 1000000 | 500000 | 500000 | 500000 |  | Roller Banners |  | 5 | 15000 | 75000
fuel cost | 200 | 85 | 10 | 5 | 850000 | 340000 | 170000 | 170000 | 170000 |  | Projector |  | 1 | 280000 | 280000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Tear Drops |  | 20 | 15000 | 300000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | printing | no | 1000 | 1000 | 1000000
Subsistence allowance (Data collectors) | 2500 | 10 | 10 | 5 | 1250000 | 500000 | 250000 | 250000 | 250000 | [5 empty] | 1745000
Training allowance (hrs) | 2000 | 4 | 30 | 5 | 1200000 | 480000 | 240000 | 240000 | 240000
training materials | 10000 | 2 | 1 | 5 | 100000 | 40000 | 20000 | 20000 | 20000
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 12900000 | 5160000 | 2580000 | 2580000 | 2580000
12900000
Sub activity 4 | [5 empty] | Q1 (Samburu, Makueni) | Q2 (Kilifi) | Q3 (Marsabit) | Q4 (Wajir)
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 21 | 5 | 14700000 | 5880000 | 2940000 | 2940000 | 2940000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 21 | 5 | 1785000 | 714000 | 357000 | 357000 | 357000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Air ticket | 28000 | 2 | 1 | 2 | 112000 | 112000 |  | 0 | 0
Subsistence allowance | 2500 | 10 | 21 | 5 | 2625000 | 1412000 | 163000 | 525000 | 525000
Training allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security | 5000 | 5 | 21 | 3 | 1575000 |  | 525000 | 525000 | 525000
[5 empty] | 0 | 0 | 0 | 0 | 0
training materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 20797000 | 8118000 | 3985000 | 4347000 | 4347000
20797000
Sub activity 5 (U8)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 1 | 5 | 700000 | 280000 | 140000 | 140000 | 140000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 1 | 5 | 85000 | 34000 | 17000 | 17000 | 17000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 5000 | 30 | 1 | 5 | 750000 | 300000 | 150000 | 150000 | 150000
Training allowance | 2000 | 5 | 6 | 5 | 300000 | 120000 | 60000 | 60000 | 60000
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 1835000 | 734000 | 367000 | 367000 | 367000
1835000
Sub activity 6 (U9)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 5 | 5 | 3500000 | 1400000 | 700000 | 700000 | 700000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000 | 170000 | 85000 | 85000 | 85000
vehicle maintenance | 200000 | 1 | 1 | 5 | 1000000 | 400000 | 200000 | 200000 | 200000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 4925000 | 1970000 | 985000 | 985000 | 985000
4925000
Sub activity 7
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Reporting tool/app | 300000 | 1 | 1 | 1 | 300000 | 0 | 300000 | 0 | 0
Total |  |  |  |  | 300000 | 0 | 300000 | 0 | 0
Sub activity 10
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 1 | 5 | 700000 | 280000 | 140000 | 140000 | 140000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 1 | 5 | 85000 | 34000 | 17000 | 17000 | 17000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 30 | 1 | 5 | 300000 | 120000 | 60000 | 60000 | 60000
Training allowance | 2000 | 5 | 6 | 6 | 360000 | 144000 | 72000 | 72000 | 72000
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 1445000 | 578000 | 289000 | 289000 | 289000
1445000
Sub activity 11 (U14)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 10 | 5 | 7000000 | 2800000 | 1400000 | 1400000 | 1400000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 10 | 5 | 850000 | 340000 | 170000 | 170000 | 170000
vehicle maintenance | 0 | 0 | 0 | 0 | 500000 | 200000 | 100000 | 100000 | 100000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 100000 | 1 | 1 | 5 | 500000 | 200000 | 100000 | 100000 | 100000
Media | 0 | 0 | 0 | 0 | 150000 | 60000 | 30000 | 30000 | 30000
Total |  |  |  |  | 9000000 | 3600000 | 1800000 | 1800000 | 1800000
9000000
Sub activity 12 (U15) | [5 empty] | 2018000
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 5 | 5 | 3500000 | 2018000 | 494000 | 494000 | 494000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000 | 170000 | 85000 | 85000 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Air ticket | 28000 | 2 | 1 | 1 | 56000 | 0 | 56000 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 500000 | 1 | 1 | 1 | 500000 | 500000 | 0 | 0 | 0
Media | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 4481000 | 2688000 | 635000 | 579000 | 579000
4481000
Sub activity 13 (U17)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
intracounty Media awareness | 100000 | 1 | 1 | 5 | 500000 | 500000 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
Total |  |  |  |  | 500000 | 500000 | 0 | 0 | 0
Sub activity 14 (U17) | [5 empty] | Q1 | Q2 | Q3 | Q4
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 5 | 3500000 | 1400000 | 700000 | 700000 | 700000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000 | 170000 | 85000 | 85000 | 85000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000 | 200000 | 100000 | 100000 | 100000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 200000 | 1 | 1 | 5 | 1000000 | 400000 | 200000 | 200000 | 200000
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 5425000 | 2170000 | 1085000 | 1085000 | 1085000
5425000
Sub activity 15 (U19)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Research personnel facilitation per month | 885000 | 1 | 12 | 1 | 10620000 | 2655000 | 2655000 | 2655000 | 2655000
Total |  |  |  |  | 10620000 | 2655000 | 2655000 | 2655000 | 2655000
Sub activity 16 (U21)
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 3 | 5 | 2100000 | 840000 | 420000 | 420000 | 420000
conference | 5000 | 35 | 3 | 5 | 2625000 | 1050000 | 525000 | 525000 | 525000
Training allowance | 2000 | 5 | 30 | 5 | 1500000 | 600000 | 300000 | 300000 | 300000
Subsistence allowance | 5000 | 20 | 5 | 5 | 2500000 | 1000000 | 500000 | 500000 | 500000
fuel cost | 200 | 85 | 5 | 5 | 425000 | 170000 | 85000 | 85000 | 85000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000 | 0 | 100000 | 100000 | 100000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 500000 | 1 | 1 | 5 | 2500000 | 700000 | 666667 | 666667 | 666667
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 12150000 | 4360000 | 2596667 | 2596667 | 2596667
12150001
Sub activity 17
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 3 | 5 | 2100000 | 840000 | 420000 | 420000 | 420000
conference | 5000 | 25 | 3 | 5 | 1875000 | 750000 | 375000 | 375000 | 375000
Training allowance | 2000 | 10 | 18 | 5 | 1800000 | 720000 | 360000 | 360000 | 360000
Subsistence allowance | 5000 | 5 | 3 | 5 | 375000 | 150000 | 75000 | 75000 | 75000
fuel cost | 200 | 85 | 3 | 5 | 255000 | 102000 | 51000 | 51000 | 51000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000 | 200000 | 100000 | 100000 | 100000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 6905000 | 2762000 | 1381000 | 1381000 | 1381000
6905000
Sub activity 18
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 5 | 1 | 700000 | 700000 | 0 | 0 | 0
conference | 5000 | 10 | 5 | 1 | 250000 | 250000 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 1 | 85000 | 85000 |  | 0 | 0
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 2000000 | 1 | 1 | 1 | 2000000 | 179000 | 1821000 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 3035000 | 1214000 | 1821000 | 0 | 0
3035000
Sub activity 19
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 14000 | 10 | 5 | 5 | 3500000 | 1400000 | 700000 | 700000 | 700000
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training allowance | 2000 | 5 | 30 | 5 | 1500000 | 600000 | 300000 | 300000 | 300000
Subsistence allowance | 2000 | 20 | 2 | 5 | 400000 | 160000 | 80000 | 80000 | 80000
fuel cost | 200 | 85 | 5 | 5 | 425000 | 170000 | 85000 | 85000 | 85000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000 | 200000 | 100000 | 100000 | 100000
Air ticket | 28000 | 4 | 1 | 1 | 112000 | 44800 | 22400 | 22400 | 22400
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 150000 | 1 | 1 | 10 | 1500000 | 600000 | 300000 | 300000 | 300000
Total |  |  |  |  | 7937000 | 3174800 | 1587400 | 1587400 | 1587400
7937000
Sub activity 20
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
conference | 5000 | 35 | 6 | 5 | 5250000 | 2100000 | 1050000 | 1050000 | 1050000
fuel cost | 200 | 85 | 6 | 5 | 510000 | 204000 | 102000 | 102000 | 102000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subsistance allowance (CHPs) | 2000 | 20 | 2 | 5 | 400000 | 160000 | 80000 | 80000 | 80000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 100000 | 1 | 1 | 1 | 100000 | 40000 | 20000 | 20000 | 20000
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 6260000 | 2504000 | 1252000 | 1252000 | 1252000
6260000
Sub activity 15
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Q1 | Q2 | Q3 | Q4
Per diem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
conference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 6 | 3 | 5 | 180000 | 0 | 60000 | 60000 | 60000
fuel cost | 200 | 5 | 90 | 5 | 450000 | 0 | 150000 | 150000 | 150000
vehicle maintenance | 100000 | 1 | 3 | 5 | 1500000 | 0 | 500000 | 500000 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 2130000 | 0 | 710000 | 710000 | 710000
2130000
|  |  |  | Grand total |  | Q1 | Q2 | Q3 | Q4
[6 empty] | 47281516 | 24029067 | 22214067 | 22214067
115738717
68457201