## Sheet1
Antivenom Quality Control, Development and Production Department Work Plan and Budget
|  | Assay/Activity | Reagents and consumables | Equiment | Common consumables | Note/Comments | Quantities | Cost in KShs | Timelines
1 | Permits acquisition | NACOSTI research license |  |  |  |  | 1 | 10000 | June to July 2024
|  | WRTI research permit |  |  |  |  | 1 | 10000 | June to July 2024
|  | NEMA access permit |  |  |  |  | 1 | 50000 | June to July 2024
|  | ISERC ethical permit |  |  |  |  | 1 | 13300 | June to July 2024
| Subtotal | [6 empty] | 83000
2 |  | Snake capture | Snake handling tools |  |  | tongs and hooks | 4 each | 64000 | June to August 2024
|  |  | Antivenom (SAIMR Polyvalent) |  |  |  | 20 | 700000 | June to August 2024
|  |  | Mobilisation and sensitization DSA |  |  | The cost covers 6 counties and included facilitation of KWS personnel | 5 days | 1118800 | June to August 2024
|  |  | Logistics, subsistence and travel |  |  | The cost covers 6 counties and included DSA for herpetologists, veterinarian, nurse, research scientist, driver and sporters. It also includes vehicle fuel and maintenance | 5 days | 2697000 | June to August 2024
|  |  | Fist Aid Kit |  |  |  | 2 | 17000 | June to August 2024
|  |  | Personal Protective Equipment (PPE) |  |  | This includes head shield, snake handling gloves, body shield and gaiters, protective boot/safty boots, cleaning rubber gloves, gumboots, dust coats |  | 116500 | June to August 2024
|  | Snake venom extraction and lyophilization | Bijou bottles, beakers, extraction stands |  |  | 40 bijous, 40 beakers, 2 stands | 82 | 44000 | June to August 2024
|  |  | Eye wash and mounted station |  |  |  | 6 | 60000 | June to August 2024
|  |  |  | Refrigerator (-20° C, +4 °C) |  |  | 1 | 170000 | June to August 2024
|  |  |  | Biosafety cabinet Class II B2 |  |  | 1 | 1058600 | June to August 2024
|  |  |  | Analytical weighing balance |  |  | 1 | 217000 | June to August 2024
|  | Herpetologist risk allowance |  |  |  | Risk allowance for two herpetologist at 10,000 each per month | 12 months | 240000 | June to August 2024
|  | Snake feeding |  |  |  |  | 12 months | 1664000 | June to August 2024
|  | Animal enrichment | trap boxes, water bowls/drinkers and bedding |  |  |  | 12 months | 321600 | June to August 2024
|  | Infrastructure |  | HVAC system |  |  | 1 | 1920000 | June to August 2024
|  |  |  | Automatic lighting system |  |  | 1 | 75000 | June to August 2024
|  |  |  | Snake rooms renovation |  | To enable housing of a larger number of snakes |  | 1000000 | June to August 2024
|  |  |  | Snake cages |  |  | 40 | 1280000 | June to August 2024
|  |  |  | snake racks |  |  | 14 | 168000 | June to August 2024
|  |  |  | CCTV camera installation and security system |  |  |  | 750000 | June to August 2024
| Subtotal | [6 empty] | 13734700
3 | Snake venom characterization | SDS-PAGE | Tris buffer, Glycine, SDS powder, Glycerol, bromophenol blue, Coomassie brilliant blue stain, acetic acid |  |  |  | 2 each | 345000 | June to December 2024
|  |  | serological pipettes (5, 10, 25 and 50ml) |  |  | 1000 pcs of 5, 10, and 25 ml serological pipettes and 500 pcs of 50ml pipettes |  | 184205 | June to December 2024
|  |  |  | Gel electrophoresis system (casting plates, electrode assembly, companion running module, buffer tank and lid, casting stand and frames, Power Pac |  | Link to equipment (https://www.bio-rad.com/en-ke/product/mini-protean-tetra-vertical-electrophoresis-cell?ID=N3F2UD4VY) | 1 | 650000 | June to December 2024
[5 empty] | Eppendorf tubes (1.5ml), 10X PBS, 50 ml falcon tubes, tips (200ul and 1000ul), Filtered tips (10ul, 200ul, 1000ul), absolute ethanol, absolute methanol | 6 eppendor packs, 5 bottles of 10X PBS, 5 bottles of ethanol, 5 boxes of methanol, 10x10x96 tips |  | 401000 | June to December 2024
|  | Chromatography | sodium phosphate (monobasic, dibasic, tribasic) |  |  |  | 2 each | 35190 | June to December 2024
|  |  | 0.2 µm filter, Nalgene rapid flow sterile disposable filter units with PES membranes |  |  | 1 pack of 12 filters | 4 packs | 264452 | June to December 2024
|  |  |  | Columns ( Sephadex G25 desalting column, RP-HPLC, Hydrophobic interactions columns) |  | Link to column (https://www.cytivalifesciences.com/en/us/shop/chromatography/prepacked-columns/desalting-and-buffer-exchange/hitrap-desalting-columns-with-sephadex-g-25-resin-p-05853) | 1 each | 419830 | June to December 2024
|  | Mass spectrometry | N/A | N/A |  | Set aside funds for sample processing (Strathmore university or KEMRI Kilifi) |  | 2400000 | June to December 2024
|  |  |  | Thermo orbitrap Fusion Lumos Mass spectrometer |  | Procure equipment to enable local mass spectrometric analysis of samples. Cost inclusive of equipment charges, freight charges, and training. Link to equipment (https://www.labx.com/item/thermo-orbitrap-fusion-lumos/scp-79351-b1b743fd-96fa-459d-a17d-c220737858a2) | 1 | 29738800
|  | Venom Biochemistry (Zymography, proteolytic, PLA2, Fibrinogenolytic, hemolytic and blood coagulation assays) | Gelatin, Triton X-100, Azocasein, Trichloroacetic acid, Sodium Phosphate, Agarose, Petridishes, Human Fibrinogen, Sodium citrate tubes, CaCl2, NaCl, NaOH, Purified protease from bovine plasma, DNA from Calf thymus |  |  |  | 2 each | 540560 | June to December 2024
|  |  |  | Microplate Spectophotometer (Preferred wavelength range 200 -999 nm) |  | Link to equipmet (https://www.agilent.com/en/product/microplate-instrumentation/microplate-readers/absorbance-microplate-readers/biotek-epoch-2-microplate-spectrophotometer-1623181) |  | 4417595 | June to December 2024
|  | Transcriptomics | Extraction kits and reagents |  | 4 | RNA extraction, mRNA enrichment, cDNA library, RNA sequencing |  | 3850000
|  |  |  | Illumina Hiseq 2500 |  | For sequencing of samples. Cost inclusive of equipment and freight charges. Link to equipment (https://shop.labexchange.com/en/703820-b00036376-illumina-hiseq-2500.html) |  | 8920670
| Subtotal | [6 empty] | 52137302
4 | Animal immunization (Horse) | Farm renting or acquisition |  |  |  | Acquire land to house research animals or rent a farm and include quarantine area |  | 2200000 | June to December 2024
|  | Purchase of animals (Horses) |  |  |  | Estimate of 600,000 ksh per horse | 24 | 14400000 | June to December 2024
|  | DSA for staff |  |  |  | Daily subsitence allowance paid to the Senior Veterinarian, Veterinarian and research scientist to cover purchase of animals and farm acquistion | 5 days | 222000 | June to December 2024
|  | Veterinary care, monitoring and vaccinations | Vaccines, drugs |  |  | per year |  | 300000 | June to December 2024
|  | Animal maintenance cost |  |  |  | per year |  | 3000000
|  | Personnel |  |  |  | Need for more animal handlers and veterinarian |  |  | June to December 2024
|  | Sampling and immunization | Vacutainer tubes (EDTA and clot activator tubes), |  |  | 1 pack with 100 tubes | 100 packs each | 280000 | June to December 2024
|  |  | Tuberculin syringes |  |  | 1 pack with 100 syringes | 20 packs | 99740 | June to December 2024
|  |  | 0.22 µm filter mebrane |  |  |  | 250 pieces | 42250 | June to December 2024
|  |  | Adjuvants and 10X PBS |  |  |  | 10 each | 181800 | June to December 2024
|  |  | Biohazard bags |  |  | 1 pack has 50 bags | 10 packs | 34900 | June to December 2024
|  |  | Portable cooler box |  |  |  | 2 | 18000 | June to December 2024
|  |  | Cottoon wool and gauze |  |  | 500g | 20 | 10400 | June to December 2024
|  |  | surgical spirit and ethanol |  |  |  | 5 each | 25000 | June to December 2024
|  |  | PPE |  |  | overalls, boots, rain coats, safety googles |  | 85000 | June to December 2024
| Subtotal | [6 empty] | 20899090
5 | Sample Processing | Serum and plasma isolation | Cryovials |  |  | 1 pack has 50 pcs | 400 packs | 360000 | June to December 2024
|  |  | Cryoboxes |  |  | 1 pack had 4 pcs | 60 packs | 646472 | June to December 2024
|  |  | serological pipettes (5, 10 and 25ml) and disposable transfer pipettes |  |  | 1000 pcs of 5, 10, and 25 ml serological pipettes aand 1000 pcs of droppers | 5 packs each | 130715 | June to December 2024
|  |  | 15 ml polypropylene conical tubes |  |  | 200 pcs per pack | 10 packs | 35193 | June to December 2024
|  |  |  | Automatic pipet aid |  |  | 3 | 55461 | June to December 2024
|  |  |  | negative 80 freezer |  | For storage of serum and plasma samples | 2 | 1713254 | June to December 2024
| Subtotal | [6 empty] | 2941095
6 | In vitro immunological assays and antibody purification | ELISA | Tween 20, 96 well plates (Nunc flat bottom), Soy milk, horseradish peroxidase-conjugated rabbit anti-horse IgG secondary antibody, Coating buffer tablets, citric acid, ABTZ tablet, Hydrogen peroxide H2O2, |  |  |  |  | 450000 | June to December 2024
|  |  | SAIMR monovalent antivenom(Boomslang), EchiTab-Plusmonovalent antivenom , Saimr polyvalent |  |  |  | 120pkts | 250000 | June to December 2024
[5 empty] | Pipettes (P10, P20, P200, P1000), Multichannel pipettes (2 - 20 µl, 20-300) |  | 2 each | 627480 | June to December 2024
|  |  |  | ELISA washer and dispenser |  | Link to equipment (https://www.agilent.com/en/product/cell-analysis/microplate-dispensers?Product_Interest_Source=Marketing%20Campaign&source=Marketing%20Campaign&Lead_Campaign_Source=7011O000002TCTjQAO&Campaign_Source=7011O000002TCTjQAO&gad_source=1&gclid=Cj0KCQjwu8uyBhC6ARIsAKwBGpSpXAvd7JSLVrIpu5maGXDEJokAJyS2weezJ1HIVREzXo9b0G-DVpoaAu1BEALw_wcB&gclsrc=aw.ds) |  | 4478642 | June to December 2024
|  | Western blotting | Dried skimmed milk, nitrocellulose membrane, Diaminobenzidine (DAB) substrate, primary and seconday antibody (see ELISA), |  |  |  |  | 120000 | June to December 2024
|  |  |  | Transblot transfer system |  | Link to equipment (https://www.bio-rad.com/en-ke/product/trans-blot-turbo-transfer-system?ID=LGOQBW15) |  | 965126 | June to December 2024
|  | Antibody purification (IgG and F(ab')2) | Caprylic acid, IgG purification Kits, dialysis cassettes, concentration devices |  |  |  |  | 1239212 | June to December 2024
|  |  | pepsin, ammonium sulfate, NaOH, NaCl, 0.22 µm filters |  |  | 1 kg for the reagents |  | 661329
|  |  |  | FPLC (AKTA pure)Protein A/G affinity chromatography columns (HiTrap Protein A HP 5ml and HiTrap Protein G HP 5ml) |  | Link to column (https://www.cytivalifesciences.com/en/us/shop/chromatography/prepacked-columns/affinity-specific-groups/hitrap-protein-g-hp-antibody-purification-columns-p-03524) and (https://www.cytivalifesciences.com/en/us/shop/chromatography/prepacked-columns/affinity-antibody/hitrap-protein-a-hp-antibody-purification-columns-p-06160) | 5 each | 911111
|  | in vitro quality control of purified antibody |  |  |  | Test for antivenom purity, pH,turbidity etc |  | 500000
| Subtotal | [6 empty] | 10202900
7 | In vivo pathological and neutralization assays | CD-1 Mice procurement |  |  |  | Procurement of CD-1 mice from Charles River Italy ( 10 males, 40 females) one off |  | 1600000 | June to August 2024
|  | Rodent house renovation and construction of preclinical testing lab |  |  |  | Develop a proper preclinical testing lab |  | 1200000
|  | Rodent house needs | Cages |  |  |  | 70 | 168000
|  |  | Water bottles |  |  |  | 100 | 80000
|  |  | Racks |  |  |  | 5 | 60000
|  |  | Mice beddings |  |  | cost per year |  | 6400
|  |  | mice feeding |  |  | cost per year |  | 481600
|  |  |  | Autoclave |  |  |  | 624352
|  | Median Lethal dose 50 (LD50) | 30 gauge insulin syringes, cotton wool, dissecting kit, formaldehyde, surgical spirit, |  |  | cost per year for in vivo assays |  | 1500000 | June to December 2024
|  | Median Effective dose 50 (ED50) | See LD50 | [5 empty] | June to December 2024
|  | Minimum Necrotic Dose (MND) and eMND | See LD50 | [5 empty] | June to December 2024
|  | Minimum Hemorrhagic Dose (MHD) and eMHD | See LD50 | [5 empty] | June to December 2024
|  | Personnel |  |  |  | Need to hire more personnel to assist with in vivo assays |  |  | June to December 2024
| Subtotal | [6 empty] | 5720352
8 | Production unit | Setting up a production unit at KIPRE |  |  |  | Setting up a production unit or developing a partnership with existing biological manufacturing centres. Cost indicated covers production, formulation, analysis of bulk product, packaging etc.. |  | 30000000
| Subtotal | [6 empty] | 30000000
9 | Naivasha Workshop | Progress Review and Planning Workshop for the Scientific Research Partnership for the Development of Anti-Necrosis Therapeutics for Snakebite (SRPNTS-NT) Project, manuscript review and GoK antivenom project planning |  |  |  | Participants: Dr. George Omondi, Valentine Musabyimana, Wathuto Ogopotse, Pamela Khasandi, Dennis Kotti, Jacob Lubuya, Brian Musau, Geoffrey Maranga, Fredrick Angote, Miheso Hannington, Munira Antar, Anne Saitoti, Thomas Adino, Priscilla Kimiti, Ezekiel Adino |  | 1060500 | May to June 2024
| Subtotal | [6 empty] | 1060500
10 | Other Activities and requirements | Laboratory requirements | Nitrile blue gloves (large, medium, small), Biohazard bags, disposable bags, dustbins, beakers, reagent bottles, flasks |  |  |  |  | 700000
|  |  |  | Liquid nitrogen tank |  | 50ml | 1 | 152000
|  |  |  | Medium centrifuge |  |  | 1 | 50157
|  |  |  | plus 5 and minus 20 refrigerator |  | double door (635 ltrs) | 1 | 280000
|  |  |  | lab stools |  |  | 15 | 75000
|  |  |  | Vortexer |  |  | 1 | 45000
|  |  |  | Eye wash and mounted stations |  |  | 5 | 50000
|  |  |  | Class II Biosafet cabinet |  |  | 1 | 1058600
|  |  |  | Power supply extension |  |  | 7 | 14000
|  |  |  | UPS |  |  | 3 | 323700
|  |  |  | Water distiller system |  |  |  | 3000000
|  | Personnel requirements | PPE (Lab coats, safety googles, etc..) |  |  |  |  | 270000
|  | Laboratory renovations | [5 empty] | 1500000
|  | Hiring of personnel |  |  |  | Need to hire more personnel (one veterinarian, two animal technicians, 2 animal handlers, biomedical engineer, production manager
|  | Staff training | [5 empty] | 2500000
|  | Staff research allowance and overtime |  |  |  |  | per year | 3500000
|  | Costa Rica or India Benchmarking trip |  |  |  | Visit antivenom manufacturing company In Costa rica (Clodomiro Picado institute) or India (premium serums vaccine producers) |  | 3000000
| Subtotal | [6 empty] | 19518457
11 | Miscellaneous |  |  |  |  | The contingency fee for unforseen costs that might arise |  | 1500000
| GRAND TOTAL | [6 empty] | 153736896
| Staff | Dr. George Omondi | Deputy Director
|  | Valentine Musabyimana | Research Scientist
|  | Geoffrey Maranga | Senior Herpetologist
|  | Fredrick Angote | Herpetologist
|  | Dr. Jacob Lubuya | Veterinarian
|  | Brian Musau | Research Scientist
|  | Pamela Khasandi | Research Scientist
|  | Dennis Kotti | Senior lab technologist
|  | Munira Antar | Research Scientist
|  | Anne Saitoti | Research Scientist
|  | Miheso Hannington | Lab technologist
|  | Lawi Totana | Animal handler
|  | Hussein Abass | Animal handler
|  | Thomas Adinoh | Animal Technician
|  | Priscilla Kimiti | Animal Technician