## ANNUAL WORK PLAN
NATIONAL MUSEUMS OF KENYA
NATURAL PRODUCT INDUSTRY
ANNUAL WORK PLAN FY 2025/2026
Strategy | Activity | Expected Output | Output Indicator | Target | Responsibility | Timeline |  |  |  | Budget (Ksh. Mn)
[6 empty] | Q1 | Q2 | Q3 | Q4
Pre-clinical research on anti obesity herbal products | Carry out in vitro studies on lipid metabolism using antiobesity herbal products | Invitro studies on lipid metabolism using antiobesity herbal products carried out | No. of herbal products tested | 4 | KIPRE | 1 | 1 |  |  | 4.36
| Conduct in vivo preliminary tests on antiobesity herbal products | in vivo preliminary tests on antiobesity herbal products conducted | No. of herbal products tested | 4 | KIPRE |  | 1 | 1 | 1 | 4.56
| Conduct a repeat of in vivo preliminary tests on antiobesity herbal products | repeat of in vivo preliminary tests on antiobesity herbal products conducted | No. of herbal products tested | 4 | KIPRE
TOTAL BUDGET | [9 empty] | #REF!

## budget
Description | Quantity | Unit cost (KShs) | Total cost (KShs)
Acquisition of rats (49 rats x for 7 herbal products) x3 | 147 | 500 | 73500
Per diem for rats (animal maintenance charges) (21 cages at 125/cage/day) for 77 days) | 1617 | 125 | 202125
Purchase of rats (breeders) (20 females, 5 males) | 25 | 500 | 12500
Administration of herbal product per cage/day 500 for 77 days | 1617 | 500 | 808500
Euthanasia charges (1000 per rat) | 147 | 1000 | 126000
Incineration ( 1 dollar per rat) | 147 | 100 | 14700
Ethical approval | 1 | 10000 | 10000
Total |  |  | 1247325
Bradford Reagent 500ml, | 2 | 50422 | 100844
Bovine Serum Albumin, 99% 99.00% 10g | 2 | 11478 | 22956
TRIS hydrochloride 1M solution (pH7.4) 500ml | 2 | 57641 | 115282
EDTA solution, 0.5M in water 0.49M 500ml | 2 | 14465 | 28930
Phenylmethanesulfonyl fluoride 0.98 5g | 2 | 17995 | 35990
2-Mercaptoethanol, molecular b. g.x50ML | 2 | 19708 | 39416
Agarose 100g | 2 | 14909 | 29818
10x TBE, 500 ml, in liquid form, | 2 | 6500 | 13000
SafeView Classic; Quantity: 1.0 ml, | 4 | 10588 | 42352
Ethidium bromide | 2 | 15067 | 30134
OneTaq DNA Polymerase - 200 units; | 2 | 11000 | 22000
Standard Taq (DF) Reaction Buffer -6ml | 2 | 5697 | 11394
Glycerol, 99.5%, Ph. Eur., USP, | 2 | 23992 | 47984
Modified RIPA Lysis Buffer (moderate-strong)-20ml | 2 | 14823 | 29646
Acrylamide/Bis-acrylamide,37.5:1,30% solution | 2 | 11320 | 22640
Ammonium persulfate 0.975 100g, | 2 | 8278 | 16556
N,N,N'',N''-Tetramethylethylendiamine 0.99 100ml, | 2 | 40834 | 81668
Wash, elution, storage buffers | 6 | 6450 | 38700
Glycine 98.50% 100g, CAS#: 56-40-6, MW of 75.07, | 2 | 10600 | 21200
Nitrocellulose mixed esters membrane. GVS. | 2 | 55086 | 110172
Bromophenol Blue 5g, CAS#: 115-39-9, MW of 669.98, | 2 | 5386 | 10772
Coomassie Brilliant Blue G250 (C.I.42655) 5g, | 2 | 9103 | 18206
Gel Loading Dye, Purple (6X) - 4,0 ml | 2 | 11010 | 22020
Tris-Glycine 10X - 1 litre | 2 | 24509 | 49018
PBS 1X, pH 7.4 solution IL, | 2 | 19977 | 39954
LDS sample buffer 4X (for PAGE using Bis-Tris or Tris Acetate gels) | 2 | 9415 | 18830
Gloves (box, packet of 10) | 26 | 1300 | 33800
PPAR gamma Transcription factor Assay kit | 3 | 178951 | 536853
SREBP- 1c assay KIT | 3 | 118287 | 354861
AMPK assay kit | 3 | 153450 | 460350
Adipogenesis assay kit | 3 | 50115 | 150345
oil red o stain kit | 3 | 38674 | 116022
Hormone-sensitive lipase assay kit | 3 | 90437 | 271311
Lipoprotein lipase activity assay kit | 3 | 74606 | 223818
Fatty acid oxidation complete assay kit | 3 | 115542 | 346626
Interleukin-6 (IL-6) Elisa Kit | 3 | 66435 | 199305
Interleukin-1 Beta (IL-1β) Elisa Kit | 3 | 66435 | 199305
Tumor Necrosis Factor-alpha (TNF-α) Elisa Kit | 3 | 66435 | 199305
Aluminum foil, roll | 12 | 950 | 11400
Paper towels, pkt | 65 | 480 | 31200
Microscope slides, pkt of 72 | 30 | 490 | 14700
Yellow tips 1000pcs | 6 | 2400 | 14400
Blue tips pkt 500pcs | 3 | 1800 | 5400
Ethanol GPR (20L) | 3 | 15000 | 45000
Bleach (5L) | 6 | 2900 | 17400
Face masks (box) | 30 | 600 | 18000
Gauge 18mm needles, pkt | 20 | 2500 | 50000
Butterfly needles, pkt | 20 | 2400 | 48000
2ml syringes pkts | 10 | 1400 | 14000
Orlistat -1 grams x 2 | 4 | 50000 | 200000
RBG (Glucometer strips) 50 pcs/pack x 11 | 66 | 2800 | 184800
OGTT (Glucometer strips) 50 pcs/pack x15 | 90 | 2800 | 252000
Glucometers (Accu-check Active Meter) | 10 | 8000 | 80000
8 ml red cap tubes, pkt of 100 | 10 | 3800 | 38000
Serum vials, 10x10 | 16 | 2400 | 38400
Gauze swabs, pkt | 80 | 480 | 38400
Cryovials (box, 500pcs) | 6 | 27500 | 165000
Centrifuge tubes, 15ml (box, 500) | 4 | 27500 | 110000
Centrifuge tubes, 50ml (500pcs) | 4 | 35000 | 140000
Eppendorf tubes (2ml), pkt of 500 | 4 | 3800 | 15200
High fat diet | 3 | 400000 | 1200000
Clinical chemistry at termination (126 samples) | 147 | 5000 | 735000
Histology (100 Kshs/slide) 2 slides per rat (adipose, liver) (126 rats) | 294 | 100 | 29400
Feacal DNA kit | 2 | 60000 | 120000
Next generational sequencing and analysis (3 samples per group) | 42 | 20000 | 840000
Gauze swabs, pkt | 40 | 480 | 19200
Coverslips, pkt of 10 | 4 | 1200 | 4800
10% SDS (w/v), 100 ml | 1 | 2709 | 2709
|  |  | 8593792 | 8593792

## Q1
Description | Quantity | Unit cost (KShs) | Total cost (KShs)
Bradford Reagent 500ml, | 1 | 50422 | 50422
Bovine Serum Albumin, 99% 99.00% 10g | 1 | 11478 | 11478
TRIS hydrochloride 1M solution (pH7.4) 500ml | 1 | 57641 | 57641
EDTA solution, 0.5M in water 0.49M 500ml | 1 | 14465 | 14465
Phenylmethanesulfonyl fluoride 0.98 5g | 1 | 17995 | 17995
2-Mercaptoethanol, molecular b. g.x50ML | 1 | 19708 | 19708
Agarose 100g | 1 | 14909 | 14909
10x TBE, 500 ml, in liquid form, | 1 | 6500 | 6500
SafeView Classic; Quantity: 1.0 ml, | 1 | 10600 | 10600
Ethidium bromide | 1 | 15067 | 15067
OneTaq DNA Polymerase - 200 units; | 1 | 11000 | 11000
Standard Taq (DF) Reaction Buffer -6ml | 1 | 5697 | 5697
Glycerol, 99.5%, Ph. Eur., USP, | 1 | 23992 | 23992
Modified RIPA Lysis Buffer (moderate-strong)-20ml | 1 | 14823 | 14823
Acrylamide/Bis-acrylamide,37.5:1,30% solution | 1 | 11320 | 11320
Ammonium persulfate 0.975 100g, | 1 | 8278 | 8278
N,N,N'',N''-Tetramethylethylendiamine 0.99 100ml, | 1 | 40834 | 40834
Wash, elution, storage buffers | 3 | 6450 | 19350
Glycine 98.50% 100g, CAS#: 56-40-6, MW of 75.07, | 1 | 10600 | 10600
Nitrocellulose mixed esters membrane. GVS. | 1 | 55086 | 55086
Bromophenol Blue 5g, CAS#: 115-39-9, MW of 669.98, | 1 | 5386 | 5386
SafeView Classic; Quantity: 1.0 ml, | 1 | 10588 | 10588
Coomassie Brilliant Blue G250 (C.I.42655) 5g, | 1 | 9103 | 9103
Gel Loading Dye, Purple (6X) - 4,0 ml | 1 | 11010 | 11010
Tris-Glycine 10X - 1 litre | 1 | 24509 | 24509
PBS 1X, pH 7.4 solution 1L, | 1 | 19977 | 19977
LDS sample buffer 4X (for PAGE using Bis-Tris or Tris Acetate gels) | 1 | 9415 | 9415
Gloves (box, packet of 10) | 1 | 13000 | 13000
PPAR gamma Transcription factor Assay kit | 1 | 178951 | 178951
SREBP- 1c assay KIT | 1 | 118287 | 118287
AMPK assay kit | 1 | 153450 | 153450
Adipogenesis assay kit | 1 | 50115 | 50115
oil red o stain kit | 1 | 38674 | 38674
Hormone-sensitive lipase assay kit | 1 | 90437 | 90437
Lipoprotein lipase activity assay kit | 1 | 74606 | 74606
Fatty acid oxidation complete assay kit | 1 | 115542 | 115542
Interleukin-6 (IL-6) Elisa Kit | 1 | 66435 | 66435
Interleukin-1 Beta (IL-1β) Elisa Kit | 1 | 66435 | 66435
Tumor Necrosis Factor-alpha (TNF-α) Elisa Kit | 1 | 66435 | 66435
Aluminum foil, roll | 3 | 950 | 2850
Paper towels, pkt | 5 | 480 | 2400
Microscope slides, pkt of 72 | 15 | 490 | 7350
Yellow tips 1000pcs | 2 | 2400 | 4800
Blue tips pkt 500pcs | 1 | 1800 | 1800
Ethanol GPR (20L) | 1 | 15000 | 15000
Bleach (5L) | 2 | 2900 | 5800
Paper towels (box) | 10 | 480 | 4800
Gloves (box, packet of 10) | 5 | 1300 | 6500
Face masks (box) | 10 | 600 | 6000
Total |  |  | 1599420

## Rats
Bradford reagent | Description | Quantity | Unit cost (KShs) | Total cost (KShs)
Bovine serum albumin (BSA) | Acquisition of rats (49 rats x for 7 herbal products) x3 | 147 | 500 | 73500
Tris HCl pH 8.1 - | Per diem for rats (animal maintenance charges) (21 cages at 125/cage/day) for 77 days) | 1617 | 125 | 202125
EDTA pH | Purchase of rats (breeders) (20 females, 5 males) | 25 | 500 | 12500
| Administration of herbal product per cage/day 500 for 77 days | 1617 | 500 | 808500
| Euthanasia charges (1000 per rat) | 147 | 1000 | 126000
| Incineration ( 1 dollar per rat) | 147 | 100 | 14700
| Ethical approval | 1 | 10000 | 10000
β-Mercaptoethanol--- | Total |  |  | 1247325
PMSF
1% (w/v) agarose gel in 1X TBE
SyBr (Red or Green)
Taq polymerase
TAQ buffer (10X)
100% Glycerol
1.25 M Na2HPO4
1.25 M KH2PO4
2.5 M NH4Cl
Lysis buffer
Wash buffer
Elution buffer
Storage Buffer
Acrylamide/Bis acrylamide solution (30%)
Ammonium Persulfate
TEMED
Glycine
Nitrocellulose membrane
1% bromophenol blue (w/v), 10 ml
Ethidium bromide (10mg/ml)
10% SDS (w/v), 100 ml
50% glycerol (v/v), 100 ml
Coomassie blue (100mL)
Coomassie destain (1L)
SDS-gel loading buffer (Dye 6x), non-reducing
LDS sample buffer 4X (for PAGE using Bis-Tris or Tris Acetate gels), non-reducing
0.05% PBS-T (1L)

## Q2
Description | Quantity | Unit cost (KShs) | Total cost (KShs)
Gauge 18mm needles, pkt | 20 | 2500 | 50000
Butterfly needles, pkt | 20 | 2400 | 48000
2ml syringes pkts | 10 | 1400 | 14000
Orlistat -1 grams x 2 | 4 | 50000 | 200000
RBG (Glucometer strips) 50 pcs/pack x 11 | 66 | 2800 | 184800
OGTT (Glucometer strips) 50 pcs/pack x15 | 90 | 2800 | 252000
Glucometers (Accu-check Active Meter) | 10 | 8000 | 80000
8 ml red cap tubes, pkt of 100 | 10 | 3800 | 38000
Serum vials, 10x10 | 16 | 2400 | 38400
Gauze swabs, pkt | 80 | 480 | 38400
Aluminum foil, roll | 6 | 950 | 5700
Paper towels, pkt | 20 | 480 | 9600
Cryovials (box, 500pcs) | 6 | 27500 | 165000
Centrifuge tubes, 15ml (box, 500) | 4 | 27500 | 110000
Centrifuge tubes, 50ml (500pcs) | 4 | 35000 | 140000
Eppendorf tubes (2ml), pkt of 500 | 4 | 3800 | 15200
Yellow tips 1000pcs | 4 | 2400 | 9600
Blue tips pkt 500pcs | 2 | 1800 | 3600
Ethanol GPR (20L) | 2 | 15000 | 30000
Bleach (5L) | 4 | 2900 | 11600
Paper towels (box) | 20 | 480 | 9600
Gloves (box, packet of 10) | 20 | 1300 | 26000
Face masks (box) | 20 | 600 | 12000
High fat diet | 3 | 400000 | 1200000
Total |  |  | 2691500

## Q3 & 4
Description | Quantity | Unit cost (KShs) | Total cost (KShs)
Clinical chemistry at termination (126 samples) | 147 | 5000 | 735000
Histology (100 Kshs/slide) 2 slides per rat (adipose, liver) (126 rats) | 294 | 100 | 29400
PPAR gamma Transcription factor Assay kit | 2 | 178951 | 357902
SREBP- 1c assay KIT | 2 | 118287 | 236574
AMPK assay kit | 2 | 153450 | 306900
Interleukin-6 (IL-6) Elisa Kit | 2 | 66435 | 132870
Interleukin-1 Beta (IL-1β) Elisa Kit | 2 | 66435 | 132870
Tumor Necrosis Factor-alpha (TNF-α) Elisa Kit | 2 | 66435 | 132870
Feacal DNA kit | 2 | 60000 | 120000
Next generational sequencing and analysis (3 samples per group) | 42 | 20000 | 840000
Gauze swabs, pkt | 40 | 480 | 19200
Aluminum foil, roll | 3 | 950 | 2850
Paper towels, pkt | 10 | 480 | 4800
Microscope slides, pkt of 72 | 15 | 490 | 7350
Coverslips, pkt of 10 | 4 | 1200 | 4800
Bradford Reagent 500ml, | 1 | 50422 | 50422
Bovine Serum Albumin, 99% 99.00% 10g | 1 | 11478 | 11478
TRIS hydrochloride 1M solution (pH7.4) 500ml | 1 | 57641 | 57641
EDTA solution, 0.5M in water 0.49M 500ml | 1 | 14465 | 14465
Phenylmethanesulfonyl fluoride 0.98 5g | 1 | 17995 | 17995
2-Mercaptoethanol, molecular b. g.x50ML | 1 | 19708 | 19708
Agarose 100g | 1 | 14909 | 14909
10x TBE, 500 ml, in liquid form, | 1 | 6500 | 6500
SafeView Classic; Quantity: 1.0 ml, | 1 | 10600 | 10600
Ethidium bromide | 1 | 15067 | 15067
OneTaq DNA Polymerase - 200 units; | 1 | 11000 | 11000
10% SDS (w/v), 100 ml | 1 | 2709 | 2709
Standard Taq (DF) Reaction Buffer -6ml | 1 | 5697 | 5697
Glycerol, 99.5%, Ph. Eur., USP, | 1 | 23992 | 23992
Modified RIPA Lysis Buffer (moderate-strong)-20ml | 1 | 14823 | 14823
Acrylamide/Bis-acrylamide,37.5:1,30% solution | 1 | 11320 | 11320
Ammonium persulfate 0.975 100g, | 1 | 8278 | 8278
N,N,N'',N''-Tetramethylethylendiamine 0.99 100ml, | 1 | 40834 | 40834
Wash, elution, storage buffers | 3 | 6450 | 19350
Glycine 98.50% 100g, CAS#: 56-40-6, MW of 75.07, | 1 | 10600 | 10600
Nitrocellulose mixed esters membrane. GVS. | 1 | 55086 | 55086
Bromophenol Blue 5g, CAS#: 115-39-9, MW of 669.98, | 1 | 5386 | 5386
SafeView Classic; Quantity: 1.0 ml, | 1 | 10588 | 10588
Coomassie Brilliant Blue G250 (C.I.42655) 5g, | 1 | 9103 | 9103
Gel Loading Dye, Purple (6X) - 4,0 ml | 1 | 11010 | 11010
Tris-Glycine 10X - 1 litre | 1 | 24509 | 24509
PBS 1X, pH 7.4 solution IL, | 1 | 19977 | 19977
LDS sample buffer 4X (for PAGE using Bis-Tris or Tris Acetate gels) | 1 | 9415 | 9415
Adipogenesis assay kit | 2 | 50115 | 100230
oil red o stain kit | 2 | 38674 | 77348
Hormone-sensitive lipase assay kit | 2 | 90437 | 180874
Lipoprotein lipase activity assay kit | 2 | 74606 | 149212
Fatty acid oxidation complete assay kit | 2 | 115542 | 231084
Liquid nitrogen | 10 | 500 | 5000
TOTAL |  |  | 4319596