## Revised 3mwp
Results Areas | Main Activities | Sub Activities | Expected Outputs | Performance Indicators | Target | Means of verification | 2023/24 |  |  | Estimated Cost | Approved Budget (Rec & Dev) |  | Off-budget resources |  | Funding Gap
[7 empty] | April | May | June |  | GOK | Source of funding | Amount | Source of funding
Mapping of snakes of medical importance and snakebite Hotspots | Conduct coverage surveys to map Snakebite Hotspots | Apply for ethical approvals and NACOSTI permits to conduct householdsurveys for the mapping of snakebite hotspots in 30 counties | applications for the Ethical approvals and NACOSTI permits submitted | Number of ethical approvals and NACOSTI | 4 | Ethical approvals, NACOSTI permits |  |  |  | 200000
|  | Procure a venue for a 3-day stakeholders meeting with county health management teams in two counties (Kitui, Turkana) to obtain approvals for conducting surveys to map snakebite hotspots. (Procure transport, conference, DSA for 15 officers for 3 days per county) | Venue to hold stakeholders meetings with county health management teams procured | Number of venues procured, number of county approval letters acquired. | 2 | Invoice receipts, Attendance sheets, county approval letters |  |  |  | 2092000 | [5 empty] | 0
|  | Conduct a 5 day workshop for the training of county data collectors on snakebite community-based survey methodologies in 2 counties (Kitui, Turkana) | Data collectors trained on community-based survey methodologies | number of data collectors trained per county | 2 | Training certificates |  |  |  | 2215000
|  | Conduct community based surveys in 2 counties (Kitui, Turkana) to map snakebite hotspots (Procure transport, subsistenance allowance for 10 data collectors, and DSA for 10 public officers for 3 weeks per county | 2 counties surveyed to map snakebite hotspots | Number of counties surveyed | 2 | survey questionnaires, geographic maps |  |  |  | 8494000
| Integrate Snakebite Envenoming mapping with other NTD programs | Conduct a 10-day workshop with national stakeholders to develop protocols for integrating snakebite management with existing MoH-NTD programs and develop a snakebite database. (Procure transport, conference, DSA for 15 officers for 3 days per county) | common integration programs on snakebite prevention and intervention identified, integration protocols and SOPs developed, Dashboard for mapping of snakes of medical importance and snakebite hotspots created | number of integration programs identified, number of protocols developed, Number of dashboards created and intergrated into the MoH-NTD database | 1 | workshop programme, attendance sheet, Meeting agendas and minutes, venue payment receipts, Database |  |  |  | 3970000
|  | Train county and sub county healthcare workers and community health promoters on protocols in 3 counties (Homa Bay, Siaya, Migori) | healthcare workers and community healthcare promoters in 3 counties trained on protocols in integrating Snakebite Envenoming mapping with other NTD programs | number of counties trained | 3 | training schedules, attendance sheets, photo evidence |  |  |  | 1542000
|  | Conduct surveys to integrate Snakebite Envenoming mapping with other NTD programs in 3 counties (Homa Bay, Siaya, Migori) (procure transport and DSA for 10 public officers for 10 days per county ) | 3 counties surveyed for integration of snakebite envenoming mapping with other NTD programs | Number of counties surveyed | 3 | Maps of surveyed counties, Vehicle work tickets, county approval letters |  |  |  | 3725000
| Integrate Snakebite mapping with the Kenya Livestock MasterPlan (KLMP) | Organize a one-week workshop with national stakeholders from the Kenya Ministry of Agriculture to integrate snakebite mortality mapping into the Kenya Livestock Master Plan (KLMP) and develop training and data collection protocols for livestock ward officers and community health promoters to support this integration. | common integration programs on snakebite prevention and intervention identified, Integration protocols and SOPs in integrating Snakebite Envenoming mapping with Livestock KLMP program developed | number of integration programs on snakebite prevention and intervention | 1 | workshop programme, attendance sheet, Meeting agendas and minutes, venue payment receipts, Integrated program protocols, SOPs |  |  |  | 1160000
|  | Train livestock ward officers and community healthcare promoters on protocols in integrating Snakebite integrating snakebite mapping with the KLMP in 3 counties (Kisumu, Siaya, Migori) | healthcare workers and community healthcare promoters in 8 counties trained on protocols in integrating Snakebite Envenoming mapping with other NTDs, Malaria and Livestock programs | number of counties trained | 3 | training schedules, attendance sheets, photo evidence |  |  |  | 1143000
|  | Conduct surveys to Integrate snakebite mapping with the KLMP in 3 counties (procure transport and DSA for 5 public officers for 10 days per county ) | 3 counties surveyed for integration of snakebite envenoming mapping with other NTDs, Malaria and Livestock programs | Number of counties surveyed | 3 | Maps of surveyed counties, Vehicle work tickets, county approval letters |  |  |  | 5660000
|  | Engage Social media, website & other digital platforms to create awareness on snake identification, snakebite first aid and prevention and control measures | Social media, website & other digital platforms engaged | Number of Social media, website & other digital platforms Engaged | 3 | Active Social Media Handles, Website |  |  |  | 500000
Subtotal | [9 empty] | 30501000
Strengthen the Human Resource for snakebite management and antivenom production | Train health care workers on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures | Conduct a training needs assessment across 2 counties (Turkana, Kitui) to evaluate the requirements for training healthcare workers in snakebite diagnosis, management, antivenom administration, and prevention and control measures (procure transportation and DSA for 5 officers, 3 weeks per county) | training needs assessment to evaluate the requirements for training healthcare workers in snakebite diagnosis, management, antivenom administration, and prevention and control measures conducted | Needs assessment reports per county | 2 | Finalized assessment reports |  |  |  | 1370000
|  | Conduct a 5 day Workshop to develop training manuals on snake identification snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures (procure workshop venue, transportation and DSA for 5 officers) | training mannuals on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures developed. | number of training mannuals developed | 2 | workshop reports, Training manuals, Vehicle work tickets, |  |  |  | 1760000
|  | Conduct a county level Trainer of Trainer (ToT) trainings on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures to capacity build across different health care carders in 2 counties (Kitui, Turkana). Procure training venue, provide daily subsistence allowance (DSA) for 15 officers, and lunch allowance for 20 healthcare workers per county, for a duration of 5 days per county | County ToTs trained on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measure | Number of counties trained | 2 | County approvals, Training Reports, training certificates, attendance sheets |  |  |  | 3620000
| Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures | Train CHPs on snake species identification, snakebite diagnosis, first aid, prevention and control measures. (Procure IEC tools to populate amongst CHPs, procure workshop venue, transportation and DSA for 5 officers for 5 days per county) | CHPs trained on snakebite diagnosis, treatment, management and rehabilitation | Number of counties where CHPs were trained | 2 | Training reports, training certificates |  |  |  | 3120000
Subtotal | [9 empty] | 6750000
Grandtotal | [9 empty] | 37251000

## 3 M-Budget
Sub activity 1
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Sub activity
Per diem | 14000 | 15 | 14 | 2 | 5880000 | ITEM | UNIT COST | QTY | Days | counties | TOTAL
conference | 0 | 0 | 0 | 0 | 0 | Per diem | 14000 | 20 | 10 | 1 | 2800000
fuel cost | 200 | 85 | 14 | 2 | 476000 | conference | 5000 | 20 | 10 | 1 | 1000000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | fuel cost | 200 | 85 | 10 | 1 | 170000
Air ticket | 28000 | 5 | 1 | 1 | 140000 | vehicle maintenance | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | Air ticket | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0 | Subsistence allowance | 0 | 0 | 0 | 0 | 0
training materials | 0 | 0 | 0 | 0 | 0 | Training allowance | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 6496000 | training materials | 0 | 0 | 0 | 0 | 0
[6 empty] | Total | 0 | 0 | 0 | 0 | 3970000
Sub activity 2 | [5 empty] | chmt budget
ITEM | UNIT COST | QTY | Days | counties | TOTAL | ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 2 | 3 | 840000 | Per diem | 14000 | 15 | 3 | 2 | 1260000
conference | 5000 | 10 | 2 | 2 | 200000 | conference | 5000 | 15 | 3 | 2 | 450000
fuel cost | 0 | 0 | 0 | 0 | 0 | fuel cost | 200 | 85 | 3 | 2 | 102000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 28000 | 5 | 1 | 1 | 140000 | Air ticket | 28000 | 5 | 1 | 2 | 280000
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | Subsistence allowance | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0 | Training allowance | 0 | 0 | 0 | 0 | 0
training materials | 0 | 0 | 0 | 0 | 0 | Security | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0 | training materials | 0 | 0 | 0 | 0 | 0
[5 empty] | 1180000 | Media | 0 | 0 | 0 | 0 | 0
2092000
Sub activity 3
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 2 | 1400000
conference | 5000 | 10 | 5 | 2 | 500000
fuel cost | 200 | 85 | 5 | 2 | 170000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Training allowance | 2500 | 5 | 5 | 2 | 125000
training materials | 10000 | 1 | 1 | 2 | 20000
Media | 0 | 0 | 0 | 0 | 0
2215000
Sub activity 4
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 21 | 2 | 2940000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 21 | 2 | 714000
vehicle maintenance |  |  |  |  | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 5000 | 10 | 21 | 2 | 2100000
Training allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 200000 | 1 | 1 | 2 | 400000
Media | 0 | 0 | 0
6654000
Sub activity 5
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 1 | 700000
conference | 5000 | 10 | 5 | 1 | 250000
fuel cost | 200 | 85 | 5 | 1 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 1035000
Sub activity 6
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 3 | 2 | 420000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 3 | 2 | 102000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 5000 | 30 | 3 | 2 | 900000
Training allowance | 2000 | 5 | 6 | 2 | 120000
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1542000
Sub activity 7 | [5 empty] | Sub activity
ITEM | UNIT COST | QTY | Days | counties | TOTAL | ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 12 | 5 | 3 | 2520000 | Per diem | 14000 | 10 | 21 | 2 | 5880000
conference | 0 | 0 | 0 | 0 | 0 | conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 3 | 255000 | fuel cost | 200 | 85 | 21 | 2 | 714000
vehicle maintenance | 0 | 0 | 0 | 0 | 500000 | vehicle maintenance | 0 | 0 | 0 | 0 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0 | Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | Subsistence allowance | 2500 | 10 | 21 | 2 | 1050000
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | Subsistence allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 100000 | 1 | 1 | 3 | 300000 | Data collection materials | 100000 | 1 | 1 | 2 | 200000
Media | 0 | 0 | 0 | 0 | 150000 | Media | 0 | 0 | 0 | 0 | 150000
[5 empty] | 3725000 | [5 empty] | 8494000
Sub activity 8
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 10 | 3 | 4200000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 10 | 3 | 510000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
[5 empty] | 4710000 | Sub activity 9
[6 empty] | ITEM | UNIT COST | QTY | Days | counties | TOTAL
Sub activity 9 | [5 empty] | Per diem | 14000 | 15 | 5 | 10 | 10500000
ITEM | UNIT COST | QTY | Days | counties | TOTAL | conference | 5000 | 15 | 5 | 10 | 3750000
Per diem | 14000 | 5 | 5 | 1 | 350000 | fuel cost | 200 | 85 | 5 | 10 | 850000
conference | 5000 | 5 | 5 | 1 | 125000 | vehicle maintenance | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 1 | 85000 | Air ticket | 0 | 0 | 0 | 0 | 0
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | Subsistence allowance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0 | Training allowance | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0 | Printing materials | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0 | Media | 0 | 0 | 0 | 0 | 0
Printing materials | 100000 | 1 | 1 | 6 | 600000 | [5 empty] | 15100000
Media | 0 | 0 | 0 | 0 | 0
1160000
Sub activity 10
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 3 | 3 | 630000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 3 | 3 | 153000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 20 | 3 | 3 | 360000
Training allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1143000
Sub activity 11
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 10 | 3 | 4200000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 10 | 3 | 510000
vehicle maintenance | 0 | 0 | 0 | 0 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 100000 | 1 | 1 | 3 | 300000
Media | 0 | 0 | 0 | 0 | 150000
5660000
Sub activity 13
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 15 | 5 | 3 | 3150000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 3 | 255000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 28000 | 2 | 1 | 1 | 56000
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 500000 | 1 | 1 | 1 | 500000
Media | 0 | 1 | 1 | 0 | 0
3961000
Sub activity 14
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 15 | 7 | 3 | 4410000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 7 | 3 | 357000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 200000 | 1 | 1 | 3 | 600000
Media | 0 | 0 | 0 | 0 | 0
5867000
Sub activity 15
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 5 | 2 | 700000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 2 | 170000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1370000
Sub activity 16
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 5 | 1 | 350000
conference | 5000 | 5 | 5 | 1 | 125000
fuel cost | 200 | 85 | 5 | 1 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 200000 | 1 | 1 | 6 | 1200000
Media | 0 | 0 | 0 | 0 | 0
1760000
Sub activity 17
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 5 | 2 | 700000
conference | 5000 | 25 | 5 | 2 | 1250000
Training allowance | 2000 | 5 | 30 | 2 | 600000
Subsistence allowance | 2000 | 20 | 5 | 2 | 400000
fuel cost | 200 | 85 | 5 | 2 | 170000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
3620000
Sub activity 18
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 5 | 1 | 350000
conference | 5000 | 5 | 5 | 1 | 125000
fuel cost | 200 | 85 | 5 | 1 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 2000000 | 1 | 1 | 1 | 2000000
Media | 0 | 0 | 0 | 0 | 0
2560000
Sub activity 19
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 15 | 5 | 3 | 3150000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 3 | 255000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 28000 | 4 | 1 | 1 | 112000
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 150000 | 1 | 1 | 3 | 450000
4467000
Sub activity 20
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 0 | 0 | 0 | 0 | 0
conference | 5000 | 35 | 5 | 3 | 2625000
fuel cost | 200 | 85 | 5 | 3 | 255000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Subsistance allowance (CHPs) | 1000 | 20 | 5 | 3 | 300000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 100000 | 1 | 1 | 1 | 100000
Media | 0 | 0 | 0 | 0 | 0
3280000
Sub activity 21
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 15 | 3 | 6 | 3780000
conference | 5000 | 15 | 1 | 6 | 450000
fuel cost | 200 | 85 | 3 | 6 | 306000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Subsistance allowance (CHMT) | 5000 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
4536000
Sub activity 23
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 0 | 0 | 0 | 0 | 0
conference | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 6 | 3 | 4 | 144000
fuel cost | 200 | 5 | 90 | 4 | 360000
vehicle maintenance | 100000 | 1 | 3 | 4 | 1200000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1704000
Sub activity 17
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 5 | 5 | 2 | 700000
conference | 5000 | 25 | 5 | 2 | 1250000
Training allowance | 2000 | 5 | 30 | 2 | 600000
Subsistence allowance | 2000 | 20 | 5 | 2 | 400000
fuel cost | 200 | 85 | 5 | 2 | 170000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
3120000

## Revised 1ywp
Results Areas | Main Activities | Sub Activities | Expected Outputs | Performance Indicators | Target | Means of verification |  | 2024/25 | [11 empty] | Estimated Cost | Approved Budget (Rec & Dev) |  | Off-budget resources |  | Funding Gap
[7 empty] | GOK | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | GOK | Source of funding | Amount | Source of funding
Mapping of snakes of medical importance and snakebite Hotspots | Identify and map Snakes of Medical Importance and other venomous snakes, map intra and intercounty snakebite hotspots in endemic counties | Train 5 program officers on mapping of snakes of Medical Importance and other venomous snakes using the Geographic Information System.(GIS) | program officers trained on mapping of snakes of Medical Importance and other venomous snakes using the GIS system | Number of program officers trained | 5 | Training programes/ schedules, training certificates | [13 empty] | 250000 | bar: 2024/25 Aug
|  | Procure voice recorders, digital camera, data collection tablets, laptops, GIS communication devices, power banks, high definition binoculars, printer, N ViVo analysis software, tents (10 units) | Items procured | Number of items procured | 73 | Invoices, DOF, Receipts | [13 empty] | 4843716 | bar: 2024/25 Aug
|  | Conduct a 5 day workshop for the training of data collectors on snakebite community-based survey methodologies in 10 counties (Kilifi, Marsabit, Wajir, Makueni, Samburu) | Data collectors trained on community-based survey methodologies | number of data collectors trained per county | 5 | Training certificates | [13 empty] | 12900000 | bar: 2024/25 Aug
|  | Survey 5 counties to map snakebite incidences (Procure subsistence allowance for 10 county data collectors, transport and DSA for 10 public officers for 3 weeks per county) | counties surveyed for venomous snake identification and GIS mapping | Number of counties surveyed, Species of snakes of medical importance and other venomous snakes identified, Number of county geographical maps developed | 5 | Vehicle work tickets, county approval letters, complete Snake species data sheets, County geographical maps | [13 empty] | 20797000 | bar: 2024/25 Aug to 2024/25 Nov; 2024/25 Jan to 2024/25 Jun
| Integrate Snakebite Envenoming mapping with other NTD programs | Train healthcare workers and community healthcare promoters on protocols in integrating Snakebite Envenoming mapping with other NTD programs in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with other NTD programs | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 1835000 | bar: 2024/25 Feb to 2024/25 Apr
|  | Conduct surveys to integrate Snakebite Envenoming mapping with other NTD programs in 5 counties. (procure transport and DSA for 10 public officers for 5 days per county ) | 10 counties surveyed for integration of snakebite envenoming mapping with other NTD programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 4925000 | bar: 2024/25 Feb to 2024/25 Apr
|  | Develop a user friendly community based reporting tool to report snakebite incidences and deaths across 8 counties | Tool for reporting community-based snakebite incidences and deaths developed | Number of reporting tools developed | 1 | reporting tool populated across 8 counties | [13 empty] | 300000
|  | Conduct a validation survey to assess and validate the reach and impact of surveys to integrate Snakebite Envenoming mapping with other NTD in 5 counties (procure transport and DSA for 10 public officers for 5 days per county) | validation surveys conducted | Number of counties where validation surveys were conducted | 5 | Validation report, Vehicle work tickets | [13 empty] | 0
|  | Disseminattion of survey findings to 5 counties (procure transport and DSA for 10 public officers for 12 days, 2 days per county- total 10 counties ) | Dissemination conducted in counties where integration of snakebite envenoming mapping with other NTD programs was conducted | Number of sub counties where dissemination was conducted | 5 | Report | [13 empty] | 0
| Integrate Snakebite mapping with the Kenya Livestock MasterPlan (KLMP) | Train livestock ward officers and community healthcare promoters on protocols in integrating Snakebite integrating snakebite mapping with the KLMP in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with the Livestock program | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 1445000 | bar: 2024/25 Sep
|  | Survey 5 counties to integrate snakebite mapping with the KLMP in 5 counties (procure transport and DSA for 5 public officers for 10 days per county ) | 5 counties surveyed for integration of snakebite envenoming mapping with other NTDs, Malaria and Livestock programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 9000000 | bar: 2024/25 Sep to 2024/25 Nov
|  | Conduct public awareness campaigns on snake identification, snakebite first aid and prevention and control measures in 5 counties | awareness campaigns to educate communities on snakebite first aidnd prevention and control measures held | Number of awareness campaigns held | 5 | Meeting notices, Photos | [13 empty] | 4481000 | bar: 2024/25 Dec to 2024/25 Feb
|  | Engage Social media, website & other digital platforms to create awareness on snake identification, snakebite first aid and prevention and control measures | Social media, website & other digital platforms engaged | Number of Social media, website & other digital platforms Engaged | 10 | Active Social Media Handles, Website | [13 empty] | 500000 | bar: 2024/25 Dec to 2024/25 Feb
|  | Conduct five school-based campaigns in each of the 10 counties to raise awareness among children on snake identification, first aid measures, and snakebite prevention and control. | school based campaigns to raise awareness on snake identification, first aid measures and prevention and control of snakebite conducted (educational games, puppetries) | Number of school based campaigns conducted | 50 | mpaign reports, attendance records, photographs, feedback forms | [13 empty] | 5425000 | bar: 2024/25 Dec to 2024/25 Feb
|  | Disseminate survey findings to 10 Counties (Kitui, Turkana, Lamu, Kwale, Baringo, Samburu) (procure transport and DSA for 15 public officers for 5 days) | Dissemination conducted in counties where integration of snakebite envenoming mapping with KLMP programs was conducted | Number of sub counties where dissemination was conducted |  | Report | [13 empty] | 0
|  | Procure projector, flipcharts, rollup banners, tear drops | Items procured | number of items procured | 30 | Invoices, receipts | [13 empty] | 0
| Subtotal | [18 empty] | 66701716
Strengthen the Human Resource for snakebite management and antivenom production | Human Resource and personnel | [18 empty] | 10620000
| Train health care workers on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures | Conduct a county level Trainer of Trainer (ToT) trainings on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures to capacity build across different health care carders in 5 counties. Procure training venue, provide daily subsistence allowance (DSA) for 5 officers, and lunch allowance for 20 healthcare workers per county, for a duration of 5 days per county | County ToTs trained on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measure | Number of counties trained | 5 | County approvals, Training Reports, training certificates, attendance sheets | [13 empty] | 12150000 | bar: 2024/25 Mar to 2024/25 May
|  | Conduct a Kenya Health Reporting System (KHIS) training workshop to county and subcounty Health Records Information Officers (HRIOs) to ensure complete accurate and timely reporting of snakebite and antivenom utilization data in 5 counties. Procure conference venue, transport, DSA for 5 officers, allowance for 20 (HRIOs) | county and subcounty HRIOs trained on snakebite reporting in the KHIS | Number of counties trained | 5 | Training reports | [13 empty] | 6905000
| Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures | organise a 5 day workshop to develop, update and improve CHP training modules Information, Education and Communication (IEC) materials on snakebite awareness, first aid measures and prevention and control of snakebite (secure workshop venue, transport and DSA for 15 officers) | CHP training modules, IEC materials developed (posters, pullup banners, leaflets, T-shirts, lesos, Caps, brochures, pamplets) | Number of IEC materials developed, Number of training modules imptroved | 1 | workshop report, attendance list, IEC materials and training mannuals | [13 empty] | 3035000
|  | Launch CHP training programs in 5 counties. procure workshop venue, transportation and DSA for 5 officers for 5 days per county. | County CHP training programes launched | Number of CHP Training programs launched | 5 | Attendance sheets, county approval letters, invitation letters, photos | [13 empty] | 7937000 | bar: 2024/25 July to 2024/25 Sep
|  | Train CHPs on snake species identification, snakebite diagnosis, first aid, prevention and control measures. (Procure IEC tools to populate amongst CHPs, procure workshop venue, transportation and DSA for 5 officers for 5 days per county) | CHPs trained on snakebite diagnosis, treatment, management and rehabilitation | Number of counties where CHPs were trained | 5 | Training reports, training certificates | [13 empty] | 6260000 | bar: 2024/25 July to 2024/25 Oct
|  | Implement Motorcycle Snakebite Emergency Response System (SERS) for Community Health Promoters (CHPs) to efficiently respond to snakebite incidents within the community. Procure fuel and maintenance for 6 motorcycle ambulances in 6 counties. | motorcycle ambulances fuel and maintenance service procured | Number of maintenance services per county | 4 | fuel invoices, receipts | [13 empty] | 2130000 | bar: 2024/25 July to 2024/25 Aug
Subtotal | [19 empty] | 49037000
Grand total | [19 empty] | 115738716

## Itemized 1ywp
Results Areas | Main Activities | Sub Activities | Expected Outputs | Performance Indicators | Target | Means of verification |  | 2024/25 | [11 empty] | Estimated Cost | Approved Budget (Rec & Dev) |  | Off-budget resources |  | Funding Gap
[7 empty] | GOK | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | GOK | Source of funding | Amount | Source of funding
Mapping of snakes of medical importance and snakebite Hotspots | Identify and map Snakes of Medical Importance and other venomous snakes, map intra and intercounty snakebite hotspots in endemic counties | Train 5 program officers on mapping of snakes of Medical Importance and other venomous snakes using the Geographic Information System.(GIS) | program officers trained on mapping of snakes of Medical Importance and other venomous snakes using the GIS system | Number of program officers trained | 5 | Training programes/ schedules, training certificates | [13 empty] | 250000 | 250000 | 250000
|  | Procure voice recorders, digital camera, data collection tablets, laptops, GIS communication devices, power banks, high definition binoculars, printer, N ViVo analysis software, tents (10 units) | Items procured | Number of items procured | 73 | Invoices, DOF, Receipts | [13 empty] | 4843716 | 4843716 | 4843716
|  | Conduct a 5 day workshop for the training of data collectors on snakebite community-based survey methodologies in 5 counties (Kilifi, Marsabit, Wajir, Makueni, Samburu) | Data collectors trained on community-based survey methodologies | number of data collectors trained per county | 5 | Training certificates | [13 empty] | 12900000 | 2580000 | 5160000
|  | Survey 5 counties to map snakebite incidences (Procure subsistence allowance for 10 county data collectors, transport and DSA for 10 public officers for 3 weeks per county) | counties surveyed for venomous snake identification and GIS mapping | Number of counties surveyed, Species of snakes of medical importance and other venomous snakes identified, Number of county geographical maps developed | 5 | Vehicle work tickets, county approval letters, complete Snake species data sheets, County geographical maps | [13 empty] | 20797000 | 4159400 | 8318800
| Integrate Snakebite Envenoming mapping with other NTD programs | Train healthcare workers and community healthcare promoters on protocols in integrating Snakebite Envenoming mapping with other NTD programs in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with other NTD programs | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 1835000 | 367000 | 734000
|  | Conduct surveys to integrate Snakebite Envenoming mapping with other NTD programs in 5 counties. (procure transport and DSA for 10 public officers for 5 days per county ) | 10 counties surveyed for integration of snakebite envenoming mapping with other NTD programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 4925000 | 985000 | 1970000
|  | Develop a user friendly community based reporting tool to report snakebite incidences and deaths across 5 counties | Tool for reporting community-based snakebite incidences and deaths developed | Number of reporting tools developed | 1 | reporting tool populated across 8 counties | [13 empty] | 300000 | 0 | 0
|  | Conduct a validation survey to assess and validate the reach and impact of surveys to integrate Snakebite Envenoming mapping with other NTD in 5 counties (procure transport and DSA for 10 public officers for 5 days per county) | validation surveys conducted | Number of counties where validation surveys were conducted | 5 | Validation report, Vehicle work tickets | [13 empty] | 0 | 0 | 0
|  | Disseminattion of survey findings to 5 counties (procure transport and DSA for 10 public officers for 12 days, 2 days per county- total 10 counties ) | Dissemination conducted in counties where integration of snakebite envenoming mapping with other NTD programs was conducted | Number of sub counties where dissemination was conducted | 5 | Report | [13 empty] | 0 | 0 | 0
| Integrate Snakebite mapping with the Kenya Livestock MasterPlan (KLMP) | Train livestock ward officers and community healthcare promoters on protocols in integrating Snakebite integrating snakebite mapping with the KLMP in 5 counties | healthcare workers and community healthcare promoters in 5 counties trained on protocols in integrating Snakebite Envenoming mapping with the Livestock program | number of counties trained | 5 | training schedules, attendance sheets, photo evidence | [13 empty] | 1445000 | 289000 | 578000
|  | Survey 5 counties to integrate snakebite mapping with the KLMP in 5 counties (procure transport and DSA for 5 public officers for 10 days per county ) | 5 counties surveyed for integration of snakebite envenoming mapping with other NTDs, Malaria and Livestock programs | Number of counties surveyed | 5 | Maps of surveyed counties, Vehicle work tickets, county approval letters | [13 empty] | 9000000 | 1800000 | 3600000
|  | Conduct public awareness campaigns on snake identification, snakebite first aid and prevention and control measures in 5 counties | awareness campaigns to educate communities on snakebite first aidnd prevention and control measures held | Number of awareness campaigns held | 5 | Meeting notices, Photos | [13 empty] | 4481000 | 896200 | 1792400
|  | Engage Social media, website & other digital platforms to create awareness on snake identification, snakebite first aid and prevention and control measures | Social media, website & other digital platforms engaged | Number of Social media, website & other digital platforms Engaged | 10 | Active Social Media Handles, Website | [13 empty] | 500000 | 0 | 500000
|  | Conduct five school-based campaigns in each of the 10 counties to raise awareness among children on snake identification, first aid measures, and snakebite prevention and control. | school based campaigns to raise awareness on snake identification, first aid measures and prevention and control of snakebite conducted (educational games, puppetries) | Number of school based campaigns conducted | 50 | mpaign reports, attendance records, photographs, feedback forms | [13 empty] | 5425000 | 1085000 | 2170000
|  | Disseminate survey findings to 10 Counties (Kitui, Turkana, Lamu, Kwale, Baringo, Samburu) (procure transport and DSA for 15 public officers for 5 days) | Dissemination conducted in counties where integration of snakebite envenoming mapping with KLMP programs was conducted | Number of sub counties where dissemination was conducted |  | Report | [13 empty] | 0 | 0 | 0
| Subtotal | [18 empty] | 66701716 |  | 29916916 | 36784800
Strengthen the Human Resource for snakebite management and antivenom production | Human Resource and personnel | [18 empty] | 10620000 | 885000 | 2655000
| Train health care workers on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures | Conduct a county level Trainer of Trainer (ToT) trainings on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measures to capacity build across different health care carders in 5 counties. Procure training venue, provide daily subsistence allowance (DSA) for 5 officers, and lunch allowance for 20 healthcare workers per county, for a duration of 5 days per county | County ToTs trained on snakebite diagnosis, management, antivenom administration and snakebite prevention and control measure | Number of counties trained | 5 | County approvals, Training Reports, training certificates, attendance sheets | [13 empty] | 12150000 | 2430000 | 4860000
|  | Conduct a Kenya Health Reporting System (KHIS) training workshop to county and subcounty Health Records Information Officers (HRIOs) to ensure complete accurate and timely reporting of snakebite and antivenom utilization data in 5 counties. Procure conference venue, transport, DSA for 5 officers, allowance for 20 (HRIOs) | county and subcounty HRIOs trained on snakebite reporting in the KHIS | Number of counties trained | 5 | Training reports | [13 empty] | 6905000 | 1381000 | 2762000
| Train Community Health Promoters (CHPs) on snake species identification, snakebite diagnosis, first aid, prevention and control measures | organise a 5 day workshop to develop, update and improve CHP training modules Information, Education and Communication (IEC) materials on snakebite awareness, first aid measures and prevention and control of snakebite (secure workshop venue, transport and DSA for 15 officers) | CHP training modules, IEC materials developed (posters, pullup banners, leaflets, T-shirts, lesos, Caps, brochures, pamplets) | Number of IEC materials developed, Number of training modules imptroved | 1 | workshop report, attendance list, IEC materials and training mannuals | [13 empty] | 3035000 | 607000 | 1214000
|  | Launch CHP training programs in 5 counties. procure workshop venue, transportation and DSA for 5 officers for 5 days per county. | County CHP training programes launched | Number of CHP Training programs launched | 5 | Attendance sheets, county approval letters, invitation letters, photos | [13 empty] | 7937000 | 1587400 | 3174800
|  | Train CHPs on snake species identification, snakebite diagnosis, first aid, prevention and control measures. (Procure IEC tools to populate amongst CHPs, procure workshop venue, transportation and DSA for 5 officers for 5 days per county) | CHPs trained on snakebite diagnosis, treatment, management and rehabilitation | Number of counties where CHPs were trained | 5 | Training reports, training certificates | [13 empty] | 6260000 | 1252000 | 2504000
|  | Implement Motorcycle Snakebite Emergency Response System (SERS) for Community Health Promoters (CHPs) to efficiently respond to snakebite incidents within the community. Procure fuel and maintenance for 6 motorcycle ambulances in 6 counties. | motorcycle ambulances fuel and maintenance service procured | Number of maintenance services per county | 4 | fuel invoices, receipts | [13 empty] | 2130000 | 0 | 0 |  | 0
Subtotal | [19 empty] | 49037000 | 8142400 | 17169800 | 31867200
Grand total | [19 empty] | 115738716

## 1Y-Budget
Sub activity 1
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Survey materials
Per diem | 14000 | 10 | 21 | 5 | 14700000 | Item | No. | QTY | Unit cost | Total
conference | 0 | 0 | 0 | 0 | 0 | Voice Recorder | No. | 10 | 20000 | 200000
fuel cost | 200 | 85 | 21 | 5 | 1785000 | External Hards Disk 3TB | No. | 5 | 26000 | 130000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 | Digital Cameras | No. | 1 | 490000 | 490000
Air ticket | 28000 | 2 | 1 | 2 | 112000 | laptops | nos | 2 | 280000 | 560000
Subsistence allowance | 2500 | 10 | 21 | 5 | 2625000 | Tablets | nos | 20 | 90000 | 1800000
Training allowance | 0 | 0 | 0 | 0 | 0 | Power Bank | nos | 20 | 10000 | 200000
Security | 5000 | 5 | 21 | 3 | 1575000 | GPS Communicaton Devices | nos | 10 | 50000 | 500000
[5 empty] | 0 | Tents |  | 10 | 40000 | 400000
training materials | 0 | 0 | 0 | 0 | 0 | Printer | nos | 1 | 50000 | 50000
Total | 0 | 0 | 0 | 0 | 20797000 | computer software | nos | 2 | 131858 | 263716
[6 empty] | High Defination Binoculars | No. | 10 | 25000 | 250000
4843716
Training materials
Sub activity 2 | [5 empty] | Flip chart | no | 20 | 2000 | 40000
ITEM | UNIT COST | QTY | Days | counties | TOTAL | Flip chart stand | no | 5 | 10000 | 50000
Per diem | 14000 | 20 | 3 | 10 | 8400000 | Roller Banners |  | 5 | 15000 | 75000
[6 empty] | Projector |  | 1 | 280000 | 280000
conference | 5000 | 20 | 3 | 10 | 3000000 | Tear Drops |  | 20 | 15000 | 300000
fuel cost | 200 | 85 | 3 | 10 | 510000 | printing | no | 1000 | 1000 | 1000000
vehicle maintenance | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1745000
Air ticket | 28000 | 3 | 1 | 2 | 168000
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0
Security | 0 | 0 | 0 | 0 | 0
training materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
12078000
Sub activity 3
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 10 | 7000000
conference | 5000 | 10 | 5 | 10 | 2500000
fuel cost | 200 | 85 | 5 | 10 | 850000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2500 | 10 | 5 | 10 | 1250000
Training allowance | 2000 | 2 | 30 | 10 | 1200000
training materials | 10000 | 1 | 1 | 10 | 100000
Media | 0 | 0 | 0 | 0 | 0
12900000
Sub activity 4
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 21 | 10 | 29400000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 21 | 10 | 3570000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2500 | 10 | 21 | 10 | 5250000
Training allowance | 0 | 0 | 0 | 0 | 0
training materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
38720000
Sub activity 5
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 1 | 5 | 700000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 1 | 5 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 5000 | 30 | 1 | 5 | 750000
Training allowance | 2000 | 5 | 6 | 5 | 300000
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1835000
Sub activity 6
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 5 | 3500000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000
vehicle maintenance | 200000 | 1 | 1 | 5 | 1000000
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
4925000
Sub activity 7
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 1 | 5 | 700000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 1 | 5 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 30 | 1 | 5 | 300000
Training allowance | 2000 | 5 | 6 | 6 | 360000
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
1445000
Sub activity 8
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 10 | 5 | 7000000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 10 | 5 | 850000
vehicle maintenance | 0 | 0 | 0 | 0 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 100000 | 1 | 1 | 5 | 500000
Media | 0 | 0 | 0 | 0 | 150000
9000000
Sub activity 9
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 5 | 3500000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 28000 | 2 | 1 | 1 | 56000
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 500000 | 1 | 1 | 1 | 500000
Media | 0 | 1 | 1 | 0 | 0
4481000
Sub activity 10
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 5 | 3500000
conference | 0 | 0 | 0 | 0 | 0
fuel cost | 200 | 85 | 5 | 5 | 425000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 200000 | 1 | 1 | 5 | 1000000
Media | 0 | 0 | 0 | 0 | 0
5425000
Sub activity 11
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 3 | 5 | 2100000
conference | 5000 | 35 | 3 | 5 | 2625000
Training allowance | 2000 | 5 | 30 | 5 | 1500000
Subsistence allowance | 5000 | 20 | 5 | 5 | 2500000
fuel cost | 200 | 85 | 5 | 5 | 425000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 500000 | 1 | 1 | 5 | 2500000
Media | 0 | 0 | 0 | 0 | 0
12150000
Sub activity 12
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 5 | 3500000
conference | 0 | 0 | 0 | 0 | 0
Training allowance | 2000 | 5 | 30 | 5 | 1500000
Subsistence allowance | 2000 | 20 | 2 | 5 | 400000
fuel cost | 200 | 85 | 5 | 5 | 425000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 28000 | 4 | 1 | 1 | 112000
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 150000 | 1 | 1 | 10 | 1500000
7937000
Sub activity 13
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 0 | 0 | 0 | 0 | 0
conference | 5000 | 35 | 5 | 6 | 5250000
fuel cost | 200 | 85 | 5 | 6 | 510000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Subsistance allowance (CHPs) | 2000 | 20 | 2 | 5 | 400000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 100000 | 1 | 1 | 1 | 100000
Media | 0 | 0 | 0 | 0 | 0
6260000
Sub activity 15
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 0 | 0 | 0 | 0 | 0
conference | 0 | 0 | 0 | 0 | 0
Training allowance | 0 | 0 | 0 | 0 | 0
Subsistence allowance | 2000 | 6 | 3 | 5 | 180000
fuel cost | 200 | 5 | 90 | 5 | 450000
vehicle maintenance | 100000 | 1 | 3 | 5 | 1500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
2130000
Sub activity 22
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 3 | 5 | 2100000
conference | 5000 | 25 | 3 | 5 | 1875000
Training allowance | 2000 | 10 | 18 | 5 | 1800000
Subsistence allowance | 5000 | 5 | 3 | 5 | 375000
fuel cost | 200 | 85 | 3 | 5 | 255000
vehicle maintenance | 500000 | 1 | 1 | 1 | 500000
Air ticket | 0 | 0 | 0 | 0 | 0
Data collection materials | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
6905000
Sub activity 12
ITEM | UNIT COST | QTY | Days | counties | TOTAL
Per diem | 14000 | 10 | 5 | 1 | 700000
conference | 5000 | 10 | 5 | 1 | 250000
fuel cost | 200 | 85 | 5 | 1 | 85000
vehicle maintenance | 0 | 0 | 0 | 0 | 0
Air ticket | 0 | 0 | 0 | 0 | 0
Printing/ Branding | 2000000 | 1 | 1 | 1 | 2000000
Data collection materials | 0 | 0 | 0 | 0 | 0
Media | 0 | 0 | 0 | 0 | 0
3035000

## ksric budget
| ITEM DESCRIPTION | UNIT | QTY | ESTIMATED UNIT PRICE | TOTAL ESTIMATED PRICE | USER DEPT | PROCUREMENT METHOD | SOURCE OF FUNDS | YOUTH | WOMEN | PWD | OPEN | QUARTER REQUIRED
[13 empty] | 1ST |  | 2ND |  | 3RD |  | 4TH
[13 empty] | QTY | KSH | QTY | KSH | QTY | KSH | QTY | KSH
1.Licenses and permits
1 | NACOSTI research license |  | 1 | 10000 | 10000 | KSRIC | Direct Procurement | GOK |  |  |  | √ | [6 empty] | 1 | 10000
2 | WRTI research permit |  | 1 | 10000 | 10000 | KSRIC | Direct Procurement | GOK |  |  |  | √ | [6 empty] | 1 | 10000
3 | NEMA access permit |  | 1 | 50000 | 50000 | KSRIC | Direct Procurement | GOK |  |  |  | √ | [6 empty] | 1 | 50000
4 | KWS research permit |  | 1 | 10000 | 10000 | KSRIC | Direct Procurement | GOK
5 | ISO Certificate |  | 1 |  |  | KSRIC | Direct Procurement | GOK |  |  |  | √
2.Medical and veterinary supplies consumables | [19 empty] | 0
2 | SAIMR monovalent antivenom(Boomslang), EchiTab-Plus monovalent antivenom , Saimr polyvalent | PKT | 50 | 72000 | 3600000 |  | Direct Procurement | GOK |  |  |  | √ | [6 empty] | 120 | 3600000
4 | 30 gauge insulin/trajector syringes | box | 20 | 3600 | 72000 |  | RFQ | GOK | [10 empty] | 20 | 72000
5 | cotton wool | roll | 10 | 600 | 6000 |  | RFQ | GOK | [10 empty] | 10 | 6000
6 | dissecting kit | no | 3 | 30000 | 90000 |  | RFQ | GOK | [10 empty] | 3 | 90000
7 | formaldehyde | 2.5litres | 4 | 3600 | 14400 |  | RFQ | GOK | [10 empty] | 4 | 14400
8 | surgical spirit | 5litres | 10 | 2600 | 26000 |  | RFQ | GOK | [10 empty] | 4 | 26000
9 | Nitrile gloves-Large | Pkt | 30 | 1600 | 48000 |  | RFQ | GOK | [10 empty] | 30 | 48000
10 | Nitrile gloves medium | Pkt | 30 | 1500 | 45000 |  | RFQ | GOK | [10 empty] | 30 | 45000
11 | Nitrile gloves small | Pkt | 30 | 1600 | 48000 |  | RFQ | GOK | [10 empty] | 30 | 48000
12 | Bio hazards bags | Pkt | 4 | 8500 | 34000 |  | RFQ | GOK | [10 empty] | 4 | 34000
13 | Disposable bags | Pkt | 4 | 5000 | 20000 |  | RFQ | GOK | [10 empty] | 4 | 20000
14 | Dustbins | No. | 10 | 9200 | 92000 |  | RFQ | GOK | [10 empty] | 10 | 92000
15 | Oxytetracycline | 100ml | 20
16 | Penstrep | 100ml | 20
17 | Biotrin | 200g | 10
18 | Piperazin | 100g | 20
19 | Albafas 10% | 1liter | 20
20 | Hydrogen peroxide | 200ml | 10
21 | Iodine | 500ml | 10
22 | Ivermectin | 100ml | 10
23 | Jik | 5litres | 30
24 | 20ml ordinary syringe | PKT | 10
25 | 5ml Ordinary syringe | pkt | 10
0
3.Medical and veterinary supplies non consumbles | [19 empty] | 0
1 | First Aid kit | No | 2 | 25000 | 50000 | KSRIC | RFQ | GOK |  |  |  | √ | [6 empty] | 2 | 50000
2 | Eye wash and mounted station | No | 6 | 20000 | 120000 | KSRIC | RFQ | GOK |  |  |  | √ | [6 empty] | 6 | 120000
3 | Spray Bottles 500ml | No | 20 | 480 | 9600 |  | RFQ | GOK | [10 empty] | 20 | 9600
5 | Wash Bottles 500ml | NO | 20 | 1600 | 32000 |  | RFQ | GOK | [10 empty] | 20 | 32000
6 | Snake bite emergency kit | no |  |  | 0 | [14 empty] | 0
| Geotagging Machine | No. | 5 |  | 0
| Health Montering Devices | No. | 10 |  | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
4.TOOLS AND EQUIPMENT |  |  |  |  | 0 | [14 empty] | 0
0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
5. VEHICLE MAITAINANCE AND FUEL |  |  |  |  | 0 | [14 empty] | 0
1 | Diesel(fuel) for snake capture work in 15 counties | litres |  | 200 | 0 | KSRIC | RFQ | GOK |  |  |  | √ | [6 empty] | 3000 | 0
2 | Service of motor vehicles | no |  |  | 0 | KSRIC | RFQ | GOK | [11 empty] | 0
3 | fuel for snake mapping | litres | 53720 | 200 | 10744000 | KSRIC | RFQ | GOK | [10 empty] | 53720 | 10744000
4 | Vehicle maintainance | several | 1 | 3500000 | 3500000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 3500000
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
6. Uniforms and Protective gears |  |  |  |  | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
7. Laboratory supplies non consumables |  |  |  |  | 0 | [14 empty] | 0
3 | Conical Flask 25ml | No | 10 | 1400 | 14000 | KSRIC | RFQ | GOK | [10 empty] | 10 | 14000
4 | Conical Flask 50ml | No | 10 | 1500 | 15000 | KSRIC | RFQ | GOK | [10 empty] | 10 | 15000
5 | Conical Flask 100ml | No | 15 | 1600 | 24000 | KSRIC | RFQ | GOK | [10 empty] | 15 | 24000
6 | Conical Flask 250ml | No | 15 | 1850 | 27750 | KSRIC | RFQ | GOK | [10 empty] | 15 | 27750
7 | Conical Flask 500ml | No | 15 | 2100 | 31500 | KSRIC | RFQ | GOK | [10 empty] | 15 | 31500
8 | Conical Flask 1000ml | No | 20 | 2400 | 48000 | KSRIC | RFQ | GOK | [10 empty] | 20 | 48000
9 | Beakers 50ml | No | 10 | 1380 | 13800 | KSRIC | RFQ | GOK | [10 empty] | 10 | 13800
10 | Beakers100ml | No | 15 | 1480 | 22200 | KSRIC | RFQ | GOK | [10 empty] | 15 | 22200
11 | Beakers 250ml | No | 15 | 1590 | 23850 | KSRIC | RFQ | GOK | [10 empty] | 15 | 23850
12 | Beakers 500ml | No | 10 | 1700 | 17000 | KSRIC | RFQ | GOK | [10 empty] | 10 | 17000
13 | Beakers 1000ml | No | 10 | 2400 | 24000 | KSRIC | RFQ | GOK | [10 empty] | 10 | 24000
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
8.Lboratory Supplies Consumables |  |  |  |  | 0 | [14 empty] | 0
1 | Serological pipettes 5ml | pc | 700 | 50 | 35000 | KSRIC | RFQ | GOK | [10 empty] | 1000 | 35000
2 | Serological pipettes 10ml | pc | 700 | 55 | 38500 | KSRIC | RFQ | GOK | [10 empty] | 1000 | 38500
3 | Serological pipettes 25ml | pc | 700 | 60 | 42000 | KSRIC | RFQ | GOK | [10 empty] | 1000 | 42000
4 | Serological pipettes 50 ml | pc | 400 | 70 | 28000 | KSRIC | RFQ | GOK | [10 empty] | 500 | 28000
5 | Eppendorf tubes (1.5ml) | pkt | 4 | 6500 | 26000 | KSRIC | RFQ | GOK | [10 empty] | 6 | 26000
6 | 50ml Falcon Tubes | box | 2 | 35000 | 70000 | KSRIC | RFQ | GOK | [10 empty] | 3 | 70000
7 | Tips( 200ul) yellow | pkt | 15 | 2400 | 36000 | KSRIC | RFQ | GOK | [10 empty] | 20 | 36000
8 | Tips (1000ul)blue | pkt | 15 | 2800 | 42000 | KSRIC | RFQ | GOK | [10 empty] | 20 | 42000
9 | Filtered Tips( 10ul) | box | 2 | 15800 | 31600 | KSRIC | RFQ | GOK | [10 empty] | 3 | 31600
10 | Filtered Tips( 200ul) | box | 2 | 14800 | 29600 | KSRIC | RFQ | GOK | [10 empty] | 3 | 29600
11 | Filtered Tips(1000ul) | box | 2 | 15800 | 31600 | KSRIC | RFQ | GOK | [10 empty] | 3 | 31600
12 | 0.2 µm filter, Nalgene rapid flow sterile disposable filter units with PES membranes(pack of 12) | no | 2 | 78000 | 156000 | KSRIC | RFQ | GOK | [10 empty] | 4 | 156000
13 | Elisa 96 well plates (Nunc flat bottom), | Box | 3 | 38000 | 114000 | KSRIC | RFQ | GOK | [11 empty] | 114000
15 | 0.22 µm filters | Pkt | 2 | 24000 | 48000 | KSRIC | RFQ | GOK | [11 empty] | 48000
16 | sodium citrate tubes( 6ml) | pkts | 3 | 6200 | 18600 | KSRIC | RFQ | GOK | [10 empty] | 5 | 18600
9.Laboratory Chemicals, Reagents and kits |  |  |  |  | 0 | [14 empty] | 0
1 | Tris buffer | 500gm | 4 | 18900 | 75600 | KSRIC | RFQ | GOK | [10 empty] | 2 | 0
2 | Glycine |  | 2 | 6500 | 13000 | KSRIC | RFQ | GOK | [10 empty] | 2 | #VALUE!
5 | SDS Powder |  | 2 | 54600 | 109200 | KSRIC | RFQ | GOK | [10 empty] | 2
6 | Glycerol |  | 2 | 6500 | 13000 | KSRIC | RFQ | GOK | [10 empty] | 2
7 | Bromophenol blue 25g |  | 2 | 38800 | 77600 | KSRIC | RFQ | GOK | [10 empty] | 2
8 | Coomassie brilliant blue stain 25g |  | 2 | 28600 | 57200 | KSRIC | RFQ | GOK | [10 empty] | 2 | 0
9 | Acetic acid |  | 2 | 5800 | 11600 | KSRIC | RFQ | GOK | [10 empty] | 2 | 11600
10 | 10X PBS 1litre | bottles | 5 | 65500 | 327500 | KSRIC | RFQ | GOK | [10 empty] | 5 | 327500
11 | absolute ethanol | bottles | 5 | 6500 | 32500 | KSRIC | RFQ | GOK | [10 empty] | 5
12 | absolute methanol | bottles | 5 | 4800 | 24000 | KSRIC | RFQ | GOK | [10 empty] | 5
13 | sodium phosphate monobasic | 500gm | 2 | 24800 | 49600 | KSRIC | RFQ | GOK | [10 empty] | 2
14 | sodium phosphate dibasic | 500gm | 2 | 26800 | 53600 | KSRIC | RFQ | GOK | [10 empty] | 2
15 | sodium phosphate tribasic | 500gm | 2 | 26800 | 53600 | KSRIC | RFQ | GOK | [10 empty] | 2
16 | PH Meter standards 4.0 (1L) | bottles | 5 | 3500 | 17500 | KSRIC | RFQ | GOK | [10 empty] | 20
17 | PH Meter standards 7.01(1L) | bottles | 5 | 4500 | 22500 | KSRIC | RFQ | GOK | [10 empty] | 20
18 | PH Meter standards storage(1L) | bottles | 5 | 4500 | 22500 | KSRIC | RFQ | GOK | [10 empty] | 20
19 | Tween 20 100ml | bottles | 10 | 18200 | 182000 | KSRIC | RFQ | GOK
20 | Soy Milk | Pkts | 2 | 150 | 300 | KSRIC | RFQ | GOK
21 | Horseradish Peroxidase-Conjugated Rabbit anti-horse 1gG secondary antibody | vials | 2 | 48000 | 96000 | KSRIC | RFQ | GOK
22 | Coating Buffer Tablets | bottles | 2 | 50580 | 101160 | KSRIC | RFQ | GOK
23 | Citric Acid | 500gm | 2 | 22200 | 44400 | KSRIC | RFQ | GOK
24 | ABTZ Tablets |  | 2 | 9000 | 18000 | KSRIC | RFQ | GOK
26 | Gelatin, (500gm) | bottles | 3 | 71500 | 214500 | KSRIC | RFQ | GOK | [10 empty] | 3
27 | Triton X-100 | litres | 3 | 26000 | 78000 | KSRIC | RFQ | GOK | [10 empty] | 3
28 | Azocasein 5gm | bottles | 3 | 62200 | 186600 | KSRIC | RFQ | GOK | [10 empty] | 3
29 | Trichloroacetic acid( 500ml) | bottles | 4 | 16500 | 66000 | KSRIC | RFQ | GOK | [10 empty] | 5
31 | Agarose 500g | bottles | 12 | 65000 | 780000 | KSRIC | RFQ | GOK | [10 empty] | 10
32 | Human fibronogen ( 100mg) | sachets | 3 | 43800 | 131400 | KSRIC | RFQ | GOK | [10 empty] | 3
| Mass spectrometry (service) |  | 3 | 2000000 | 6000000 | KSRIC | RFQ | GOK
| CaCL2 (500grams) | bottle | 5 | 2500 | 12500 | KSRIC | RFQ | GOK | [10 empty] | 5
| NaCL (500g) | bottle | 5 | 1500 | 7500 | KSRIC | RFQ | GOK | [10 empty] | 5
| NaOH (500g) | bottle | 5 | 1100 | 5500 | KSRIC | RFQ | GOK | [10 empty] | 5
| Purified protease from bovine plasma |  | 2 | 33250 | 66500 | KSRIC | RFQ | GOK
| DNA from calf thymus | bottle | 1 | 107100 | 107100 | KSRIC | RFQ | GOK | [10 empty] | 2
| Dnase from bovine pancreas |  | 2 | 44050 | 88100
| One Taq 2X master mix | kit | 3 | 18000 | 54000 | KSRIC | RFQ | GOK | [10 empty] | 2
| Phusion Green hot star 11 high fidelity PCR master mix | kit | 3 | 78600 | 235800 | KSRIC | RFQ | GOK | [10 empty] | 2
| Molecular grade water (500ml) | bottle | 2 | 12000 | 24000
| DNA sequencing | sample | 150 | 1700 | 255000 | KSRIC | RFQ | GOK | [10 empty] | 2
| DNA extraction kit | kit | 2 | 55000 | 110000 | KSRIC | RFQ | GOK | [10 empty] | 2
| TAE X10 (5 liter) | Bottle | 1 | 50000 | 50000 | KSRIC | RFQ | GOK
| DNA purification kit (EXOSAP) | kit | 3 | 35000 | 105000 | KSRIC | RFQ | GOK
| Big dye sequencing kit | kit | 2 | 90000 | 180000 | KSRIC | RFQ | GOK
| Dried skimmed milk (500grams) | tin | 3 | 600 | 1800 | KSRIC | RFQ | GOK
| 0.45 μm nitrocellulose membrane |  | 2 | 47600 | 95200 | KSRIC | RFQ | GOK
| Diaminobenzidine (DAB) substrate | bottles | 1 | 59500 | 59500 | KSRIC | RFQ | GOK
| Caprylic acid (500grams) | bottles | 3 | 8000 | 24000 | KSRIC | RFQ | GOK
| IgG purification kit | kit | 3 | 77150 | 231450 | KSRIC | RFQ | GOK
| Dialysis cassettes | Pkts | 3 | 36720 | 110160 | KSRIC | RFQ | GOK
| Concetration devices | Pkts | 3 |  |  | KSRIC | RFQ | GOK
| pepsin | kg | 2 | 23800 | 47600 | KSRIC | RFQ | GOK | [10 empty] | 1
| ammonium sulfate (500 grams) | bottle | 3 | 2500 | 7500 | KSRIC | RFQ | GOK | [10 empty] | 1
| Prestained protein ladder (100-250 kDa (2 vials) | Pkts | 2 | 48000 | 96000 | KSRIC | RFQ | GOK
| Unstained protein ladder (100-250 kDa (2vials) | Pkts | 2 | 25000 | 50000 | KSRIC | RFQ | GOK
| β-mercaptoethanol | bottles | 3 | 8400 | 25200 | KSRIC | RFQ | GOK
| 100bp DNA ladder | vials | 2 | 24000 | 48000 | KSRIC | RFQ | GOK
| 1kb DNA ladder | vials | 2 | 37000 | 74000 | KSRIC | RFQ | GOK
| DNA loading dye | vials | 2 | 15000 | 30000 | KSRIC | RFQ | GOK
| Acrylamide | bottles | 2 | 22950 | 45900 | KSRIC | RFQ | GOK
| Bis-acrylamide | bottles | 2 | 4590 | 9180 | KSRIC | RFQ | GOK
| Ammonium persulfate (500g) | bottles | 3 | 2500 | 7500 | KSRIC | RFQ | GOK
| TEMED | bottles | 2 | 17850 | 35700 | KSRIC | RFQ | GOK
| Purified horse IgG (1mg/ml) | bottles | 2 | 22950 | 45900 | KSRIC | RFQ | GOK
| Bovine serum albumin (1mg/ml) | bottles | 2 | 15000 | 30000 | KSRIC | RFQ | GOK
| Yeast Extract (250g) | bottle | 2 | 22000 | 44000 | KSRIC | RFQ | GOK
| D-Sorbitol (500g) | bottle | 2 | 6409 | 12818 | KSRIC | RFQ | GOK
| Electroporation cuvettes | Pkts | 2 | 31280 | 62560 | KSRIC | RFQ | GOK
| SR-CAA yeast growth media (500g) | bottle | 2 | 22763 | 45526 | KSRIC | RFQ | GOK
| D Raffinose Pentahydrate powder (100g) | bottle | 2 | 44586 | 89172 | KSRIC | RFQ | GOK
| Bacto Casamino acids (500g) | bottle | 1 | 137683 | 137683 | KSRIC | RFQ | GOK
| Dextrose (1kg) | bottle | 1 | 33315 | 33315 | KSRIC | RFQ | GOK
| Galactose (1kg) | bottle | 1 | 172601 | 172601 | KSRIC | RFQ | GOK
| anti-llama antibody | vials | 2 | 34500 | 69000 | KSRIC | RFQ | GOK
| Streptavidin-488 (SA-PE), Alexa fluor 488 dye | vials | 1 | 119952 | 119952 | KSRIC | RFQ | GOK
| KCL (500g) | bottles | 2 | 2500 | 5000 | KSRIC | RFQ | GOK
10.Laboratory tools and equipments |  |  |  |  | 0 | [14 empty] | 0
| STANDS |  |  |  | 0 | [14 empty] | 0
0
| Refrigerator (-20° C, +4 °C) | No | 1 | 170000 | 170000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 170000
| Biosafety cabinet Class II B2 | No | 2 | 1800000 | 3600000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 3600000
| Analytical weighing balance | No | 1 | 250000 | 250000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 250000
| Gel electrophoresis system (casting plates, electrode assembly, companion running module, buffer tank and lid, casting stand and frames, Power Pac | No | 1 | 650000 | 650000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 650000
| Microplate Spectophotometer (Preferred wavelength range 200 -999 nm) | No | 1 | 4417595 | 4417595 | KSRIC | Open tender | GOK | [10 empty] | 1 | 4417595
| Illumina Hiseq 2500 | No | 1 | 8920670 | 8920670 | KSRIC | Open tender | GOK | [10 empty] | 1 | 8920670
| Automatic pipet aid | No | 3 | 25000 | 75000 | KSRIC | RFQ | GOK | [10 empty] | 3 | 75000
| Negative 80 freezer | No | 2 | 3900000 | 7800000 | KSRIC | open tender | GOK | [10 empty] | 2 | 7800000
| Columns ( Sephadex G25 desalting column, RP-HPLC, Hydrophobic interactions columns) | No | 1 | 419830 | 419830 | KSRIC | RFQ | GOK | [10 empty] | 1 | 419830
| Pipettes P10 | No | 2 | 55000 | 110000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 110000
| Pipettes P20 | No | 2 | 55000 | 110000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 110000
| Pipettes P200 | No | 2 | 55000 | 110000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 110000
| Pipettes P1000) | No | 2 | 55000 | 110000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 110000
| 12 Multichannel pipettes 30 - 300 µl | No | 2 | 178000 | 356000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 356000
| 12 Multichannel Pipettes 10 - 100 µl | No | 2 | 178000 | 356000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 356000
| ELISA washer and dispenser | no | 1 | 4900000 | 4900000 | KSRIC | open tender | GOK | [10 empty] | 1 | 4900000
| Transblot transfer system | No | 1 | 965126 | 965126 | KSRIC | RFQ | GOK | [10 empty] | 1 | 965126
| Protein A/G affinity chromatography columns (HiTrap Protein A HP 5ml and HiTrap Protein G HP 5ml) | No | 5 | 300000 | 1500000 | KSRIC | RFQ | GOK | [10 empty] | 5 | 1500000
Ultra-Performance Liquid Chromatography (1290 Infinity II, Agilent Technologies)
| Autoclave | No | 1 |  | 0 | KSRIC | RFQ | GOK | [10 empty] | 1 | 0
| Liquid nitrogen tank | 50ml | 1 | 152000 | 152000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 152000
| Medium centrifuge |  | 1 | 50157 | 50157 | KSRIC | RFQ | GOK | [10 empty] | 1 | 50157
| CO2 Incubator |  | 1
| plus 5 and minus 20 refrigerator double door 635 litres |  | 1 | 280000 | 280000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 280000
| lab stools |  | 15 | 75000 | 1125000 | KSRIC | RFQ | GOK | [10 empty] | 15 | 1125000
| Vortexer |  | 2 | 45000 | 90000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 90000
| Eye wash and mounted stations |  | 5 | 50000 | 250000 | KSRIC | RFQ | GOK | [10 empty] | 5 | 250000
| Class II Biosafet cabinet |  | 1 | 1800000 | 1800000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 1800000
| Power supply extension |  | 7 | 14000 | 98000 | KSRIC | RFQ | GOK | [10 empty] | 7 | 98000
| UPS |  | 3 | 323700 | 971100 | KSRIC | RFQ | GOK | [10 empty] | 3 | 971100
| UPS Invertor |  | 1
| Water distiller system |  | 1 | 3000000 | 3000000 | KSRIC | RFQ | GOK | [11 empty] | 3000000
| Mini Centrifuge (PCR tubes) | No. | 1 | [16 empty] | 0
Mini vortexer
| Thermocycler | No. | 1 |  | 0 | [14 empty] | 0
| Biological microscope MSC-B5005M | no | 1 |  | 0 | [14 empty] | 0
| microscope camera BUC1D-830C( mount usb2.0 cmos) | no | 1 | [16 empty] | #VALUE!
| BD Facs Melody Cell Sorter | No | 1 | 84000000 | 84000000 | KSRIC | open tender | GOK | [11 empty] | 1500000
| Refrigerator (-20° C, +4 °C) | No. | 1 | 170000 | 170000 | KSRIC | RFQ | GOK | [11 empty] | 0
| Fume Hood | No. | 1 |  | 0
| Chest Freezer 480L | No. | 1 | 80000 | 80000 | [14 empty] | 84000000
| Analytical weighing balance | No. | 1 | 250000 | 250000
SD-CAA plates
| Autoclave Machine | No. | 1 |  | 0
11.Colony Supplies |  |  |  |  | 0 | [14 empty] | #REF!
| Trap boxes |  |  |  | 0 | [14 empty] | 0
| Water bowls/Drinkers |  |  |  | 0 | [14 empty] | 0
| Beddings |  |  |  | 0 | [14 empty] | 0
| Mice beddings | Bags | 30 | 750 | 22500 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 22500
0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
12.New snake cages |  |  |  |  | 0 | [14 empty] | 0
1 | Snake cages |  | 40 | 32000 | 1280000 | KSRIC | RFQ | GOK | [10 empty] | 40 | 1280000
2 | snake racks |  | 14 | 12000 | 168000 | KSRIC | RFQ | GOK | [10 empty] | 14 | 168000
3 | Mice Cages | No | 70 | 24000 | 1680000 | KSRIC | RFQ | GOK | [10 empty] | 70 | 1680000
4 | Water bottles | No | 100 | 1800 | 180000 | KSRIC | RFQ | GOK | [10 empty] | 100 | 180000
5 | Racks | No | 5 | 20000 | 100000 | KSRIC | RFQ | GOK | [10 empty] | 5 | 100000
0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
13.F00D FOR PRIMATES AND SMALL ANIMALS |  |  |  |  | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
1 | Mice feeds | bag | 120 | 4000 | 480000 | [14 empty] | 480000
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
14.TRAINING,WORKSHOPS AND CONFERENCES |  |  |  |  | 0 | [14 empty] | 0
1 | STAFF TRAINING | NO | 1 | 2500000 | 2500000 | [14 empty] | 2500000
2 | conference facilities | lot | 1 | 9187000 | 9187000 | [13 empty] | 1 | 9187000
3 | conference facilities | lot | 1 | 4925000 | 4925000 | [14 empty] | 4925000
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
15.AIR TICKETS EXPENSES |  |  |  |  | 0 | [14 empty] | 0
1 | Air ticket | tickets | 1 | 3500000 | 3500000 | [13 empty] | 1 | 3500000
2 | Air ticket | TICKETS | 1 | 308000 | 308000 | [13 empty] | 1 | 308000
3 | Air ticket | tickets | 1 | 1280000 | 1280000 | [14 empty] | 1280000
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
15.insurance |  |  |  |  | 0 | [14 empty] | 0
| Travel insurance | nos | 1 | 80000 | 80000 | [14 empty] | 80000
0
0
0
16. INFRASTRUCTURE | [19 empty] | 0
1 | Installation of HVAC SYSTEM |  | 1 | 1920000 | 1920000 | [13 empty] | 1 | 1920000
2 | Automatic lighting system |  | 1 | 75000 | 75000 |  | RFQ | [11 empty] | 1 | 75000
3 | Snake rooms renovation |  | 1 | 1000000 | 1000000 |  | RFQ | [11 empty] | 1 | 1000000
4 | CCTV camera installation and security system |  | 1 | 750000 | 750000 |  | RFQ | [11 empty] | 1 | 750000
5 | purchase /lease of land for animal research | no | 1 | 2200000 | 2200000 | [13 empty] | 1 | 2200000
6 | purchase of horses |  | 24 | 600000 | 14400000 | [13 empty] | 24 | 14400000
7 | CD-1 MICE PROCUREMENT |  |  |  | 0 | [14 empty] | 0
8 | Rodent house renovation and construction of preclinical testing lab | NO |  |  | 0 | [14 empty] | 560000
9 | Setting up a production unit at KIPRE |  |  |  | 0 | [14 empty] | 240000
10 | Laboratory renovations | no | 1 | 1500000 | 1500000 | [13 empty] | 1 | 1500000
0
0
0
0
0
0
0
0
0
0
0
| Automatic Lighting System at Herptarium | No. | 1 |  | 0
| CCTV Cameras Installation | No. | 1 |  | 0
| Installation Motion Sensor Cameras | No. | 1 |  | 0
| Installation Smoke detectors | No. | 3 |  | 0
0
0
| HVAC Systems at Herptarium | No. | 2 |  | 0
[5 empty] | 0 | [14 empty] | 0
17.Computer hardware and accessories |  |  |  |  | 0 | [14 empty] | 0
| Alluminium Troys | No. | 4 |  | 0
| Voice Recorder | No. | 10 |  | 0
| External Hards Disk 3TB | No. | 5 | 26000 | 130000
| Digital Cameras | No. | 2 | 490000 | 980000
1 | laptops | nos | 2 | 280000 | 560000 | KSRIC | RFQ | GOK | [10 empty] | 2 | 560000
2 | Projector | nos | 1 | 240000 | 240000 | KSRIC | RFQ | GOK | [10 empty] | 1 | 240000
3 | Tablets | nos | 20 | 90000 | 1800000 | KSRIC | RFQ | GOK | [11 empty] | 960000
4 | Power Bank | nos | 20 |  | 0 | KSRIC | RFQ | GOK | [11 empty] | 0
5 | GPS Communicaton Devices | nos | 10 |  | 0 | KSRIC | RFQ | GOK | [11 empty] | 0
6 | Printer | nos | 2 |  | 0 | KSRIC | RFQ | GOK | [11 empty] | #REF!
7 | computer software | No. | 2 |  | 0 | KSRIC | RFQ | GOK | [11 empty] | 0
8 | High Defination Binoculars | Np. | 10
9 | Desktop computers | nos | 4 | 240000 | 960000 | KSRIC | RFQ | GOK | [11 empty] | 0
10 | laptops | nos | 6 | 280000 | 1680000 | KSRIC | RFQ | GOK
11 | tablets | nos | 6 | 90000 | 540000
12 | External hard disk 3TB | NOS | 3 | 26000 | 78000
13 | M &E tools and software network |  |  |  | 0
14 | NETWORK ASSISTED STORAGE 10TB | nos | 1 |  | 0
15 | Printer EcosystemM3145idn | nos | 1 | 480000 | 480000
16 | Camera | nos | 1 | 490000 | 490000
| laptops | nos | 8 | 280000 | 2240000
| Desktop computers | nos | 2 | 240000 | 480000
| One Digital camera | nos | 1 |  | 0
[5 empty] | 0 | [14 empty] | 0
18.STATIONERIES AND PRINTING |  |  |  |  | 0 | [14 empty] | 0
1 | Flip chart |  |  |  | 0 | [14 empty] | 0
2 | Flip chart stand |  |  |  | 0 | [14 empty] | 0
3 | Roller Banners |  |  |  | 0 | [14 empty] | 0
4 | Tear Drops |  |  |  | 0 | [14 empty] | 0
5 | Printing materials,data collection material and training material | lots | 1 | 8430000 | 8430000 | [13 empty] | 1 | 8430000
6 | printing papers | nos | 40 | 1000 | 40000
7 | Branded pens | pkts | 4 | 2500 | 10000
8 | highlighters | pkts | 4 | 1400 | 5600
9 | Paper flip charts | rolls | 5 | 12000 | 60000
10 | Pencils | pkts | 5 | 1200 | 6000
11 | White out | pcs | 12 | 80 | 960
12 | Yellow stickers | pcs | 10 | 380 | 3800
13 | Box file | pcs | 30 | 380 | 11400
14 | Spring files | pcs | 30 | 95 | 2850
15 | Folders | pcs | 20 | 120 | 2400
16 | Portfolio | pcs | 20 | 970 | 19400
17 | Staplers | pcs | 10 | 490 | 4900
18 | Staple pins | pkts | 10 | 240 | 2400
19 | Thumb pin | pkts | 10 | 120 | 1200
20 | Paper punch | pcs | 4 | 980 | 3920
21 | Binders | pcs | 500 | 480 | 240000
22 | Paper Cutter | pcs | 2 | 12800 | 25600
23 | Standing board | pcs | 1 | 24000 | 24000 | [14 empty] | 0
19.purchase of new motor vehicle | [19 empty] | 0
1 | 4x4 motor vehicle loaded with GPS COMMUNICATION ACCESSORIES | no | 1 | 17000000 | 17000000
2 | Double cabin motor vehicle loaded with GPS communication accessories | no | 1 |  | 0
3 |  |  |  |  | 0
0
0
0
0
20. Electricals |  |  |  |  | 0
1 | Torch | No. | 10 |  | 0 | [14 empty] | 0
[5 empty] | 0 | [14 empty] | 0
0
21.Publicity expenses |  |  |  |  | 0
1 | Media expenses | lots | 1 | 1200000 | 1200000
22.TONERS AND CATRIDGES
1 | Catridges for Ecosystem | nos | 10
0
0
0
23.OFFICE FURNITURE AND EQUIPMENT |  |  |  |  | 0
1 | Office cabinets | nos | 3 | 36000 | 108000
2 | Binding machines | nos | 2 | 64000 | 128000
24. SOFTWARES
1 | N vivo qual Analysis Software License | No. | 5 |  | 0
2 | Graph pad prism software((academic package 10 users package) | No. | 1 | 318000 | 318000
3 | SPSS Software single user | No. | 1 | 157113 | 157113
4 | Turnitin software | No. | 1 | 13250 | 13250
5 | Subscription per year for 100 students | No. | 1 | 397500 | 397500
6 | Geneious software | No. | 1 | 260000 | 260000
[5 empty] | 0 | [14 empty] | 0
245471348