## Sheet1
ANNUAL WORK PLAN 2024- 2025
Programme Name: ……………………………………………………………….
Programme Outcome: ……………………………………………………………….
Sub-Programme Name: ……………………………………………………………….
Delivery Unit/Directorate/Division/Section Name: ……………………………………………………………….
| Results Areas | Main Activities | Sub Activities | Expected Outputs | Performance Indicators | Target | Means of verification | 2024/25 | [11 empty] | Estimated Cost | Approved Budget (Rec & Dev) |  | Off-budget resources |  | Funding Gap
[8 empty] | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | GOK | Source of funding | Amount | Source of funding
5 | Modernization and expansion of infrastructure and equipment for antivenom research and production | Establish/initiate an anti-venom fill & finish facility | Feasibility study | Board visit & Approval | Board Approval
Environmental, Impact Assessment
|  |  | Technology transfer for establishing the Fill & Finish | Skills & technology for antivenom fill & finish acquired
|  |  | Construct antivenom fill & finish facility | Fill & Finish facility Constructed
|  |  | Operationalize fill & finish facility | Fill & Finish facility operationalized
Establish a Snakebite Preclinical rodent & bio-containment facility
|  |  | Construct a snakebite preclinical rodent & bio-containment facility | Facility Construction
Operationalize snakebite preclinical rodent & bio-containment facility
Establish snakebite venom & anti-venom research Laboratories, Coldroom, Offices & conference /training facility
Construct snakebite venom & anti-venom research Laboratories, Coldroom, Offices & conference /training facility
Operationalize snakebite venom & anti-venom research Laboratories, Coldroom, Offices & conference /training facility
|  | Construct pre-clinical animal housing facility at KIPRE for venom research & antivenom production | Construct a horse stable
Construct a camel stable & phlebotomy facility at KALRO Naivasha farm
|  | procure of equipment for snakebite venom & antivenom Research & Development | Procurement of fill & finish equipment & installation | Procurement of fill & finish equipment & installation
Procurement of Laborarory, cold room & phlebetomy facility equipment
Procurement of audio visual equipment
|  |  | Procurement of field vehicles & snakebite ambulances | Field vehicles & snakebite ambulances procured | Number of Field vehicles & snakebite ambulances | 6 | DOF, LPO issued, Delivery Notes
|  |  | Procurement of office furniture & equipment | Office furniture & equipment procured | Number of offices / counters Equipped | 8 | DOF, LPO issued, Delivery notes
|  |  | Procurement of software & licences | Software & licences procured | Number of Software & licences procured | 20 | Licences Issued
|  |  | Procurement of rodent facility equipment | Procurement of rodent facility equipment | Number of offices / counters Equipped | 1 | DOF, LPO issued, Delivery notes
|  |  | Leverage IT infrastructure/ internet expansion & optimization at the new snakebite facilities | IT infrastructure/ internet expansion & optimization at the new snakebite facilities Leveraed | Nimber of offices leveraged | 8 | DOF, LPO issued, Delivery notes
|  | Servicing & Calibration of equipment | Procurement of equipment maintenance services | Equipment maintenance services procured | Number of contracts signed | 5 | Signed Contract
|  |  | Procurement of Insurance services | Insurance services procured | Number of contracts signed | 1 | Signed Contract
6 | Partnership on research and antivenom production | Inittiate partnership on research and antivenom production | Formulate snakebite management guidelines & policies | Policies and Guidelines Fromulated | Number of Policies and uidelines | 2 | Attendance Register
|  |  | Mapping of snakebite partners,stakeholders & collaborators | Partners, Stakeholders and Partners Mapped |  | 3 | Minutes of meeting
|  |  | Acquire statutory obligations and regulations | Statutory Obligations and Regulatons Acquired | Number of permits and Licenses | 3 | Request Letter
|  |  | Establish Strategic patnership & collaborations | Strategic patnership & collaborations Established | Number of Statutory Obligayions and Regulations Acquired | 3 | Request letter
|  | Advocacy for snakebite | Hold Public awareness campaigns | Public awareness campaigns Held | Number of Public Awareness Campains held | 4 | Meeting notices, Photos
|  |  | Develop Information, education & communication materials | Information, education & communication materialsDeveloped | Number of Informatiion, Education and communication materials developed | 6 | DOFs Raised
|  |  | Hold Public barazas to educate communities on snakebite first aid | Hold Public barazas to educate communities on snakebite first aid held | Number of Barazas Held | 10 | Meeting notices, Photos
|  |  | Engage Social media, website & other digital platforms | Social media, website & other digital platforms engaged | Number of Social media, website & other digital platforms Engaged | 3 | Active Social Media Handles, Website
|  |  | Policy engagements | Development of policies | Number of Policies developed | 1 | Policy | [17 empty] | 0
|  |  | Conduct workshops to educate healthcare workers on snakebites | Workshops to educate healthcare workers on snakebites Conducted | Number of Workshops Conducted | 25 | Attandance list, Photos, Venue Bookings
| Total | [18 empty] | 0 | 0 |  | 0 |  | 0