## Sheet1
TABLE 23B: STATUS OF PROJECTS UNDERTAKEN IN FY 2023/24
Sector : State Corporation and SAGAs
Name of Institution : Kenya institute of Primate Research
S/No. | NAME OF THE DEVELOPMENT PROJECT UNDERTAKEN (INCLUDE ALL STALLED PROJECTS,ONGOING AND COMPLETED) | PROJECT CODE | ENVIRONMENTAL IMPACT ASSESSMENT (EIA) (UNDERTAKEN,NOT UNDERTAKEN) | FEASIBILITY STUDIES (UNDERTAKEN,NOT UNDERTAKEN) | DATE OF COMMENCEMENT (DD/MM/YYYY) | EXPECTED DATE OF COMPLETION (DD/MM/YYYY) | STATUS OF COMPLETION (COMPLETED/ONGOING/STALLED) | % RATE OF COMPLETION (0-100) | ACTUAL DATE OF COMPLETION (DD/MM/YYYY) | ESTIMATED PROJECT COST (KSHS) | TOTAL EXPENDITURE ON THE PROJECT (KSHS)
1 | PROPOSED CONSTRUCTION OF BOUNDARY WALL FOR KENYA INSTITUTE OF PRIMATE RESEARCH | W.P. ITEM No.D113RV/2021JOB No.10952A | UNDERTAKEN | UNDERTAKEN | 2023-08-09 | 2024-04-17 | STALLED | 58 | - | 44163895 | 26478560.56
2 | PROPOSED EXTENSION OF OFFICE FOR BOARD CHAIRMAN AND PAYROLL OFFICES AT KENYA INSTITUTE OF PRIMATE RESEARCH | W.P. ITEM No.D113NB/NB/ 2301 JOB No.10847A | NOT UNDERTAKEN | NOT UNDERTAKEN | 2024-04-22 | 2024-12-30 | ONGOING | 98 | 2024-12-30 | 21780635 | 18535411.9
3 | PROPOSED CONSTRUCTION OF PARKING AT KENYA INSTITUTE OF PRIMATE RESEARCH | W.P. ITEM No.D113NB/NB/2102JOB No.11057B | NOT UNDERTAKEN | NOT UNDERTAKEN | 2024-04-22 | 2024-12-30 | ONGOING | 98 | 2024-12-30 | 20554810 | 20203850