Proposed working programme

Institutional data protection governance and compliance implementation retreat

Overall approach

The retreat will be conducted over ten (10) working days using a combination of technical presentations, facilitated plenary sessions, institutional assessments, group work, policy review, process mapping, drafting sessions and validation. The programme will progressively move from establishing a common understanding of the regulatory and institutional context to the development and validation of a practical, costed implementation strategy.

| Day | Theme | Key activities | Principal outputs |
| --- | --- | --- | --- |
| Day 1 | Opening, regulatory orientation and institutional context | Official opening; introduction of retreat objectives and expected outputs; overview of KIPRE's institutional data environment; overview of the Data Protection Act, 2019 and subsidiary regulations; roles of the ODPC, data controller, data processor and DPO; principles of data protection; discussion of KIPRE's current compliance journey | Common understanding of regulatory obligations; agreed retreat methodology and expected outputs |
| Day 2 | Institutional data protection governance and accountability | Review of KIPRE's existing governance arrangements; roles of Management, DPO, directorates, divisions, programmes and projects; review of proposed Data Protection Steering Committee and Data Protection Champion model; identification of institutional responsibilities; governance gap analysis | Draft institutional data protection governance and accountability structure |
| Day 3 | Institutional data-processing and information-flow mapping | Identification of major categories of personal and sensitive personal data; mapping of data collection, processing, storage, access, sharing and disposal; mapping of research, laboratory, clinical, administrative and digital-data workflows; identification of internal and external data recipients; identification of cross-border data flows where applicable | Preliminary institutional data-processing inventory and data-flow maps |
| Day 4 | Compliance assessment, privacy risks and gap analysis | Institutional compliance self-assessment; review of existing controls; identification of legal, governance, technical and operational gaps; assessment of privacy and data-protection risks; prioritisation of critical gaps; identification of areas requiring DPIAs | Institutional data protection compliance gap assessment; preliminary risk register |
| Day 5 | Policy review and harmonisation | Detailed review of KIPRE Data Management and Protection Policy; alignment with the Data Protection Act and applicable regulations; alignment with Institutional Data Governance Framework; review of data classification, access, retention, sharing, security, privacy and accountability provisions; identification of policy gaps | Revised draft Data Management and Protection Policy; policy gap matrix |
| Day 6 | Operational procedures, controls and compliance tools | Development/review of priority SOPs; DPIA procedure; personal-data breach response procedure; data-subject rights request procedure; privacy notice and consent templates; data-sharing/transfer procedures; data-retention and disposal procedures; data-processing inventory/template; compliance monitoring tools | Draft priority SOPs, templates and compliance tools |
| Day 7 | Research, laboratory and health-data protection | Application of data protection requirements to biomedical research; research participant data; health and clinical data; laboratory information; biological and genomic data; secondary use of data; research collaborations; data sharing; publication and dissemination; international collaborations and transfers; DPIA requirements for high-risk processing | Research and laboratory data protection requirements; priority research-related controls and DPIA requirements |
| Day 8 | Data protection compliance implementation strategy | Consolidation of identified gaps and priorities; definition of strategic interventions; development of strategic objectives and implementation pillars; assignment of institutional responsibilities; development of indicators and monitoring mechanisms; sequencing of implementation activities | Draft KIPRE Data Protection Compliance Implementation Strategy |
| Day 9 | Costed implementation work plan | Conversion of strategy into activities and deliverables; assignment of responsible units; timelines and milestones; resource requirements; capacity-building requirements; ICT and infrastructure requirements; development of budget estimates; identification of immediate, medium-term and longer-term actions | Draft costed implementation work plan and implementation matrix |
| Day 10 | Validation, adoption and way forward | Presentation of retreat outputs; technical review; plenary validation; refinement of governance structure, policy, SOPs, strategy and work plan; confirmation of institutional responsibilities; agreement on monitoring and reporting arrangements; identification of immediate 30-, 60- and 90-day actions; closing session | Validated implementation strategy; validated work plan; agreed immediate actions; retreat report and recommendations |

Detailed daily working programme

Day 1 — Opening, regulatory orientation and institutional context

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Registration and arrival | Secretariat |
| 09:00–09:30 | Official opening and remarks | Director General / Management |
| 09:30–10:00 | Introduction to the retreat: purpose, objectives, methodology and expected outputs | DSAS / DPO |
| 10:00–10:30 | Tea break |  |
| 10:30–11:30 | KIPRE's institutional data environment and emerging data-governance requirements | DSAS |
| 11:30–13:00 | Data Protection Act, 2019 and applicable regulations: institutional obligations | Resource person / ODPC |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | Principles of data protection and practical application in institutional settings | Resource person |
| 15:00–15:30 | Roles of the data controller, data processor, DPO and institutional data users | ODPC / DPO |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | KIPRE's current data protection compliance journey | DPO |
| 16:45–17:00 | Questions, reflections and summary of Day 1 | Facilitator |

Day 2 — Governance and accountability

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Recap of Day 1 | Secretariat |
| 09:00–10:00 | Institutional data protection governance principles | Resource person |
| 10:00–10:30 | KIPRE's current governance arrangements | DPO / DSAS |
| 10:30–10:45 | Tea break |  |
| 10:45–12:00 | Proposed Data Protection Steering Committee and Data Protection Champion framework | DPO |
| 12:00–13:00 | Roles and responsibilities across directorates, divisions, programmes and projects | Facilitator |
| 13:00–14:00 | Lunch |  |
| 14:00–15:30 | Group work: institutional accountability mapping | Working groups |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Group presentations and plenary discussion | Working groups |
| 16:45–17:00 | Consolidation of governance structure | Facilitator |

Day 3 — Data-processing and information-flow mapping

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Recap and introduction to data mapping | DSAS / DPO |
| 09:00–10:30 | Institutional data-processing inventory: concepts and methodology | DSAS |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group work: mapping institutional data-processing activities | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:30 | Data-flow mapping: collection, processing, storage, sharing and disposal | DSAS / ICT |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Group presentations and identification of common institutional data flows | Working groups |
| 16:45–17:00 | Consolidation of institutional data-processing inventory | Secretariat |

Day 4 — Compliance assessment and risk analysis

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Recap of institutional data mapping | Facilitator |
| 09:00–10:00 | Data protection compliance assessment methodology | DPO / Resource person |
| 10:00–10:30 | Existing KIPRE policies, controls and compliance mechanisms | DPO |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group assessment of compliance gaps | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | Privacy and data-protection risk identification | Internal Audit / DPO |
| 15:00–15:30 | Risk prioritisation and treatment principles | Facilitator |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Development of institutional compliance gap matrix and risk register | Working groups |
| 16:45–17:00 | Plenary validation | Facilitator |

Day 5 — Policy review and harmonisation

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Review of compliance gaps | Secretariat |
| 09:00–10:00 | Review of KIPRE Data Management and Protection Policy | DPO / DSAS |
| 10:00–10:30 | Policy alignment with legal and regulatory requirements | Legal / Resource person |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group review of policy sections | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:30 | Harmonisation with the Institutional Data Governance Framework | DSAS |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Consolidation of proposed policy amendments | Drafting team |
| 16:45–17:00 | Agreement on policy revision actions | Plenary |

Day 6 — SOPs, templates and compliance tools

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Recap and prioritisation of operational controls | Facilitator |
| 09:00–10:00 | Data Protection Impact Assessment procedure | DPO / Resource person |
| 10:00–10:30 | Personal-data breach detection, reporting and response | DPO / ICT |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group drafting of priority SOPs and templates | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | Data-subject rights request procedure | DPO / Legal |
| 15:00–15:30 | Data retention, disposal and records management | Registry / DPO |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Data-sharing, transfer and third-party processing controls | DPO / Legal / ICT |
| 16:45–17:00 | Consolidation and allocation of post-retreat drafting responsibilities | Facilitator |

Day 7 — Research, laboratory and health-data protection

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Recap of operational controls | Secretariat |
| 09:00–10:00 | Data protection in biomedical and health research | Research representative / Resource person |
| 10:00–10:30 | Protection of research participant and clinical data | Research / Ethics |
| 10:30–10:45 | Tea break |  |
| 10:45–12:00 | Laboratory, biological and genomic data governance | Laboratory / DSAS |
| 12:00–13:00 | Secondary use, research collaboration and data sharing | Research / DPO |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | International data sharing and cross-border data transfers | Legal / DPO |
| 15:00–15:30 | DPIAs for research and other high-risk processing | DPO |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Group exercise: research data protection scenarios | Working groups |
| 16:45–17:00 | Plenary discussion and recommendations | Facilitator |

Day 8 — Development of the Data Protection Compliance Implementation Strategy

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Review of identified gaps and priority risks | Facilitator |
| 09:00–10:00 | Strategy development framework | DSAS / DPO |
| 10:00–10:30 | Proposed strategic pillars and institutional priorities | Facilitator |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group work: strategic objectives, interventions and outputs | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:30 | Development of implementation indicators and monitoring mechanisms | Planning / M&E |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Consolidation of strategy | Drafting team |
| 16:45–17:00 | Plenary review | Participants |

Day 9 — Costed implementation work plan

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Review of draft implementation strategy | Facilitator |
| 09:00–10:00 | Translating strategic priorities into activities and deliverables | Planning / DSAS |
| 10:00–10:30 | Responsibility assignment and implementation sequencing | Facilitator |
| 10:30–10:45 | Tea break |  |
| 10:45–13:00 | Group development of implementation matrix | Working groups |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | Resource and capacity requirements | Finance / HR / ICT |
| 15:00–15:30 | Costing methodology and budget development | Finance / Planning |
| 15:30–15:45 | Tea break |  |
| 15:45–16:45 | Consolidation of costed implementation work plan | Drafting team |
| 16:45–17:00 | Review and agreement on outstanding items | Plenary |

Day 10 — Validation, adoption and way forward

| Time | Session | Lead/Facilitator |
| --- | --- | --- |
| 08:30–09:00 | Review of retreat outputs | Secretariat |
| 09:00–10:30 | Presentation of the Institutional Data Protection Governance Framework | DSAS / DPO |
| 10:30–10:45 | Tea break |  |
| 10:45–12:00 | Presentation of compliance assessment and priority gaps | DPO |
| 12:00–13:00 | Presentation of Data Protection Compliance Implementation Strategy | Drafting team |
| 13:00–14:00 | Lunch |  |
| 14:00–15:00 | Presentation of costed implementation work plan | Planning / Finance |
| 15:00–15:30 | Plenary validation and amendments | Participants |
| 15:30–15:45 | Tea break |  |
| 15:45–16:15 | Agreement on immediate 30-, 60- and 90-day actions | Management / DPO |
| 16:15–16:45 | Confirmation of governance, reporting and monitoring arrangements | Management / DPO |
| 16:45–17:00 | Closing remarks and way forward | Director General / Management |

Core retreat deliverables

At the conclusion of the retreat, the following institutional outputs should be available for finalisation and submission to Management:

- Institutional data protection compliance assessment report.

- Institutional data-processing inventory and preliminary data-flow maps.

- Institutional data protection risk register and compliance gap matrix.

- Revised KIPRE Data Management and Protection Policy.

- Institutional data protection governance and accountability structure.

- Data Protection Champion framework.

- Priority data protection SOPs and compliance templates.

- DPIA procedure and supporting tools.

- Data-breach management and response framework.

- Data-subject rights management procedure.

- Data-sharing and third-party processing controls.

- KIPRE Data Protection Compliance Implementation Strategy.

- Costed implementation work plan.

- Monitoring, evaluation and reporting framework.

- Immediate 30-, 60- and 90-day implementation action plan.

- Final retreat report containing recommendations for Management.